## INV-Gantt
Customer | INV_Number | INV_Model | Project_Name | Unit_Qty | TP_Kinds | Qualify_Cycles | Status | TP_Cat | Trial_Run_Type | TP_Vendor | TP_Key_Parameter | Lenovo_TP_PN | Compal_TP_PN | Issue_Link | Remark | Attend_Time | Get_INV | Year | Month | Test_Start | Test_End
C38(AIO) | TBD | EOC31 | EOC31 | 6 | 1 | Re-Qualify | Testing | SSD | 2nd source | Toshiba | SSD_M 128G N4SP2 KBG40ZMT128G C38(AIO) |  | DD900017P50 | ECR123456 |  | 17.9 |  |  | Jul
C38(AIO) | TBD | EOC30 | EOC30 | 6 | 12 | Re-Qualify | Testing | SSD | 2nd source | Toshiba | SSD_M 128G N4SP2 KBG40ZMT128G C38(AIO) |  | DD900017P50 |  |  | 17.9 |  |  | Jul
C38(AIO) | TBD | FLY00 | FLY00 | 24 | 1 |  | Planning | CPU | New source | Intel | I5-10200H 2.4/4C/8M Match to G1B, G1R,G2R,G3R VGA | SSA1B09974 |  |  |  | 1 |  |  |  | 2020-07-04 | 2020-07-16
A39 | TBD | FLY00 | FLY00 | 24 | 1 |  | Planning | CPU | New source | Intel | I7-10870H 2.2G/8C/16M Match to G1B, G1R,G2R,G3R VGA | SSA1B09975 |  |  |  | 1 |  |  |  | 2020-07-04 | 2020-07-16
A39 | TBD | FOC70 | FOC70 | 6 | 1 | New-Qualify | Pass | KB/Mouse | 2nd source | G-Tech | G-Tech Eos 2.4G KB&MC Kit Black US English 103P |  | SKM1A25395 |  |  | 19.9 |  |  | Jun | 2020-07-04 | 2020-07-16
A39 | TBD | FOY11 | FOY11 | 6 | 1 | New-Qualify | Pass | RAM | 2nd source | Micron | DDR4 MODU MTA8ATF2G64HZ-3G2E1 16G/3200 |  | PK05400A800 |  |  | 47.1 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | FOY10 | FOY10 | 6 | 1 | New-Qualify | Pass | RAM | 2nd source | Micron | DDR4 MODU MTA8ATF2G64HZ-3G2E1 16G/3200 |  | PK05400A800 |  |  | 47.1 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | FOY11 | FOY11 | 6 | 1 | New-Qualify | Pass | RAM | 2nd source | Micron | DDR4 MODU MTA4ATF1G64HZ-3G2E1 8G/3200 |  | PK05400AW00 |  |  | 47.1 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | FOY10 | FOY10 | 6 | 1 | New-Qualify | Pass | RAM | 2nd source | Micron | DDR4 MODU MTA4ATF1G64HZ-3G2E1 8G/3200 |  | PK05400AW00 |  |  | 47.1 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | FOY11 | FOY11 | 6 | 1 | New-Qualify | Pass | SSD | 2nd source | Hynix | SSD_M 512G N4SP4 HFM512GD3HX015N C38(AIO) |  | DD90001AV20 |  |  | 61.9 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | FOY10 | FOY10 | 6 | 1 | New-Qualify | Pass | SSD | 2nd source | Hynix | SSD_M 512G N4SP4 HFM512GD3HX015N C38(AIO) |  | DD90001AV20 |  |  | 61.9 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | FOY11 | FOY11 | 6 | 1 | New-Qualify | Pass | SSD | 2nd source | Hynix | SSD_M 256G N4SP4 HFM256GD3HX015N C38(AIO) |  | DD90001AU20 |  |  | 61.9 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | FOY10 | FOY10 | 6 | 1 | New-Qualify | Pass | SSD | 2nd source | Hynix | SSD_M 256G N4SP4 HFM256GD3HX015N C38(AIO) |  | DD90001AU20 |  |  | 61.9 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | FOY11 | FOY11 | 6 | 1 | New-Qualify | Fail | SSD | 2nd source | Hynix | SSD_M 128G N4SP4 HFM128GD3HX015N C38(AIO) |  | DD90001AW00 |  |  | 61.9 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | FOY10 | FOY10 | 6 | 1 | New-Qualify | Fail | SSD | 2nd source | Hynix | SSD_M 128G N4SP4 HFM128GD3HX015N C38(AIO) |  | DD90001AW00 |  |  | 61.9 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | FOY21 | FOY21 | 6 | 1 | New-Qualify | Pass | RAM | 2nd source | Micron | DDR4 MODU MTA8ATF2G64HZ-3G2E1 16G/3200 |  | PK05400A800 |  |  | 47.1 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | FOY20 | FOY20 | 6 | 1 | New-Qualify | Pass | RAM | 2nd source | Micron | DDR4 MODU MTA8ATF2G64HZ-3G2E1 16G/3200 |  | PK05400A800 |  |  | 47.1 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | FOY21 | FOY21 | 6 | 1 | New-Qualify | Pass | RAM | 2nd source | Micron | DDR4 MODU MTA4ATF1G64HZ-3G2E1 8G/3200 |  | PK05400AW00 |  |  | 47.1 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | FOY20 | FOY20 | 6 | 1 | New-Qualify | Pass | RAM | 2nd source | Micron | DDR4 MODU MTA4ATF1G64HZ-3G2E1 8G/3200 |  | PK05400AW00 |  |  | 47.1 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | FOY21 | FOY21 | 6 | 1 | New-Qualify | Pass | SSD | 2nd source | Hynix | SSD_M 512G N4SP4 HFM512GD3HX015N C38(AIO) |  | DD90001AV20 |  |  | 61.9 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | FOY20 | FOY20 | 6 | 1 | New-Qualify | Pass | SSD | 2nd source | Hynix | SSD_M 512G N4SP4 HFM512GD3HX015N C38(AIO) |  | DD90001AV20 |  |  | 61.9 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | FOY21 | FOY21 | 6 | 1 | New-Qualify | Pass | SSD | 2nd source | Hynix | SSD_M 256G N4SP4 HFM256GD3HX015N C38(AIO) |  | DD90001AU20 |  |  | 61.9 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | FOY20 | FOY20 | 6 | 1 | New-Qualify | Pass | SSD | 2nd source | Hynix | SSD_M 256G N4SP4 HFM256GD3HX015N C38(AIO) |  | DD90001AU20 |  |  | 61.9 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | FOY21 | FOY21 | 6 | 1 | New-Qualify | Pass | SSD | 2nd source | Hynix | SSD_M 128G N4SP4 HFM128GD3HX015N C38(AIO) |  | DD90001AW00 |  |  | 61.9 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | FOY20 | FOY20 | 6 | 1 | New-Qualify | Pass | SSD | 2nd source | Hynix | SSD_M 128G N4SP4 HFM128GD3HX015N C38(AIO) |  | DD90001AW00 |  |  | 61.9 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | FOC60 | FOC60 | 8 | 1 | New-Qualify | Pass | KB/Mouse | 2nd source | G-Tech | G-Tech Eos 2.4G KB&MC Kit Black US English 103P |  | SKM1A25395 |  |  | 19.9 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | FOC60 | FOC60 | 8 | 1 | New-Qualify | Pass | SSD | 2nd source | Toshiba | SSD_M 128G N4SP2 KBG40ZMT128G C38(AIO) |  | DD900017P50 |  |  | 61.9 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | FOC60 | FOC60 | 8 | 1 | New-Qualify | Pass | SSD | 2nd source | UMIS | SSD_M 512G N4SP4 RPJTJ512MEE1OWX C38(AIO) |  | DD900016Y20 |  |  | 61.9 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | FOC51 | FOC51 | 8 | 1 | New-Qualify | Pass | KB/Mouse | 2nd source | G-Tech | G-Tech Eos 2.4G KB&MC Kit Black US English 103P |  | SKM1A25395 |  |  | 19.9 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | FOC51 | FOC51 | 8 | 1 | New-Qualify | Pass | SSD | 2nd source | Toshiba | SSD_M 512G N4SP4 KBG40ZNT512G C38(AIO) |  | DD900017R20 |  |  | 61.9 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | FOC51 | FOC51 | 8 | 1 | New-Qualify | Pass | SSD | 2nd source | Toshiba | SSD_M 256G KBG40ZNT256G F:0104AELA C38(AIO) |  | DD900017Q20 |  |  | 61.9 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | FOC51 | FOC51 | 8 | 1 | New-Qualify | Pass | SSD | 2nd source | UMIS | SSD_M 256G N4SP4 RPJTJ256MEE1OWX C38(AIO) |  | DD900016W20 |  |  | 61.9 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | FOC81 | FOC81 | 6 | 1 |  | Planning | RAM | 2nd source | Micron | DDR4 MODU MTA4ATF1G64HZ-3G2E1 8G C38(AIO) ! | SM30N76643 | PK05400AW20 | [6 empty] | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | FOC80 | FOC80 | 6 | 1 |  | Planning | RAM | 2nd source | Micron | DDR4 MODU MTA4ATF1G64HZ-3G2E1 8G C38(AIO) ! | SM30N76643 | PK05400AW20 | [6 empty] | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | EOC21 | EOC21 | 6 | 1 |  | Planning | RAM | 2nd source | Micron | DDR4 MODU MTA4ATF1G64HZ-3G2E1 8G C38(AIO) ! | SM30N76643 | PK05400AW20 | [6 empty] | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | EOC20 | EOC20 | 6 | 1 |  | Planning | RAM | 2nd source | Micron | DDR4 MODU MTA4ATF1G64HZ-3G2E1 8G C38(AIO) ! | SM30N76643 | PK05400AW20 | [6 empty] | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | EOC30 | EOC30 | 6 | 1 |  | Planning | RAM | 2nd source | Micron | DDR4 MODU MTA4ATF1G64HZ-3G2E1 8G C38(AIO) ! | SM30N76643 | PK05400AW20 | [6 empty] | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | EOC31 | EOC31 | 6 | 1 |  | Planning | RAM | 2nd source | Micron | DDR4 MODU MTA4ATF1G64HZ-3G2E1 8G C38(AIO) ! | SM30N76643 | PK05400AW20 | [6 empty] | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | EOS11 | EOS11 | 6 | 1 | Re-Qualify | Testing | RAM | 2nd source | Micron | DDR4 MODU MTA4ATF1G64HZ-3G2E1 8G C38(AIO) ! | SM30N76643 | PK05400AW20 |  |  | 47.1 |  |  | Jul | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | EOS10 | EOS10 | 6 | 1 | Re-Qualify | Testing | RAM | 2nd source | Micron | DDR4 MODU MTA4ATF1G64HZ-3G2E1 8G C38(AIO) ! | SM30N76643 | PK05400AW20 |  |  | 47.1 |  |  | Jul | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | EOS11 | EOS11 | 8 | 1 | New-Qualify | Planning | SSD | 2nd source | Hynix | SSD_M 128G N4SP4 HFM128GD3HX015N C38(AIO) ! | SSS0L24811 | DD90001AW10 | [6 empty] | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | EOS10 | EOS10 | 8 | 1 | New-Qualify | Planning | SSD | 2nd source | Hynix | SSD_M 128G N4SP4 HFM128GD3HX015N C38(AIO) ! | SSS0L24811 | DD90001AW10 | [6 empty] | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | EOS11 | EOS11 | 8 | 1 | New-Qualify | Testing | SSD | 2nd source | Hynix | SSD_M 256G N4SP4 HFM256GD3HX015N C38(AIO) ! | SSS0L24812 | DD90001AU30 |  |  | 61.9 |  |  | Jul | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | EOS10 | EOS10 | 8 | 1 | New-Qualify | Testing | SSD | 2nd source | Hynix | SSD_M 256G N4SP4 HFM256GD3HX015N C38(AIO) ! | SSS0L24812 | DD90001AU30 |  |  | 61.9 |  |  | Jul | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | EOS11 | EOS11 | 8 | 1 | New-Qualify | Pass | SSD | 2nd source | Hynix | SSD_M 512G N4SP4 HFM512GD3HX015N C38(AIO) ! | SSS0L24813 | DD90001AV30 |  |  | 61.9 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | EOS10 | EOS10 | 8 | 1 | New-Qualify | Pass | SSD | 2nd source | Hynix | SSD_M 512G N4SP4 HFM512GD3HX015N C38(AIO) ! | SSS0L24813 | DD90001AV30 |  |  | 61.9 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(AIO) | INV_O2060100 | FOC20 | FOC20 | 8 | 1 | Re-Qualify | Pass | SSD+Opante | 2nd source | Intel | OPT_H 512G+32G HBRPEKNX0202AL F:33 C38(AIO)! |  | DD900012Q80 |  |  | 46.4 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2061210 | ELAC1 | ELAC1 | 5 | 1 | New-Qualify | Pass | ME | 2nd Source | 金凌 | ELAC1_LCD_PANEL_ADHESIVE_L/ELAC1_LCD_PANEL_ADHESIVE_R |  | EL2G3000H00EL2G3000I00 |  |  | 2 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2061220 | ELAC2 | ELAC2 | 5 | 1 | New-Qualify | Pass | ME | 2nd Source | 金凌 | ELAC1_LCD_PANEL_ADHESIVE_L/ELAC1_LCD_PANEL_ADHESIVE_R |  | EL2G3000H00EL2G3000I00 |  |  | 2 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(NB) | TBD | FLY00 | FLY00 | 12 | 1 | New-Qualify | Pending | CPU | 2nd Source | Intel | i7-10875H CPU+ G1B(RTX2060) + HP (heat pipe)thermal solution |  |  | Click here |  | 258.7 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(NB) | TBD | FLMA0 | FLMA0 | 12 | 2 |  | Planning | RAM | New source | Micron | S IC D4 16G/3200 MT40A1G16KD-062E:E C38! | SM30N76641 | SA0000D3U10 |  |  | 1 |  |  | Jul | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | EOC21 | EOC21 | 6 | 1 | New-Qualify | Pass | SSD | 2nd source | WD | SSD_M 512G N4SP4 SDBPMPZ-512G-1001 C38(AIO) | SSS0L24786 | DD900019D00 |  |  | 61.9 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | EOC20 | EOC20 | 6 | 1 | New-Qualify | Pass | SSD | 2nd source | WD | SSD_M 512G N4SP4 SDBPMPZ-512G-1001 C38(AIO) | SSS0L24786 | DD900019D00 |  |  | 61.9 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | EOC21 | EOC21 | 6 | 1 | New-Qualify | Pass | SSD | 2nd source | WD | SSD_M 256G N4SP4 SDBPMPZ-256G-1001 C38(AIO) | SSS0L25785 | DD900019C00 |  |  | 61.9 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(NB) | TBD | FLMS0 | FLMS0 | 12 | 1 |  | Planning | EE | 2nd source | REALTEK | S IC RTS5457U-GRT QFN 32P TYPE-C CTRL |  | SA0000DRW00 |  | PD IC change | 1 |  |  |  | 2020-07-04 | 2020-07-16
C38(NB) | TBD | FLMA0 | FLMA0 | 12 | 1 |  | Planning | EE | 2nd source | REALTEK | S IC RTS5457U-GRT QFN 32P TYPE-C CTRL |  | SA0000DRW00 |  | PD IC change | 1 |  |  | Jul | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2060270 | FL5C5 | FL5C5 | 10 | 1 | New-Qualify | Pass | Package | design change | 裕同/申健 | PAPER PAD 2D5 ACC BOX SP10S95768 |  | HE2D5000200 |  |  | 3 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | EOC20 | EOC20 | 6 | 1 | New-Qualify | Pass | SSD | 2nd source | WD | SSD_M 256G N4SP4 SDBPMPZ-256G-1001 C38(AIO) | SSS0L25785 | DD900019C00 |  |  | 61.9 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2060040 | EL432 | EL432532 | 5 | 1 | New-Qualify | Pass | RAM | 2nd Source | Micron | DDR4 MODU MTA4ATF1G64HZ-3G2E1 8G/3200 | SM30N76643 | PK05400AW00 |  |  | 37.4 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2060050 | EL532 | EL432532 | 5 | 1 | New-Qualify | Pass | RAM | 2nd Source | Micron | DDR4 MODU MTA4ATF1G64HZ-3G2E1 8G/3200 | SM30N76643 | PK05400AW00 |  |  | 37.4 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(NB) | TBD | FLY00 | FLY00 | 10 | 11 |  | Planning | EE | design change |  | PCB R1B plus for fin lighting left and right module have heterochromatic issue |  |  |  |  | 1 |  |  |  | 2020-07-04 | 2020-07-16
C38(NB) | TBD | FLY00 | FLY00 | 10 | 1 |  | Planning | EE | 2nd Source | TOPSUN | S COIL 3.3UH 20% STPI1004-3R3M-E2-TW 10A |  | SH00001ZL00 |  |  | 1 |  |  |  | 2020-07-04 | 2020-07-16
C38(NB) | TBD | FLY00 | FLY00 | 10 | 2 |  | Planning | EE | 2nd Source | TOPSUN | S COIL 2.2UH 20% SHPI0402-2R2M-HF-TW 3A |  | SH00001VY00 |  |  | 1 |  |  |  | 2020-07-04 | 2020-07-16
C38(NB) | TBD | FLY00 | FLY00 | 10 | 3 |  | Planning | EE | 2nd Source | TOPSUN | S COIL 1UH +-20% STPI0503-1R0M-E1-TW 8A |  | SH000020L00 |  |  | 1 |  |  |  | 2020-07-04 | 2020-07-16
C38(NB) | TBD | FLY00 | FLY00 | 10 | 4 |  | Planning | EE | 2nd Source | TOPSUN | S COIL 1UH +-20% STPI0603-1R0M-E1-TW 11A |  | SH00001ZQ00 |  |  | 1 |  |  |  | 2020-07-04 | 2020-07-16
C38(NB) | TBD | FLY00 | FLY00 | 10 | 5 |  | Planning | EE | 2nd Source | TAI-TECH | S COIL 1UH +-20% VMPI0724AR-1R0M-Z01 11A |  | SH00000LP00 |  |  | 1 |  |  |  | 2020-07-04 | 2020-07-16
C38(NB) | TBD | FLY00 | FLY00 | 10 | 6 |  | Planning | EE | 2nd Source | TOPSUN | S COIL 1UH +-20% STPI0402-1R0M-HF-TW 5A |  | SH00001W200 |  |  | 1 |  |  |  | 2020-07-04 | 2020-07-16
C38(NB) | TBD | FLY00 | FLY00 | 10 | 7 |  | Planning | EE | 2nd Source | TOPSUN | S COIL 3.3UH 20% STPI0603-3R3M-E7-TW 6A |  | SH000021R00 |  |  | 1 |  |  |  | 2020-07-04 | 2020-07-16
C38(NB) | TBD | FLY00 | FLY00 | 10 | 8 |  | Planning | EE | 2nd Source | WILLAS | S SCH DIO BAS40W-05-TH‐WS SOT-323 |  | SCS0000GI00 |  |  | 1 |  |  |  | 2020-07-04 | 2020-07-16
C38(NB) | TBD | FLY00 | FLY00 | 10 | 9 |  | Planning | EE | 2nd Source | APAQ | S POLY C 470U 2V M D2 ESR9M ACAH H1.9 |  | SGA0000BK00 |  |  | 1 |  |  |  | 2020-07-04 | 2020-07-16
C38(NB) | TBD | FLY00 | FLY00 | 10 | 10 |  | Planning | EE | 2nd Source | GUOGUANG | S POLY C 560U 2V M D2 ESR6M 700 H1.9 |  | SGA0000DK00 |  |  | 1 |  |  |  | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2060020 | ELAV5 | ELAV4V5 | 20 | 1 | New-Qualify | Pass | Package | design change | 裕同/申健 | paper pad design change PAPER PAD 2D5 ACC BOX SP10S95768 |  | HE2D5000200 |  |  | 3 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(NB) | DCR_N2060031 | FLMA0 | FLMA0 | 12 | 1 | New-Qualify | Conditional Pass | EE | 2nd source | TAITIEN | S CRYSTAL 32.768KHZ 9PF 06172-W-114-3 |  | SJ100013000 | Click here |  | 19.3 |  |  | May | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | EOC21 | EOC21 | 6 | 1 | New-Qualify | Pass | SSD | 2nd source | UMIS | SSD_M 256G N4SP4 RPJTJ256MEE1OWX C38(AIO) | SSS0L25189 | DD900016W20 |  |  | 61.9 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | EOC20 | EOC20 | 6 | 1 | New-Qualify | Pass | SSD | 2nd source | UMIS | SSD_M 256G N4SP4 RPJTJ256MEE1OWX C38(AIO) | SSS0L25189 | DD900016W20 |  |  | 61.9 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | EOC21 | EOC21 | 6 | 1 | New-Qualify | Pass | SSD | 2nd source | UMIS | SSD_M 512G N4SP4 RPJTJ512MEE1OWX C38(AIO) | SSS0L25190 | DD900016Y20 |  |  | 61.9 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | EOC20 | EOC20 | 6 | 1 | New-Qualify | Pass | SSD | 2nd source | UMIS | SSD_M 512G N4SP4 RPJTJ512MEE1OWX C38(AIO) | SSS0L25190 | DD900016Y20 |  |  | 61.9 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2052480 | FLY00 | FLY00 | 2 | 1 | New-Qualify | Pass | Keyborad | F/W Change |  | ITE FW Update |  |  |  |  | 7 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2060290 | FLY00 | FLY00 | 13 | 1 | New-Qualify | Conditional Pass | Thermal Module | 2nd Source | Microloop | FLY00_DIS_2080_THM_ASSY_DE_MC |  | AT2VH004DQ0 | Click here |  | 19.3 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2060550 | FLY00 | FLY00 | 8 | 2 | New-Qualify | Conditional Pass | Thermal Module | 2nd Source | Microloop | FLY00_DIS_2070_THM_ASSY_DE_MC |  | AT2VH003DQ0 | Click here |  | 19.3 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2060560 | FLY00 | FLY00 | 8 | 3 | New-Qualify | Conditional Pass | Thermal Module | 2nd Source | Microloop | FLY00_DIS_2060B_THM_ASSY_VC_DE_MC |  | AT2VH00DDQ0 | Click here |  | 19.3 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(NB) | TBD | ELAC1 | ELAC1 | 2 | 2 |  | Planning | Panel | 2nd Source | IVO | LCD_LED_TS R140NWF5 RC H:1.1 FHD AG C38 |  | AC60001PA20 |  |  | 1 |  |  |  | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2052280 | FL436 | FL436536 | 10 |  | New-Qualify | Testing | package | Desgin Change | 博琛 | EPE CUSHION desgin change |  |  |  |  | 3 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2060010 | FLZ04 | FLZ04 | 10 | 1 | New-Qualify | Pass | package | New source | ShenJian | PAPER PAD 2D5 ACC BOX SP10S95768 | SP10S95768 | HE2D5000200 |  |  | 3 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2060480 | FLMS0 | FLMS0 | 10 | 1 | New-Qualify | Pass | EE | FW Change | Realtek | Realtek PD RTS5457V FW: V07 S IC RTS5457V-GRT TYPE-C CTRL 0X0128BD14 |  | SA0000CY690 |  | PD FW update | 103.2 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(NB) | TBD | FLMA0 | FLMA0 | 12 | 1 | New-Qualify | Conditional Pass | EE | FW Change | Realtek | Realtek PD RTS5457V FW: V06 S IC RTS5457V-GRT TYPE-C CTRL 0X01293D27 |  | SA0000CY6A0 | Click here | PD FW update | 103.2 |  |  | May | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2060740 | GLY5U | GLY5U | 12 | 1 | New-Qualify | Pending | RAM | 2nd Source | Hynix | S IC D4 32G/3200 H5ANBG6NAMR-XNC C38 ! | SM30N76626 | SA0000DAU20 | Click here |  | 37.4 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(NB) | TBD | GLY5U | GLY5U | 16 | 1 |  | Planning | CPU | 2nd Source | Intel | Intel i9-10980HK 2.4G/8C/16M S IC CL8070104502004 SRH8T R1 2.4G FCBGA | SSA0X88979 | SA0000DCE10 |  |  | 1 |  |  |  | 2020-07-04 | 2020-07-16
C38(NB) | TBD | GLY5U | GLY5U | 10 | 1 |  | Planning | Battery | 2nd Source | Celxpert | CP/B L19C4PG0 15.36V60Wh4cellbty BATT CP BY 4S1P 3.97AH 8 BIS3 2RY C38 | SB10W67271 | GC02002XI00 |  |  | 1 |  |  |  | 2020-07-04 | 2020-07-16
C38(NB) | TBD | GLY5U | GLY5U | 14 | 1 |  | Planning | Panel | 2nd Source | BOE | LCD_LED_M NE156QUM-N6A V3.1 UHD AG S C38 | SD10Y68491 | AC60001PIC0 |  |  | 1 |  |  |  | 2020-07-04 | 2020-07-16
C38(AIO) | INV_O2050080 | FOC10 | FOC10 | 4 | 1 | New-Qualify | Pass | ME | 2nd source | M_OTHER | CARTON 2TL COLOURED SP10Q99380, A.3 (Design) |  | HB2TL000200 |  |  | 20 |  |  | May | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2052130 | FLMS0 | FLMS0 | 10 | 1 | New-Qualify | Fail | panel | design change | BOE+鼎興/日昌 | LCD_LED_M NV140FHM-N66 V8.0 FHD AG C38! FLMS0_LCD_COVER_SPONGE_BTM_P24 (change A cover sponge to panel) |  | AC60001XY50 FH2UZ000Y00 | Click here |  | 65.8 |  |  | May | 2020-07-04 | 2020-07-16
C38(NB) | TBD | FLMS0 | FLMS0 | 10 | 1 |  | Planning | panel | design change | INX+鼎興/日昌 | change A cover sponge to panel |  |  |  |  | 1 |  |  |  | 2020-07-04 | 2020-07-16
C38(NB) | TBD | FLMS0 | FLMS0 | 10 | 1 |  | Planning | panel | design change | AUO+鼎興/日昌 | change A cover sponge to panel 2.4t |  |  |  |  | 1 |  |  |  | 2020-07-04 | 2020-07-16
C38(NB) | TBD | FLMA0 | FLMA0 | 12 | 1 |  | Planning | EE | 2nd source | TAITIEN | S CRYSTAL 32.768KHZ 9PF 06172-W-114-3 |  | SJ100013000 |  |  | 1 |  |  |  | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | EOS11 | EOS11 | 6 | 1 | Re-Qualify | Pass | RAM | 2nd source | Micron | DDR4 MODU MTA8ATF2G64HZ-3G2E1 16G C38(AIO) ! | SM30N76644 | PK05400A820 |  |  | 47.1 |  |  | May | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | EOS10 | EOS10 | 6 | 1 | Re-Qualify | Pass | RAM | 2nd source | Micron | DDR4 MODU MTA8ATF2G64HZ-3G2E1 16G C38(AIO) ! | SM30N76644 | PK05400A820 |  |  | 47.1 |  |  | May | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2051330 | FLMA0 | FLMA0 | 16 | 1 | New-Qualify | Fail | CPU | 2nd source | AMD | 4800U S IC RYZEN7 100-000000082 1.8G BGA APU |  | SA0000D1750 | Click here |  | 258.7 |  |  | May | 2020-07-04 | 2020-07-16
C38(NB) | TBD | FLMS0 | FLMS0 | 12 | 1 |  | Planning | Camera | New source | Chicony | CAMERA M CNFKH18 CHICONY 1M 2MIC S VID: 04F2; PID:B6EE; F/W:2721 | SC20Z72238 | PK40001R500 |  | new lens | 1 |  |  |  | 2020-07-04 | 2020-07-16
C38(NB) | TBD | FLMS0 | FLMS0 | 12 | 1 |  | Planning | Camera | New source | Bison | CAMERA M BNLB19KSE BISON 1M 2MIC S VID: 5986; PID:2137; F/W:5604 | SC20Z72236 | PK40001R600 |  | new lens | 1 |  |  |  | 2020-07-04 | 2020-07-16
C38(NB) | TBD | FLMA0 | FLMA0 | 12 | 1 |  | Planning | Camera | New source | Chicony | CAMERA M CNFKH18 CHICONY 1M 2MIC S VID: 04F2; PID:B6EE; F/W:2721 | SC20Z72238 | PK40001R500 |  | new lens | 1 |  |  |  | 2020-07-04 | 2020-07-16
C38(NB) | TBD | FLMA0 | FLMA0 | 12 | 1 |  | Planning | Camera | New source | Bison | CAMERA M BNLB19KSE BISON 1M 2MIC S VID: 5986; PID:2137; F/W:5604 | SC20Z72236 | PK40001R600 |  | new lens | 1 |  |  |  | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2050790 | FLIC7 | FLIC7 | 10 | 1 | New-Qualify | Pass | TPM | F/W Change | GUC | S IC UR0605B-FT027 TFBGA 78P H1 SECURE |  | SA0000AXF20 |  |  | 42.26 |  |  | May | 2020-07-04 | 2020-07-16
C38(NB) | TBD | ELAV4 | ELAV4V5 | 6 | 1 | New-Qualify | Pass | ME | 2nd source | 和諧山川 | SCREW M M 2D 2.5L K 4.5D 0.5T ZK NL + SCREW M M 2.0D 7.0L K 3.5D 0.7T BNI NL + SCREW M M 2.0D 6.0L K 4.3D NI NL + |  | MA00001QTG0,MA00001GRG0,MA00000DVG0 |  |  | 4 |  |  | May | 2020-07-04 | 2020-07-16
C38(NB) | TBD | ELAV5 | ELAV4V5 | 6 | 1 | New-Qualify | Pass | ME | 2nd source | 和諧山川 | SCREW M M 2D 2.5L K 4.5D 0.5T ZK NL + SCREW M M 2.0D 7.0L K 3.5D 0.7T BNI NL + SCREW M M 2.0D 6.0L K 4.3D NI NL + |  | MA00001QTG0,MA00001GRG0,MA00000DVG0 |  |  | 4 |  |  | May | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2050700 | ELAC2 | ELAC2 | 6 | 1 | New-Qualify | Pass | ME | 2nd source | 和諧山川 | SCREW M M 2.5D 5.0L K 4.6D ZK NL + CR3+ |  | MA000004NG0MA000008YG0 |  |  | 4 |  |  | May | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2050710 | ELAC1 | ELAC1 | 6 | 1 | New-Qualify | Pass | ME | 2nd source | 和諧山川 | SCREW M M 2.5D 5.0L K 4.6D ZK NL + CR3+ |  | MA000004NG0MA000008YG0 |  |  | 4 |  |  | May | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2050670 | ELMV2 | ELMV2 | 6 | 1 | New-Qualify | Pass | ME | 2nd source | 和諧山川 | SCREW M M 2.0D 4.5L K 3.5D 0.8T ZK NL + |  | MA00000SQG0 |  |  | 4 |  |  | May | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2050660 | ELMEA | ELMEA | 6 | 1 | New-Qualify | Pass | ME | 2nd source | 和諧山川 | SCREW M M 2.0D 4.5L K 3.5D 0.8T ZK NL + |  | MA00000SQG0 |  |  | 4 |  |  | May | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2050940 | ELAC2 | ELAC2 | 2 | 1 | New-Qualify | Fail | TPM | 2nd source | Nuvoton | S IC NPCT750LABYX QFN 32P TPM | SL80R40158 | SA0000AQ240 | Click here |  | 42.26 |  |  | May | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2050930 | ELAC1 | ELAC1 | 6 | 1 | New-Qualify | Pass | Connector | 2nd source | ARGOSY | S CONN ARGOSY UCF3T-4TN01-0P0B TYPE_C |  | SP06000C100 |  |  | 19.3 |  |  | May | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2050780 | ELIC1 | ELIC1 | 10 | 1 | New-Qualify | Pass | TPM | F/W Change | GUC | S IC UR0605B-FT027 TFBGA 78P H1 SECURE |  | SA0000AXF20 |  |  | 19.3 |  |  | May | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2041630 | ELAV5 | ELAV4V5 | 6 | 1 | New-Qualify | Pass | package | New source | EQM | Label | SL10Z72211 SL10Z72212 |  |  |  | 2 |  |  | May | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2052330 | FLMS0 | FLMS0 | 12 | 1 | New-Qualify | Fail | WLAN | 2nd source | Foxconn | Foxconn RTL8822CE 2*2ac+BT5.0 PCIE M.2 W/L_BT _ T99H152.00 C38 ! | SW10M73301 | PK32000K410 | Click here |  | 91.6 |  |  | May | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2060530 | FLMS0 | FLMS0 | 12 | 3 | New-Qualify | Pending | Camera | FW Change | AVC | CS20 Common Camera type A2, HD, 2MIC, ZIF, AVC HA2-FN2205 | SC20X02125 | PK40001OU00 | Click here |  | 42.5 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2050950 | FLMS0 | FLMS0 | 12 | 1 | New-Qualify | Pass | Camera | FW Change | Chicony | CS20 Common Camera type A2, HD, 2MIC, ZIF, CCY CNFJH49 | SC20X02139 | PK40001OT00 |  |  | 42.5 |  |  | May | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2052170 | FLMA0 | FLMA0 | 12 | 1 | New-Qualify | Fail | WLAN | 2nd source | Liteon | W/L_BT WCBN807A-L6 A7Z000004D0 C38 ! NFA344A |  | PK32000GR10 | Click here |  | 91.6 |  |  | May | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | EOS11 | EOS11 | 6 | 1 | New-Qualify | Fail | SSD | 2nd source | WD | SSD_M 512G N4SP4 SDBPMPZ-512G-1001 C38(AIO) | SSS0L24786 | DD900019D00 |  |  | 61.9 |  |  | May | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | EOS10 | EOS10 | 6 | 1 | New-Qualify | Fail | SSD | 2nd source | WD | SSD_M 512G N4SP4 SDBPMPZ-512G-1001 C38(AIO) | SSS0L24786 | DD900019D00 |  |  | 61.9 |  |  | May | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | FOC21 | FOC21 | 6 | 1 | New-Qualify | Pass | SSD | 2nd source | WD | SSD_M 512G N4SP4 SDBPMPZ-512G-1001 C38(AIO) | SSS0L24786 | DD900019D00 |  |  | 61.9 |  |  | May | 2020-07-04 | 2020-07-16
C38(AIO) | INV_O2050010 | FOC20 | FOC20 | 6 | 1 | New-Qualify | Pass | SSD | 2nd source | WD | SSD_M 512G N4SP4 SDBPMPZ-512G-1001 C38(AIO) | SSS0L24786 | DD900019D00 |  |  | 61.9 |  |  | May | 2020-07-04 | 2020-07-16
C38(AIO) | INV_O2050010 | FOC21 | FOC21 | 6 | 1 | Re-Qualify | Testing | RAM | 2nd source | Micron | DDR4 MODU MTA4ATF1G64HZ-3G2E1 8G C38(AIO) ! | SM30N76643 | PK05400AW20 |  |  | 47.1 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | FOC20 | FOC20 | 6 | 1 | Re-Qualify | Testing | RAM | 2nd source | Micron | DDR4 MODU MTA4ATF1G64HZ-3G2E1 8G C38(AIO) ! | SM30N76643 | PK05400AW20 |  |  | 47.1 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | FOC11 | FOC11 | 6 | 1 | Re-Qualify | Testing | RAM | 2nd source | Micron | DDR4 MODU MTA4ATF1G64HZ-3G2E1 8G C38(AIO) ! | SM30N76643 | PK05400AW20 |  |  | 47.1 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | FOC10 | FOC10 | 6 | 1 | Re-Qualify | Testing | RAM | 2nd source | Micron | DDR4 MODU MTA4ATF1G64HZ-3G2E1 8G C38(AIO) ! | SM30N76643 | PK05400AW20 |  |  | 47.1 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(AIO) | INV_O2050020 | FOC21 | FOC21 | 6 | 1 | New-Qualify | Pass | SSD | 2nd source | WD | SSD_M 256G N4SP4 SDBPMPZ-256G-1001 C38(AIO) | SSS0L25785 | DD900019C00 |  |  | 61.9 |  |  | May | 2020-07-04 | 2020-07-16
C38(AIO) | INV_O2050020 | FOC20 | FOC20 | 6 | 1 | New-Qualify | Pass | SSD | 2nd source | WD | SSD_M 256G N4SP4 SDBPMPZ-256G-1001 C38(AIO) | SSS0L25785 | DD900019C00 |  |  | 61.9 |  |  | May | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2050290 | FLY00 | FLY00 | 6 | 1 | New-Qualify | Pass | package | New source | MAKEROS | LABEL 31S CAMERA BEZEL NEW SL10Z56991 |  | HG31S000100 |  |  | 2 |  |  | May | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2050300 | FLY00 | FLY00 | 6 | 1 | New-Qualify | Pass | package | New source | 裕同 | Label Mode function label(Fn+Q) |  |  |  |  | 2 |  |  | May | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | EOC41 | EOC41 | 8 | 1 | Re-Qualify | Pass | RAM | 2nd source | Micron | DDR4 MODU MTA4ATF1G64HZ-3G2E1 8G C38(AIO) ! | SM30N76643 | PK05400AW20 |  |  | 47.1 |  |  | May | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | EOG70 | EOG70 | 8 | 1 | Re-Qualify | Pass | RAM | 2nd source | Micron | DDR4 MODU MTA4ATF1G64HZ-3G2E1 8G C38(AIO) ! | SM30N76643 | PK05400AW20 |  |  | 47.1 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | EOG70 | EOG70 | 8 | 1 | Re-Qualify | Pass | RAM | 2nd source | Micron | DDR4 MODU MTA8ATF2G64HZ-3G2E1 16G C38(AIO) ! | SM30N76644 | PK05400A820 |  |  | 47.1 |  |  | May | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2041600 | FLIC7 | FLIC7 | 20 | 1 | New-Qualify | Conditional Pass | package | 2nd source | 申健 | PAPER PAD 268 VE ACC BOX SP10Q15550 |  | HE268000100 | Click here |  | 3 |  |  | May | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2041940 | EL452 | EL452 | 20 | 1 | New-Qualify | Pass | package | 2nd source | 申健&裕同 博琛&法克达拉 | PAPER PAD 2D5 ACC BOX SP10S95768&EPE CUSHION 2GK 14 SP10U40397 |  | HE2D5000200 HE2GK000100 |  |  | 3 |  |  | Apr | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2042470 | FL435 | FL435535 | 10 |  | New-Qualify | Pass | package | 2nd source | 申健&裕同 | PAPER PAD 2D5 ACC BOX SP10S95768 |  | HE2D5000200 |  |  | 3 |  |  | Apr | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2042470 | FL436 | FL436536 | 10 |  | New-Qualify | Pass | package | 2nd source | 申健&裕同 | PAPER PAD 2D5 ACC BOX SP10S95768 |  | HE2D5000200 |  |  | 3 |  |  | Apr | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2010641 | FLMS0 | FLMS0 | 20 | 1 | Re-Qualify | Pass | SSD | New source | Intel | SSD_M 512G SSDPEKNW512G8L F:C02C C38 ! | SSS0W90997 | DD900013LC0 | Click here | Re-INV | 6 |  |  | Apr | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2052030 | FLMS0 | FLMS0 | 14 | 1 | New-Qualify | Pass | Panel | New source | AUO | LCD_LED_M B140XTN07.7 H:0A HD AG S C38 | SD10Z26829 | AC60001SP80 | Click here |  | 65.8 |  |  | May | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2051670 | FLMS0 | FLMS0 | 12 | 1 | New-Qualify | Pass | RAM | New source | Micron | S IC D4 16G/3200 MT40A1G16KD-062E:E FBGA | SM30N76641 | SA0000D3U00 |  |  | 37.4 |  |  | May | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2050960 | FLMS0 | FLMS0 | 12 | 1 | New-Qualify | Pass | Camera | FW Change | Bison | CAMERA M BNL119KSE BISON 1M 2MIC | SC20X02126 | PK40001OS00 |  |  | 42.5 |  |  | May | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2050420 | FLMS0 | FLMS0 | 12 | 1 | New-Qualify | Pass | EE | 2nd source | TOPSUN | S COIL 1.5UH 20% SHPI0603-1R5M-HF-TW 8A |  | SH00001VZ00 |  |  | 19.3 |  |  | May | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2050690 | FLMS0 | FLMS0 | 12 | 1 | New-Qualify | Pass | EE | 2nd source | TOPSUN | S COIL .15UH 20% STPI0603-R15M-T4-TW 37A |  | SH000024200 |  |  | 19.3 |  |  | May | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | FOC20 | FOC20 | 8 | 1 | New-Qualify | Pass | RAM | 2nd source | Samsung | DDR4 MODU M471A2K43DB1-CWE 16G C38(AIO)! |  | PK054009H30 |  |  | 47.1 |  |  | May | 2020-07-04 | 2020-07-16
C38(AIO) | INV_O2040080 | FOC81 | FOC81 | 6 | 1 | New-Qualify | Pass | HDD | 2nd source | Toshiba | HDD 1T H7 MQ04ABF100 F:JU0A1E C38(AIO) |  | DD10000ZNP0 |  |  | 60.1 |  |  | Apr | 2020-07-04 | 2020-07-16
C38(AIO) | INV_O2040080 | FOC80 | FOC80 | 6 | 1 | New-Qualify | Pass | HDD | 2nd source | Toshiba | HDD 1T H7 MQ04ABF100 F:JU0A1E C38(AIO) |  | DD10000ZNP0 |  |  | 60.1 |  |  | Apr | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | FOC11 | FOC11 | 6 | 1 | New-Qualify | Pass | SSD | 2nd source | WD | SSD_M 512G N4SP4 SDBPMPZ-512G-1001 C38(AIO) | SSS0L25785 | DD900019C00 |  |  | 61.9 |  |  | Apr | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | FOC10 | FOC10 | 6 | 1 | New-Qualify | Pass | SSD | 2nd source | WD | SSD_M 512G N4SP4 SDBPMPZ-512G-1001 C38(AIO) | SSS0L24786 | DD900019D00 |  |  | 61.9 |  |  | Apr | 2020-07-04 | 2020-07-16
C38(AIO) | INV_O2040010 | FOC11 | FOC11 | 4 | 1 | Re-Qualify | Pass | ME | 2nd source | LG | LCD_LED_M LM215WF9-SSA1 21.5" FHD C38(AIO)! |  | AC60001G110 |  |  | 12 |  |  | Apr | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2041660 | FL435535 | FL435535 | 12 | 1 | New-Qualify | Conditional Pass | WLAN | 2nd source | Foxconn | Foxconn RTL8822CE 2*2ac+BT5.0 W/L_BT _ T99H152.00 C38 | SW10M73301 | PK32000K410 | Click here |  | 91.6 |  |  | Apr | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2041670 | FL436536 | FL436536 | 12 | 1 | New-Qualify | Conditional Pass | WLAN | 2nd source | Foxconn | Foxconn RTL8822CE 2*2ac+BT5.0 W/L_BT _ T99H152.00 C38 | SW10M73301 | PK32000K410 | Click here |  | 91.6 |  |  | Apr | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2041640 | FLMS0 | FLMS0 | 12 | 1 | New-Qualify | Fail | package | New source |  | Label SL10Z78287 IdeaPad Slim 5 PR label-EN | SL10Z78287 |  | Click here |  | 2 |  |  | Apr | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2041910 | FLMS0 | FLMS0 | 12 | 1 | New-Qualify | Conditional Pass | EE | New source | DIODES | S IC DPS1113FIA-13 QFN 18P TYPE-C OVP |  | SA0000AOX00 | Click here | TYPE C IC+PD FW | 103.2 |  |  | Apr | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2041980 | FLMA0 | FLMA0 | 12 | 1 | New-Qualify | Conditional Pass | EE | New source | DIODES | S IC DPS1113FIA-13 QFN 18P TYPE-C OVP |  | SA0000AOX00 | Click here | TYPE C IC+PD FW | 103.2 |  |  | Apr | 2020-07-04 | 2020-07-16
C38(AIO) | INV_O2040030 | EOC21 | EOC21 | 6 | 1 | New-Qualify | Pass | HDD | 2nd source | Toshiba | HDD 1T H7 MQ04ABF100 F:JU0A1E C38(AIO) |  | DD10000ZNP0 |  |  | 60.1 |  |  | Apr | 2020-07-04 | 2020-07-16
C38(AIO) | INV_O2040030 | EOC20 | EOC20 | 6 | 1 | New-Qualify | Pass | HDD | 2nd source | Toshiba | HDD 1T H7 MQ04ABF100 F:JU0A1E C38(AIO) |  | DD10000ZNP0 |  |  | 60.1 |  |  | Apr | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2040250 | ELAC2 | ELAC2 | 2 | 1 | New-Qualify | Pass | TPM | FW Change | STM | S IC ST33HTPH2E32AHD0 VQFN 32P TPM | SSS0V42257 | SA00009SO70 |  |  | 42.26 |  |  | Apr | 2020-07-04 | 2020-07-16
C38(NB) | TBD | FLMS0 | FLMS0 | 12 | 1 | New-Qualify | Pass | SSD | 2nd source | WD SN530 | WD 256 SN530 256GB SDBPMPZ-256G-1101 PCIe 2242 SSD | SSS0X54154 | DD900019C20 |  | 與支架組裝干涉, 導入新支架 | 58.8 |  |  | Apr | 2020-07-04 | 2020-07-16
C38(NB) | TBD | FLMS0 | FLMS0 | 12 | 1 | New-Qualify | Pass | SSD | 2nd source | WD SN530 | WD 512 SN530 512GB SDBPMPZ-512G-1101 PCIe 2242 SSD | SSS0X54156 | DD900019D20 |  | 與支架組裝干涉, 導入新支架 | 58.8 |  |  | Apr | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2031680 | ELAC2 | ELAC2 | 12 | 1 | New-Qualify | Pass | SSD | New source | Samsung | PM991 2242 SSD_M 256G N4SP4 MZALQ256HAJD-000L2 C38 | SSS0V42257 | DD900017000 |  |  | 58.8 |  |  | Apr | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2031670 | ELAC2 | ELAC2 | 12 | 2 | New-Qualify | Pass | SSD | New source | Samsung | PM991 2242 SSD_M 128G N4SP4 MZALQ128HBHQ-000L2 C38! | SSS0V42252 | DD900016J30 |  |  | 58.8 |  |  | Apr | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | FOC21 | FOC21 | 6 | 1 | New-Qualify | Pass | RAM | 2nd source | Hynix | DDR4 MODU HMA82GS6DJR8N-XN 16G C38(AIO)!, |  | PK054009E20 |  |  | 47.1 |  |  | Apr | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | FOC20 | FOC20 | 6 | 1 | New-Qualify | Pass | RAM | 2nd source | Hynix | DDR4 MODU HMA82GS6DJR8N-XN 16G C38(AIO)!, |  | PK054009E20 |  |  | 47.1 |  |  | Apr | 2020-07-04 | 2020-07-16
C38(AIO) | INV_O2040100 | FOC81 | FOC81 | 6 | 1 | New-Qualify | Pass | SSD | 2nd source | WD | SSD_M 512G N4SP4 SDBPMPZ-512G-1001 C38(AIO) | SSS0L24786 | DD900019D00 |  |  | 61.9 |  |  | Apr | 2020-07-04 | 2020-07-16
C38(AIO) | INV_O2040100 | FOC80 | FOC80 | 6 | 1 | New-Qualify | Pass | SSD | 2nd source | WD | SSD_M 512G N4SP4 SDBPMPZ-512G-1001 C38(AIO) | SSS0L24786 | DD900019D00 |  |  | 61.9 |  |  | Apr | 2020-07-04 | 2020-07-16
C38(AIO) | INV_O2040110 | FOC81 | FOC81 | 6 | 1 | New-Qualify | Pass | SSD | 2nd source | WD | SSD_M 256G N4SP4 SDBPMPZ-256G-1001 C38(AIO) | SSS0L25785 | DD900019C00 |  |  | 61.9 |  |  | Apr | 2020-07-04 | 2020-07-16
C38(AIO) | INV_O2040110 | FOC80 | FOC80 | 6 | 1 | New-Qualify | Pass | SSD | 2nd source | WD | SSD_M 256G N4SP4 SDBPMPZ-256G-1001 C38(AIO) | SSS0L25785 | DD900019C00 |  |  | 61.9 |  |  | Apr | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2040780 | ELAC1 | ELAC1 | 10 | 1 | New-Qualify | Pass | TPM | F/W Change | GUC | S IC UR0605B-FT027 TFBGA 78P H1 SECURE |  | SA0000AXF20 | Click here |  | 19.3 |  |  | Apr | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2041380 | ELMEA | ELMEA | 6 | 1 | Re-Qualify | Pass | VRAM | New source | Samsung | S IC D5 256M32 K4G80325FC-HC25 FBGA 170P K4G80325FC-HC25 8Gb 8Gbps GDDR5 | SV20T35751 | SA00009TA60 |  |  | 210 |  |  | Mar | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2041390 | DLMVA | DLMVA | 6 | 1 | Re-Qualify | Pass | VRAM | New source | Samsung | S IC D5 256M32 K4G80325FC-HC25 FBGA 170P K4G80325FC-HC25 8Gb 8Gbps GDDR5 | SV20T35751 | SA00009TA60 |  |  | 210 |  |  | Mar | 2020-07-04 | 2020-07-16
C38(AIO) | DCR_O2030014 | FOC81 | FOC81 | 6 | 1 | New-Qualify | Fail | SSD | 2nd source | Toshiba | SSD_M 512G N4SP4 KBG40ZNT512G C38(AIO) |  | DD900017R20 |  | Lenovo cancel it | 61.9 |  |  | Mar | 2020-07-04 | 2020-07-16
C38(AIO) | DCR_O2030014 | FOC80 | FOC80 | 6 | 1 | New-Qualify | Fail | SSD | 2nd source | Toshiba | SSD_M 512G N4SP4 KBG40ZNT512G C38(AIO) |  | DD900017R20 |  | Lenovo cancel it | 61.9 |  |  | Mar | 2020-07-04 | 2020-07-16
C38(AIO) | DCR_O2030011 | FOC81 | FOC81 | 6 | 1 | New-Qualify | Fail | SSD | 2nd source | Toshiba | SSD_M 256G KBG40ZNT256G F:0104AELA C38(AIO) |  | DD900017Q20 |  | Lenovo cancel it | 61.9 |  |  | Mar | 2020-07-04 | 2020-07-16
C38(AIO) | DCR_O2030011 | FOC80 | FOC80 | 6 | 1 | New-Qualify | Fail | SSD | 2nd source | Toshiba | SSD_M 256G KBG40ZNT256G F:0104AELA C38(AIO) |  | DD900017Q20 |  | Lenovo cancel it | 61.9 |  |  | Mar | 2020-07-04 | 2020-07-16
C38(AIO) | INV_O2030150 | EOS10 | EOS10 | 2 | 1 | New-Qualify | Pass | Connector | 2nd source | Deren | S SOCKET DEREN 570B17-008H CARD READER |  | SP07001ON00 |  |  | 12 |  |  | Mar | 2020-07-04 | 2020-07-16
C38(AIO) | INV_O2030080 | FOC81 | FOC81 | 6 | 1 | New-Qualify | Pass | SSD | 2nd source | UMIS | SSD_M 512G N4SP4 RPJTJ512MEE1OWX C38(AIO) | SSS0L25190 | DD900016Y20 |  |  | 61.9 |  |  | Mar | 2020-07-04 | 2020-07-16
C38(AIO) | INV_O2030080 | FOC80 | FOC80 | 6 | 1 | New-Qualify | Pass | SSD | 2nd source | UMIS | SSD_M 512G N4SP4 RPJTJ512MEE1OWX C38(AIO) | SSS0L25190 | DD900016Y20 |  |  | 61.9 |  |  | Mar | 2020-07-04 | 2020-07-16
C38(AIO) | DCR_O2030012 | FOC81 | FOC81 | 6 | 1 | New-Qualify | Pass | SSD | 2nd source | UMIS | SSD_M 256G N4SP4 RPJTJ256MEE1OWX C38(AIO) | SSS0L25189 | DD900016W20 |  |  | 61.9 |  |  | Apr | 2020-07-04 | 2020-07-16
C38(AIO) | DCR_O2030012 | FOC80 | FOC80 | 6 | 1 | New-Qualify | Pass | SSD | 2nd source | UMIS | SSD_M 256G N4SP4 RPJTJ256MEE1OWX C38(AIO) | SSS0L25189 | DD900016W20 |  |  | 61.9 |  |  | Apr | 2020-07-04 | 2020-07-16
C38(AIO) | INV_O2040060 | EOC31 | EOC31 | 6 | 1 | New-Qualify | Pass | HDD | 2nd source | Toshiba | HDD 1T H7 MQ04ABF100 F:JU0A1E C38(AIO) |  | DD10000ZNP0 |  |  | 60.1 |  |  | Mar | 2020-07-04 | 2020-07-16
C38(AIO) | INV_O2040060 | EOC30 | EOC30 | 6 | 1 | New-Qualify | Pass | HDD | 2nd source | Toshiba | HDD 1T H7 MQ04ABF100 F:JU0A1E C38(AIO) |  | DD10000ZNP0 |  |  | 60.1 |  |  | Mar | 2020-07-04 | 2020-07-16
C38(AIO) | INV_O2030220 | EOC41 | EOC41 | 4 | 1 | Re-Qualify | Pass | Panel | 2nd source | BOE | LCD_LED_M MV215FHM-N40 FHD ES8.0 C38(AIO)! |  | AC60001G250 |  | FW Update | 36.25 |  |  | Mar | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2041250 | FLMA0 | FLMA0 | 10 | 1 | New-Qualify | Conditional Pass | SSD | FW Change | Samsung | Samsung 2242 SSD_M 256G N4SP4 MZALQ256HAJD-000L2 C38! |  | DD900017010 | Click here |  | 46.4 |  |  | Apr | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2041260 | FLMA0 | FLMA0 | 10 | 1 | New-Qualify | Conditional Pass | SSD | FW Change | Samsung | Samsung 2242 SSD_M 512G N4SP4 MZALQ512HALU-000L2 C38! |  | DD900017110 | Click here |  | 46.4 |  |  | Apr | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2041240 | FLMA0 | FLMA0 | 10 | 1 | New-Qualify | Pass | SSD | FW Change | Samsung | Samsung 2280 SSD_M 512G N8SP4 MZVLB512HBJQ-000L2 C38! |  | DD900011Z40 | Click here |  | 46.4 |  |  | Apr | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2042150 | FLMA0 | FLMA0 | 10 | 2 | New-Qualify | Conditional Pass | Panel | New source | INX | INX IPS 3.0t Panel LCD_LED_M N140HCA-EAE C1 14" FHD AG C38! |  | AC60001GAS0 | Click here |  | 65.8 |  |  | Apr | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2052040 | FLMA0 | FLMA0 | 10 | 2 | New-Qualify | Conditional Pass | Panel | New source | INX | INX TN 3.0t Panel LCD_LED_M N140HGA-EA1 C4 14" FHD AG C38! |  | AC60001TH30 | Click here | ME leverage Intel 平台 | 65.8 |  |  | Apr | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2041530 | FLMA0 | FLMA0 | 10 | 3 | New-Qualify | Pass | SSD | New source | Hynix | Hynix 2280 SSD_M 512G N8SP4 HFS512GD9TNI-L2A0B C38! |  | DD900017800 |  |  | 58.8 |  |  | Apr | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2052110 | FLMA0 | FLMA0 | 12 | 1 | New-Qualify | Fail | SSD | New source | Intel | Intel 2280 SSD_M 512G SSDPEKNW512G8L F:C02C C38 ! |  | DD900013LC0 | Click here |  | 58.8 |  |  | May | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2052050 | FLMA0 | FLMA0 | 10 | 2 | New-Qualify | Pass | Panel | New source | AUO | AUO TN 3.0t 250nit Panel LCD_LED_M B140XTN07.7 H:0A 14 HD AG C38! |  | AC60001SP90 | Click here |  | 65.8 |  |  | May | 2020-07-04 | 2020-07-16
C38(NB) | TBD | FLMA0 | FLMA0 | 10 | 1 |  | Planning | SSD | New source | UMIS | Umis 2242 SSD_M 256G N4SP4 RPJTJ256MEE1OWX C38 ! |  | DD900016W10 |  |  | 1 |  |  |  | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2031540 | FLMS0 | FLMS0 | 20 | 1 | Re-Qualify | Conditional Pass | SSD | New source | WD SN730 | SSD_M 512G N8SP4 SDBPNTY-512G-1101 C38 ! | SSS0V13672 | DD900015440 | Click here |  | 58.8 |  |  | Mar | 2020-07-04 | 2020-07-16
C38(AIO) | INV_O2040050 | FOC11 | FOC11 | 4 | 1 | New-Qualify | Pass | HDD | 2nd source | Toshiba | HDD 1T H7 MQ04ABF100 F:JU0A1E C38(AIO) |  | DD10000ZNP0 |  |  | 60.1 |  |  | Mar | 2020-07-04 | 2020-07-16
C38(AIO) | INV_O2040050 | FOC10 | FOC10 | 4 | 1 | New-Qualify | Pass | HDD | 2nd source | Toshiba | HDD 1T H7 MQ04ABF100 F:JU0A1E C38(AIO) |  | DD10000ZNP0 |  |  | 60.1 |  |  | Mar | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2032360 | FLMS0 | FLMS0 | 12 | 1 | New-Qualify | Conditional Pass | SSD | 2nd source | Hynix | Hynix 2280 SSD_M 512G N8SP4 HFS512GD9TNI-L2A0B C38! | SSS0W86213 | DD900017800 | Click here |  | 58.8 |  |  | Mar | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2042120 | FLMS0 | FLMS0 | 8 | 1 | New-Qualify | Pass | adapter | New source | Delta | Delta ADP-45DW B 20V2.25A COO | SA10M42785 | PK100014BO0 |  |  | 55.9 |  |  | Apr | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2042130 | FLMS0 | FLMS0 | 8 | 1 | New-Qualify | Pass | adapter | New source | Liteon | Liteon PA-1450-55LL 20V2.25A COO | SA10M42742 | PK100013WP0 |  |  | 55.9 |  |  | May | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2042140 | FLMS0 | FLMS0 | 8 | 1 | New-Qualify | Pass | adapter | New source | Chicony | Chicony ADL45WCC 20V2.25A COO | SA10M42697 | PK10001A150 |  |  | 55.9 |  |  | Apr | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2040980 | FLMS0 | FLMS0 | 8 | 1 | New-Qualify | Pass | adapter | New source | Liteon | Liteon PD 95W 3pin | SA10R16876 | PK10001GV10 |  |  | 55.9 |  |  | Mar | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2041290 | FLMS0 | FLMS0 | 8 | 1 | New-Qualify | Pass | adapter | New source | Chicony | Chicony PD 95W 3pin | SA10R16878 | PK10001GX10 |  |  | 55.9 |  |  | Apr | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2041650 | FLMS0 | FLMS0 | 8 | 1 | New-Qualify | Pass | adapter | New source | Acbel | Acbel PD 95W 3pin | SA10R16880 | PK10001GW10 |  |  | 55.9 |  |  | Apr | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2030670 | EL571 | EL571 | 10 | 1 | New-Qualify | Pass | Battery | FW Change | Sunwoda | BATT SW AL 4S1P 4.51AH 8 2GL C38 ! | 5B10T83737 | GC02002SB10 | Click here |  | 56 |  |  | Mar | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2030380 | EL571 | EL571 | 4 | 1 | New-Qualify | Pass | FAN | design change | FCN | FAN DC5V FORCECON 0FLBP0000H RFAN FAN DC5V FORCECON 0FLBN0000H LFAN | / | DC28000O2F0 DC28000O1F0 |  |  | 19.3 |  |  | Mar | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2031550 | FLMS0 | FLMS0 | 12 | 1 | New-Qualify | Pass | Finger Print | design change | Top touch | FINGPRINT FPT TTCF122393 IRON GREY | SF30X01313 | PK09000PX00 |  |  | 52.6 |  |  | Mar | 2020-07-04 | 2020-07-16
C38(AIO) | INV_O2030140 | FOC21 | FOC21 | 4 | 1 | New-Qualify | Pass | SSD | 2nd source | UMIS | SSD_M 512G N4SP4 RPJTJ512MEE1OWX C38(AIO) | SSS0L25190 | DD900016Y20 |  |  | 61.9 |  |  | Apr | 2020-07-04 | 2020-07-16
C38(AIO) | INV_O2030140 | FOC20 | FOC20 | 4 | 1 | New-Qualify | Pass | SSD | 2nd source | UMIS | SSD_M 512G N4SP4 RPJTJ512MEE1OWX C38(AIO) | SSS0L25190 | DD900016Y20 |  |  | 61.9 |  |  | Apr | 2020-07-04 | 2020-07-16
C38(AIO) | INV_O2030110 | FOC21 | FOC21 | 4 | 1 | New-Qualify | Pass | SSD | 2nd source | UMIS | SSD_M 256G N4SP4 RPJTJ256MEE1OWX C38(AIO) | SSS0L25189 | DD900016W20 |  |  | 61.9 |  |  | Mar | 2020-07-04 | 2020-07-16
C38(AIO) | INV_O2030110 | FOC20 | FOC20 | 4 | 1 | New-Qualify | Pass | SSD | 2nd source | UMIS | SSD_M 256G N4SP4 RPJTJ256MEE1OWX C38(AIO) | SSS0L25189 | DD900016W20 |  |  | 61.9 |  |  | Mar | 2020-07-04 | 2020-07-16
C38(AIO) | INV_O2030170 | FOC20 | FOC20 | 6 | 1 | New-Qualify | Pass | ME | 2nd source |  | JD Stand change to WW units |  | HE2FM000M00/HE2FM000L00 |  |  | 20 |  |  | Mar | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2031530 | EL432 | EL432532 | 10 | 1 | New-Qualify | Conditional Pass | Panel | New source | INX | LCD_LED_M N140HCA-EAC C5 14" FHD AG C38 | SD10W91002 | AC60001GAT0 | Click here |  | 65.8 |  |  | Mar | 2020-07-04 | 2020-07-16
C38(AIO) | INV_O2040020 | EOS11 | EOS11 | 6 | 1 | New-Qualify | Pass | HDD | 2nd source | Toshiba | HDD 1T H7 MQ04ABF100 F:JU0A1E C38(AIO) |  | DD10000ZNP0 |  |  | 60.1 |  |  | Mar | 2020-07-04 | 2020-07-16
C38(AIO) | INV_O2040020 | EOS10 | EOS10 | 6 | 1 | New-Qualify | Pass | HDD | 2nd source | Toshiba | HDD 1T H7 MQ04ABF100 F:JU0A1E C38(AIO) |  | DD10000ZNP0 |  |  | 60.1 |  |  | Mar | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2030240 | ELAC2 | ELAC2 | 12 | 1 | New-Qualify | Pass | SSD | New source | UMIS | UMIS AM620 128GB PCIe 2242 RPJTJ128MEE1MWX SSD | SSS0W76185 | DD900016X00 |  |  | 58.8 |  |  | Mar | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2030250 | ELAC2 | ELAC2 | 12 | 2 | New-Qualify | Pass | SSD | New source | UMIS | SSD_M 256G N4SP4 RPJTJ256MEE1OWX C38 | SSS0W76181 | DD900016W00 |  |  | 58.8 |  |  | Mar | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2030100 | FLAE1 | FLAE1 | 12 | 1 | New-Qualify | Pass | RAM | New source | Ramaxel | DDR4 MODU RMSA3310MJ86H9F-3200 4G/3200 S | SM30N76646 | PK05400A210 |  |  | 37.4 |  |  | Mar | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2030180 | FLAE1 | FLAE1 | 16 | 1 | New-Qualify | Pass | HDD | New source | Toshiba | ToshibaHDD 500G H7 MQ01ABF050 H:ABM AC12 C38 | ASM:SH20U59756 Bare:SHD0U59633 | DD10000WND0 |  |  | 77.4 |  |  | Mar | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2030190 | FLAE1 | FLAE1 | 16 | 2 | New-Qualify | Pass | SSD | New source | WD | SSD_M 256G N8SP4 SDBPNTY-256G-1101 C38 | SSS0V13670 | DD900015330 |  |  | 58.8 |  |  | Mar | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2030090 | FLAE1 | FLAE1 | 16 | 3 | New-Qualify | Pass | RAM | New source | Ramaxel | DDR4 MODU RMSA3320MJ78HAF-3200 8G/3200 | SM30N76647 | PK05400A300 |  |  | 37.4 |  |  | Mar | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2050130 | FLAE1 | FLAE1 | 12 | 1 | New-Qualify | Conditional Pass | Camera | New source | Liteon | CAMERA M 6SF111N2A LITE-ON 1M W/MIC | SC20M52114 | PK40001H900 | Click here |  | 42.5 |  |  | Apr | 2020-07-04 | 2020-07-16
C38(NB) | TBD | FLAE1 | FLAE1 | 12 | 1 |  | Planning | RAM | New source | Micron | DDR4 MODU MTA4ATF1G64HZ-3G2E1 8G/3200 S | SM30N76643 | PK05400AW10 |  |  | 1 |  |  |  | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2030110 | FLAE1 | FLAE1 | 12 | 1 | New-Qualify | Pass | Camera | New source | AVC | CAMERA M HA2-FN1000-A0A AVC 0.3M | SC20T84693 | PK40001MI00 |  |  | 42.5 |  |  | Mar | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2030170 | FLAE1 | FLAE1 | 12 | 2 | New-Qualify | Fail | Battery | New source | Simplo | BATT SP AL 3S2P 4.19AH 8 28Q C38 | 5B10R33000 | GC02002NT00 | Click here |  | 56 |  |  | Mar | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2030160 | FLAE1 | FLAE1 | 12 | 3 | New-Qualify | Pass | SSD | New source | Hynix | SSD_M 512G N4SP4 HFM512GDHTNI-87A0B C38 | SSS0V27609 | DD900014340 |  |  | 58.8 |  |  | Mar | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2060520 | FLMS0 | FLMS0 | 10 | 2 | New-Qualify | Pending | Panel | 2nd source | INX | INX 3.0t IPS LCD_LED_M N140HCA-EAE C1 14" FHD AG C38 | SD10W87243 | AC60001GAR0 | Click here |  | 65.8 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(NB) | TBD | FLMS0 | FLMS0 | 12 | 1 |  | Planning | SSD | 2nd source | Toshiba | SSD_M 128G N4SP2 KBG40ZMT128G C38 2242 | SSS0T35790 | DD900017P00 |  |  | 1 |  |  |  | 2020-07-04 | 2020-07-16
C38(NB) | TBD | FLMS0 | FLMS0 | 12 | 1 |  | Planning | SSD | 2nd source | Toshiba | SSD_M 256G N4SP4 KBG40ZNT256G C38 2242 | SSS0T35787 | DD900017Q00 |  |  | 1 |  |  |  | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2041300 | FLMS0 | FLMS0 | 12 | 1 | New-Qualify | Fail | SSD | FW Change | UMIS | UMIS AM620 256GB PCIe 2242 SSD_M 256G N4SP4 RPJTJ256MEE1OWX C38 | SSS0W76181 | DD900016W00 | Click here | for SSD over temp issue | 46.4 |  |  | Apr | 2020-07-04 | 2020-07-16
C38(NB) | TBD | FLMS0 | FLMS0 | 20 | 1 |  | Planning | SSD | New source | UMIS | AH640 SSD_M 1T N8SP4 RPITJ1TBVME2HWD C38 | SSS0W86208 | DD900017V00 |  |  | 1 |  |  |  | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2040770 | ELAC1 | ELAC1 | 10 | 1 | New-Qualify | Pass | BIOS ROM | New source | WINBOND | S IC FL 128M W25Q128JWSIQ SOIC8P SPI ROM |  | SA00009KY30 | Click here |  | 72.7 |  |  | Apr | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | EOC31 | EOC31 | 6 | 1 | Re-Qualify | Fail | SSD | 2nd source | Toshiba | SSD_M 128G N4SP2 KBG40ZMT128G C38(AIO) |  | DD900017P50 |  |  | 61.9 |  |  | Mar | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | EOC30 | EOC30 | 6 | 1 | Re-Qualify | Fail | SSD | 2nd source | Toshiba | SSD_M 128G N4SP2 KBG40ZMT128G C38(AIO) |  | DD900017P50 |  |  | 61.9 |  |  | Mar | 2020-07-04 | 2020-07-16
C38(AIO) | INV_O19A0010 | EOS11 | EOS11 | 6 | 1 | New-Qualify | Pass | SSD | 2nd source | Toshiba | SSD_M 128G N4SP2 KBG40ZMT128G C38(AIO) |  | DD900017P50 |  |  | 61.9 |  |  | Feb | 2020-07-04 | 2020-07-16
C38(AIO) | INV_O19A0010 | EOS10 | EOS10 | 6 | 1 | New-Qualify | Pass | SSD | 2nd source | Toshiba | SSD_M 128G N4SP2 KBG40ZMT128G C38(AIO) |  | DD900017P50 |  |  | 61.9 |  |  | Feb | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2020430 | EL432 | EL432532 | 8 | 2 | New-Qualify | Pass | RAM | New source | Ramaxel | DDR4 MODU RMSA3320MJ78HAF-3200 8G/3200 | SM30N76647 | PK05400A300 |  |  | 37.4 |  |  | Feb | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2020420 | EL532 | EL432532 | 8 | 2 | New-Qualify | Pass | RAM | New source | Ramaxel | DDR4 MODU RMSA3320MJ78HAF-3200 8G/3200 | SM30N76647 | PK05400A300 |  |  | 37.4 |  |  | Feb | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2020440 | EL4C2 | EL4C2 | 12 | 1 | New-Qualify | Pass | SSD | New source | samsung | SAMSUNG PM981a 256GB M.2 Pie 2280 MZVLB256HBHQ-000L2 SSD | SSS0T22292 | DD900011Y30 |  |  | 58.8 |  |  | Feb | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2010770 | FLMS0 | FLMS0 | 16 | 2 | New-Qualify | Conditional Pass | Camera | 2nd source | Azurewave | CAMERA M AM-9SF5407 AZUREWAVE 1M 2MIC FW:1919 |  | PK40001OR00 |  | NPI fail | 42.5 |  |  | Jan | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2010630 | FLMS0 | FLMS0 | 20 | 1 | New-Qualify | Fail | SSD | New source | WD | SSD_M 512G N8SP4 SDBPNTY-512G-1101 C38 ! | SSS0V13672 | DD900015440 | Click here |  | 58.8 |  |  | Jan | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2010640 | FLMS0 | FLMS0 | 20 | 1 | New-Qualify | Fail | SSD | New source | Intel | SSD_M 512G SSDPEKNW512G8L F:C02C C38 ! | SSS0W90997 | DD900013LC0 | Click here |  | 58.8 |  |  | Jan | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | FOC21 | FOC21 | 6 | 1 | New-Qualify | Fail | CPU | 2nd source | Intel | S IC FJ8070104307803 QSBM V0 1.9G |  | SA0000D8U00 |  |  | 123.74 |  |  | Jan | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | FOC21 | FOC21 | 6 | 1 | New-Qualify | Fail | CPU | 2nd source | Intel | S IC FJ8070104307703 QSBL V0 2.4G |  | SA0000D2A00 |  |  | 123.74 |  |  | Jan | 2020-07-04 | 2020-07-16
C38(AIO) | INV_O19C0040 | EOS11 | EOS11 | 13 | 1 | New-Qualify | Conditional Pass | Panel | 2nd source | Innoux | LCD_LED_M M215HCA-L3B FHD AG ES8.0 C38(AIO) |  | AC60001MM70 |  |  | 112.25 |  |  | Jan | 2020-07-04 | 2020-07-16
C38(AIO) | INV_O19C0060 | EOS10 | EOS10 | 13 | 1 | New-Qualify | Conditional Pass | Panel | 2nd source | Innoux | LCD_LED_M M238HCA-L3B FHD AG ES8.0 C38(AIO) |  | AC60001MN20 |  |  | 112.25 |  |  | Jan | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2010190 | EL432 | EL432532 | 10 | 1 | New-Qualify | Fail | Panel | New source | AUO | LCD_LED_M B140HAN04.0 H:1A 14 FHD AG C38 | 5D10M42862 | AC60001KO80 | Click here | ME leverage FL436 | 65.8 |  |  | Jan | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2010250 | EL432 | EL432532 | 6 | 3 | New-Qualify | Pass | RAM | New source | Samsung | DDR4 MODU SAM M471A1K43DB1-CWE 8G/3200 | SM30N76636 | PK054009G00 |  |  | 37.4 |  |  | Jan | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2010250 | EL532 | EL432532 | 6 | 3 | New-Qualify | Pass | RAM | New source | Samsung | DDR4 MODU SAM M471A1K43DB1-CWE 8G/3200 | SM30N76636 | PK054009G00 |  |  | 37.4 |  |  | Jan | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2010340 | EL432 | EL432532 | 8 | 1 | New-Qualify | Pass | HDD | New source | Seagate | HDD 2T H7 ST2000LM007 F:LGM1 C38 | SHD0P03179 | DD10000YPQ0 |  |  | 77.4 |  |  | Feb | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2010350 | EL532 | EL432532 | 8 | 1 | New-Qualify | Pass | HDD | New source | Seagate | HDD 2T H7 ST2000LM007 F:LGM1 C38 | SHD0P03179 | DD10000YPQ0 |  |  | 77.4 |  |  | Feb | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2010320 | EL432 | EL432532 | 8 | 2 | New-Qualify | Pass | HDD | New source | Seagate | HDD 1T H7 ST1000LM035 F:LFM1 C38 | SHD0P03178 | DD10000WWR0 |  |  | 77.4 |  |  | Jan | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2010330 | EL532 | EL432532 | 8 | 2 | New-Qualify | Pass | HDD | New source | Seagate | HDD 1T H7 ST1000LM035 F:LFM1 C38 | SHD0P03178 | DD10000WWR0 |  |  | 77.4 |  |  | Jan | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2010230 | EL531 | EL531 | 16 | 1 | New-Qualify | Pass | HDD | New source | Seagate | HDD 1T H7 ST1000LM035 F:LFM1 C38 | SHD0P03178 | DD10000WWR0 |  |  | 77.4 |  |  | Jan | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2010760 | EL5C4 | EL5C4 | 20 | 1 | New-Qualify | Conditional Pass | SSD | New source | Samsung | PM991 MZALQ128HBHQ-000L2 128GB M.2 PCIe 2242 SSD | SSS0V42252 | DD900016J20 | Click here |  | 58.8 |  |  | Jan | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2030340 | ELAV5 | ELAV4V5 | 6 | 1 | New-Qualify | Pass | SSD | New source | samsung | Samsung PM881 128GB 2.5 MZ7LH128HBHQ-000L2 SATA SSD | SSS0U53621 | DD900016I30 | Click here |  | 58.8 |  |  | Mar | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2030350 | ELAV4 | ELAV4V5 | 6 | 1 | New-Qualify | Pass | SSD | New source | samsung | Samsung PM881 128GB 2.5 MZ7LH128HBHQ-000L2 SATA SSD | SSS0U53621 | DD900016I30 | Click here |  | 58.8 |  |  | Mar | 2020-07-04 | 2020-07-16
C38(NB) | INV_N19C1430 | ELY5U | ELY5U | 6 | 1 | New-Qualify | Pass | ME | 2nd source | HDD | change power button adhesive type change from DS-15 to HDD 3565BK(點膠) |  | EL2RY001300 |  |  | 7 |  |  | Jan | 2020-07-04 | 2020-07-16
C38(NB) | TBD | EL432 | EL432532 | 8 | 1 |  | Planning | HDD | New source | WD | HDD 1T H7 WD5000LPSX-08A6WT0 C38 | SHD0P03182 | DD100013I50 |  |  | 1 |  |  |  | 2020-07-04 | 2020-07-16
C38(NB) | TBD | EL532 | EL432532 | 8 | 1 |  | Planning | HDD | New source | WD | HDD 1T H7 WD5000LPSX-08A6WT0 C38 | SHD0P03182 | DD100013I50 |  |  | 1 |  |  |  | 2020-07-04 | 2020-07-16
C38(NB) | TBD | EL531 | EL531 | 16 | 1 |  | Planning | HDD | New source | WD | HDD 1T H7 WD5000LPSX-08A6WT0 C38 | SHD0P03182 | DD100013I50 |  |  | 1 |  |  |  | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2030220 | FLPR5 | FLPR5R7 | 16 | 1 | New-Qualify | Pass | HDD | New source | WD | HDD 1T H7 WD10SPSX-08A6WT0 S C38 | SHD0P03182 | DD100013J80 |  |  | 77.4 |  |  | Mar | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2010520 | EL452 | EL452 | 10 | 1 | New-Qualify | Pass | Panel | New source | INX | FHD IPS 250nits 45% 3.0t INX panel --DC (N140HCA-EAC C5 ) | SD10W91002 | AC60001GAT0 |  | ME leverage FL454 | 65.8 |  |  | Jan | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2010840 | EL432 | EL432532 | 6 | 1 | New-Qualify | Conditional Pass | SSD | New source | UMIS | AM620 SSD_M 512G N4SP4 RPJTJ512MEE1OWX C38 !, | SSS0W76184 | DD900016Y10 | Click here |  | 58.8 |  |  | Jan | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2010830 | EL532 | EL432532 | 6 | 1 | New-Qualify | Conditional Pass | SSD | New source | UMIS | AM620 SSD_M 512G N4SP4 RPJTJ512MEE1OWX C38 !, | SSS0W76184 | DD900016Y10 | Click here |  | 58.8 |  |  | Jan | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2032330 | FL536 | FL436536 | 14 | 1 | New-Qualify | Pass | Panel | New source | BOE | HD TN 220nits 45% BO NT156WHM-N44 V8.0 HDT AG S NB | 5D10P53898 | AC60001HQS0 |  |  | 65.8 |  |  | Mar | 2020-07-04 | 2020-07-16
C38(NB) | TBD | FL536 | FL436536 | 14 | 1 |  | Planning | Panel | New source | INX | HD TN 220nits 45% IN N156BGA-EA3 C2 HDT AG S NB | 5D10P54289 | AC60001EWR0 |  |  | 1 |  |  |  | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2052190 | FL536 | FL436536 | 14 | 1 | New-Qualify | Pass | Panel | New source | AUO | HD TN 220nits 45% AU B156XTN08.1 3A HDT AG S NB | 5D10S74987 | AC60001RK50 |  |  | 65.8 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2010180 | FL536 | FL436536 | 14 | 1 | New-Qualify | Pass | Panel | New source | AUO | FHD TN AU B156HTN06.1 HW:3A FHDT AG NB | 5D10R41285 | AC60001QX50 |  |  | 65.8 |  |  | Jan | 2020-07-04 | 2020-07-16
C38(NB) | TBD | FL536 | FL436536 | 14 | 1 |  | Planning | Panel | New source | AUO | FHD IPS on cell AG 3.2t 250nit AU B156HAK02.0 6A FHDI AG NB(T) | 5D10R59145 | AC60001PO50 |  |  | 1 |  |  |  | 2020-07-04 | 2020-07-16
C38(NB) | TBD | FL536 | FL436536 | 14 | 1 |  | Planning | Panel | New source | BOE | FHD IPS on cell AG 3.2t 250nit BO NV156FHM-T03 V8.0 FHDI AG (T) | 5D10R60839 | AC60001T270 |  |  | 1 |  |  |  | 2020-07-04 | 2020-07-16
C38(NB) | TBD | FL536 | FL436536 | 14 | 1 |  | Planning | Touch Panel | New source | BOE | HD TN w/o BKT on cell Touch LCD BO NT156WHM-T02 V8.0 oncell | 5D10T05360 | AC60001UJ40 |  |  | 1 |  |  |  | 2020-07-04 | 2020-07-16
C38(NB) | TBD | FL536 | FL436536 | 14 | 1 |  | Planning | Touch Panel | New source | AUO | HD TN w/o BKT on cell Touch LCD AU B156XTK02.1 HW0A oncell | 5D10T05359 | AC60001UK50 |  |  | 1 |  |  |  | 2020-07-04 | 2020-07-16
C38(NB) | TBD | FL536 | FL436536 | 14 | 1 |  | Planning | Panel | New source | BOE | FHD IPS BO NV156FHM-N48 V8.2 FHDI AG S NB | 5D10S68976 | AC60001T2Y0 |  |  | 1 |  |  | Jul | 2020-07-04 | 2020-07-16
C38(NB) | TBD | FL436 | FL436536 | 14 | 1 |  | Planning | Panel | New source | INX | HD TN 220nits 45% IN N140BGA-EA4 C2 HDT AG S NB | 5D10M42863 | AC60001EX70 |  |  | 1 |  |  |  | 2020-07-04 | 2020-07-16
C38(NB) | TBD | FL436 | FL436536 | 14 | 1 |  | Planning | Panel | New source | BOE | HD TN 220nits 45% BO NT140WHM-N43 V8.0 HDT AG S NB | 5D10M42866 | AC600019HR0 |  |  | 1 |  |  |  | 2020-07-04 | 2020-07-16
C38(NB) | TBD | FL436 | FL436536 | 14 | 1 |  | Planning | Panel | New source | INX | FHD IPS 250nits 45% 3.0t IN N140HCA-EAC C4 FHDI AG S NB | 5D10R65302 | AC60001GAK0 |  |  | 1 |  |  | Jul | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2052180 | FL436 | FL436536 | 14 | 1 | New-Qualify | Pending | Panel | New source | BOE | FHD IPS 250nits 45% 3.0t BO NV140FHM-N48 V8.2 FHDI AG S NB | 5D10S68975 | AC60001ALV0 | Click here |  | 65.8 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2031520 | FL436 | FL436536 | 14 | 1 | New-Qualify | Conditional Pass | Panel | New source | INX | FHD IPS 250nits 45% 3.0t INX panel --DC (N140HCA-EAC C5 ) | SD10W91002 | AC60001GAT0 | Click here |  | 65.8 |  |  | Mar | 2020-07-04 | 2020-07-16
C38(NB) | TBD | FL536 | FL436536 | 6 | 1 |  | Planning | RAM | New source | Kingston | 4GB D4 26S LV26D4S9S1HJ-4 | SM30N76663 | PK05400B210 |  |  | 1 |  |  |  | 2020-07-04 | 2020-07-16
C38(NB) | TBD | FL436 | FL436536 | 6 | 1 |  | Planning | RAM | New source | Kingston | 4GB D4 26S LV26D4S9S1HJ-4 | SM30N76663 | PK05400B210 |  |  | 1 |  |  |  | 2020-07-04 | 2020-07-16
C38(NB) | INV_N19A1770 | FLIC7 | FLIC7 | 14 | 1 | New-Qualify | Pass | Touch panel | New source | Mutto+AUO | LCD_LED_TS B152487Q3 15.6" FHD C38 ! | ST50X63195 | AC600020G10 |  |  | 106 |  |  | Mar | 2020-07-04 | 2020-07-16
C38(NB) | INV_N19C0710 | ELY5U | ELY5U | 12 | 1 | New-Qualify | Conditional Pass | SSD | New source | WD(SN730) | SSD_M 1T N8SP4 SDBPNTY-1T00-1101 C38 PCIE 2280 | SSS0V13671 | DD900015930 | Click here |  | 58.8 |  |  | Mar | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2030150 | FL535 | FL435535 | 10 | 1 | New-Qualify | Pass | panel | New source | BOE | BO NV156FHM-N48 V8.2 FHDI AG S NB | 5D10S68976 | AC60001T2X0 |  |  | 65.8 |  |  | Mar | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2030140 | FL535 | FL435535 | 10 | 2 | New-Qualify | Pass | panel | New source | INX | IN N156BGA-EA3 C2 HDT AG S NB HD TN 220nits 45% | 5D10P54289 | AC60001EWR0 |  |  | 65.8 |  |  | Mar | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2010030 | FL435 | FL435535 | 10 | 1 | New-Qualify | Pass | panel | New source | BOE | BO NT140WHM-N43 V8.0 HDT AG S NB HD TN 220nits 45% | 5D10M42866 | AC600019HQ0 |  |  | 65.8 |  |  | Jan | 2020-07-04 | 2020-07-16
C38(NB) | TBD | FL435 | FL435535 | 14 | 1 |  | Planning | panel | New source | INX | IN N140HCA-EAC C5 FHDI AG S NB | SD10W91002 | AC60001GAT0 |  |  | 1 |  |  |  | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2020390 | EL5C4 | EL5C4 | 12 | 1 | New-Qualify | Conditional Pass | VRAM | New source | Samsung | S IC D5 256M32 K4G80325FC-HC25 FBGA 170P K4G80325FC-HC25 8Gb 8Gbps GDDR5 | SV20T35751 | SA00009TA60 | Click here |  | 210 |  |  | Mar | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2020470 | EL5C4 | EL5C4 | 12 | 2 | New-Qualify | Pass | EE | 2nd source | LITE ON | S DIO(BR) L05L5V0C6-4C SOT23-6L USB2.0 |  | SC300006800 |  | USB function | 19.3 |  |  | Mar | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2020400 | EL534 | EL434534 | 12 | 1 | New-Qualify | Conditional Pass | VRAM | New source | Samsung | S IC D5 256M32 K4G80325FC-HC25 FBGA 170P K4G80325FC-HC25 8Gb 8Gbps GDDR5 | SV20T35751 | SA00009TA60 | Click here |  | 210 |  |  | Mar | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2020410 | EL434 | EL434534 | 12 | 1 | New-Qualify | Conditional Pass | VRAM | New source | Samsung | S IC D5 256M32 K4G80325FC-HC25 FBGA 170P K4G80325FC-HC25 8Gb 8Gbps GDDR5 | SV20T35751 | SA00009TA60 | Click here |  | 210 |  |  | Mar | 2020-07-04 | 2020-07-16
C38(NB) | INV_N2020450 | EL434534 | EL434534 | 12 | 3 | New-Qualify | Pass | EE | New source | LRC | S SCH DIO LRB751V-40T1G SOD-323 |  | SCS00009500 |  |  | 19.3 |  |  | Mar | 2020-07-04 | 2020-07-16
C38(NB) | TBD | EL4C4 | EL4C4 | 12 | 1 |  | Planning | VRAM | New source | Samsung | S IC D5 256M32 K4G80325FC-HC25 FBGA 170P K4G80325FC-HC25 8Gb 8Gbps GDDR5 | SV20T35751 | SA00009TA60 |  |  | 1 |  |  |  | 2020-07-04 | 2020-07-16
C38(NB) | TBD | FL454 | FL454 | 12 | 1 |  | Planning | VRAM | New source | Samsung | S IC D5 256M32 K4G80325FC-HC25 FBGA 170P K4G80325FC-HC25 8Gb 8Gbps GDDR5 | SV20T35751 | SA00009TA60 |  |  | 1 |  |  |  | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | FOC20 | FOC20 | 6 | 1 | New-Qualify | Fail | CPU | 2nd source | Intel | S IC FJ8070104307803 QSBM V0 1.9G |  | SA0000D8U00 |  |  | 123.74 |  |  | Jan | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | FOC20 | FOC20 | 6 | 1 | New-Qualify | Fail | CPU | 2nd source | Intel | S IC FJ8070104307703 QSBL V0 2.4G |  | SA0000D2A00 |  |  | 123.74 |  |  | Jan | 2020-07-04 | 2020-07-16
C38(NB) | TBD | FLPR5 | FLPR5R7 | 6 | 1 |  | Planning | VRAM | New source | Micron | S IC D6 256M32 MT61K256M32JE-14:A C38 ! | SV20T04513 | SA0000BND30 |  |  | 1 |  |  |  | 2020-07-04 | 2020-07-16
C38(NB) | TBD | FLPR7 | FLPR5R7 | 6 | 1 |  | Planning | VRAM | New source | Micron | S IC D6 256M32 MT61K256M32JE-14:A C38 ! | SV20T04513 | SA0000BND30 |  |  | 1 |  |  |  | 2020-07-04 | 2020-07-16
C38(AIO) | INV_O19A0230 | EOS11 | EOS11 | 8 | 1 | New-Qualify | Pass | SSD | 2nd source | Toshiba | SSD_M 128G N4SP2 KBG40ZMT128G C38(AIO) |  | DD900017P50 |  |  | 61.9 |  |  | Mar | 2020-07-04 | 2020-07-16
C38(NB) | TBD | ELY5U | ELY5U | 12 | 1 |  | Planning | RAM | New source | Samsung | S IC D4 16G/2666 K4AAG165WB-MCTD C38! | SM30N76504 | SA0000B9K10 |  |  | 1 |  |  |  | 2020-07-04 | 2020-07-16
C38(NB) | TBD | ELY5U | ELY5U | 12 | 1 |  | Planning | RAM | New source | Micron | S IC D4 16G/2666 MT40A1G16KNR-075:E C38! | SM30E51324 | SA0000BC720 |  |  | 1 |  |  |  | 2020-07-04 | 2020-07-16
C38(AIO) | INV_O1990050 | FOC11 | FOC11 | 6 | 1 |  | Planning | SSD | 2nd source | Toshiba | SSD_M 128G N4SP2 KBG40ZMT128G C38(AIO) |  | DD900017P50 | [6 empty] | 2020-07-04 | 2020-07-16
C38(AIO) | INV_O1990070 | FOC10 | FOC10 | 6 | 1 |  | Planning | SSD | 2nd source | Toshiba | SSD_M 128G N4SP2 KBG40ZMT128G C38(AIO) |  | DD900017P50 | [6 empty] | 2020-07-04 | 2020-07-16
C38(NB) | TBD | EL334 | EL334 | 12 | 1 |  | Planning | VRAM | New source | Samsung | S IC D5 256M32 K4G80325FC-HC25 FBGA 170P K4G80325FC-HC25 8Gb 8Gbps GDDR5 | SV20T35751 | SA00009TA60 |  |  | 1 |  |  |  | 2020-07-04 | 2020-07-16
C38(NB) | TBD | EL534 | EL434534 | 14 | 1 |  | Planning | Panel | New source | INX | LCD_LED_M N156BGA-EA3 C2 15.6 HD AG C38! |  |  |  |  | 1 |  |  |  | 2020-07-04 | 2020-07-16
C38(NB) | INV_N19B0590 | EL434 | EL434534 | 14 | 2 | New-Qualify | Fail | Panel | New source | BOE | LCD_LED_M NT140WHM-N43 V8.0 HD AG C38! | 5D10M42866 | AC600019HR0 | Click here | ME Leverage EL431 | 65.8 |  |  | Feb | 2020-07-04 | 2020-07-16
C38(AIO) | INV_O2040070 | EOG70 | EOG70 | 8 | 1 | New-Qualify | Fail | HDD | 2nd source | Toshiba | HDD 1T H7 MQ04ABF100 F:JU0A1E C38(AIO) |  | DD10000ZNP0 |  |  | 60.1 |  |  | Feb | 2020-07-04 | 2020-07-16
C38(NB) | TBD | EL4C2 | EL4C2 | 12 | 1 |  | Planning | SSD | New source | Intel | Intel 660P SSD_M 512G N8SP4 SSDPEKNW512G8L C38 2280 | SSS0W90997 | DD900013LB0 |  |  | 1 |  |  |  | 2020-07-04 | 2020-07-16
C38(AIO) | INV_O2060100 | FOC21 | FOC21 | 6 | 1 | Re-Qualify | Pass | SSD+Opante | New source | Intel | OPT_H 512G+32G HBRPEKNX0202AL F:33 C38(AIO) |  | DD900012Q80 |  |  | 46.4 |  |  | Jun | 2020-07-04 | 2020-07-16
C38(AIO) | INV_O2040090 | EOC41 | EOC41 | 8 | 1 | New-Qualify | Fail | HDD | 2nd source | Toshiba | HDD 1T H7 MQ04ABF100 F:JU0A1E C38(AIO) |  | DD10000ZNP0 |  |  | 60.1 |  |  | Feb | 2020-07-04 | 2020-07-16
C38(AIO) | INV_O2040040 | FOC20 | FOC20 | 4 | 1 |  | Planning | HDD | 2nd source | Toshiba | HDD 1T H7 MQ04ABF100 F:JU0A1E C38(AIO) | SHD0X01045 | DD10000ZNP0 | [6 empty] | 2020-07-04 | 2020-07-16
C38(AIO) | INV_O2040040 | FOC21 | FOC21 | 4 | 1 |  | Planning | HDD | 2nd source | Toshiba | HDD 1T H7 MQ04ABF100 F:JU0A1E C38(AIO) |  | DD10000ZNP0 | [6 empty] | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | EOC30 | EOC30 | 6 | 1 |  | Planning | SSD | 2nd source | WD | SDBPMPZ-256G-1001 | SSS0L25785 | DD900019C00 | [6 empty] | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | EOS10 | EOS10 | 4 | 1 | New-Qualify | Pass | HDD | 2nd source | WD | HDD 500G H7 WD5000LPSX-08A6WT0 C38(AIO) ! |  | DD100013I40 |  |  | 60.1 |  |  | Apr | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | EOS11 | EOS11 | 4 | 1 | New-Qualify | Pass | HDD | 2nd source | WD | HDD 500G H7 WD5000LPSX-08A6WT0 C38(AIO) ! |  | DD100013I40 |  |  | 60.1 |  |  | Apr | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | EOS10 | EOS10 | 4 | 1 | Re-Qualify | Pass | RAM | 2nd source | Micron | DDR4 MODU MTA8ATF2G64HZ-3G2E1 16G C38(AIO) |  | PK05400A820 |  |  | 47.1 |  |  | May | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | EOS11 | EOS11 | 4 | 1 | New-Qualify | Fail | RAM | 2nd source | Hynix | DDR4 MODU HMA82GS6DJR8N-XN 16G C38(AIO)!, |  | PK054009E20 |  |  | 47.1 |  |  | Jan | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | EOS10 | EOS10 | 4 | 1 | New-Qualify | Fail | RAM | 2nd source | Hynix | DDR4 MODU HMA82GS6DJR8N-XN 16G C38(AIO)!, |  | PK054009E20 |  |  | 47.1 |  |  | Jan | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | EOC31 | EOC31 | 6 | 1 | New-Qualify | Pass | SSD | 2nd source | UMIS | SSD_M 256G N4SP4 RPJTJ256MEE1OWX C38(AIO) | SSS0L25189 | DD900016W20 | [5 empty] | Apr | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | EOC30 | EOC30 | 6 | 1 | New-Qualify | Pass | SSD | 2nd source | UMIS | SSD_M 256G N4SP4 RPJTJ256MEE1OWX C38(AIO) | SSS0L25189 | DD900016W20 |  |  | 61.9 |  |  | Apr | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | EOS11 | EOS11 | 4 | 1 | New-Qualify | Pass | RAM | 2nd source | Micron | DDR4 MODU MTA4ATF51264HZ-3G2J1 4G C38(AIO) |  | PK054009340 |  |  | 47.1 |  |  | Jan | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | EOS10 | EOS10 | 4 | 1 | New-Qualify | Pass | RAM | 2nd source | Micron | DDR4 MODU MTA4ATF51264HZ-3G2J1 4G C38(AIO) |  | PK054009340 |  |  | 47.1 |  |  | Jan | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | EOC31 | EOC31 | 6 | 1 | New-Qualify | Pass | SSD | 2nd source | UMIS | SSD_M 512G N4SP4 RPJTJ512MEE1OWX C38(AIO) | SSS0L25190 | DD900016Y20 |  |  | 61.9 |  |  | Apr | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | EOC30 | EOC30 | 6 | 1 | New-Qualify | Pass | SSD | 2nd source | UMIS | SSD_M 512G N4SP4 RPJTJ512MEE1OWX C38(AIO) | SSS0L25190 | DD900016Y20 |  |  | 61.9 |  |  | Apr | 2020-07-04 | 2020-07-16
C38(AIO) | TBD | EOC31 | EOC31 | 6 | 1 |  | Planning | SSD | 2nd source | WD | SDBPMPZ-256G-1001 | SSS0L25785 | DD900019C00 | [6 empty] | 2020-07-04 | 2020-07-16
Note on C1: Happy_Zhang: All INV Number we refered to ISPD
Note on D1: Alien: All INV model name information we refered to ISPD
Note on F1: Alien: The quantiy of new build test units by MFG for sustaining test
Note on G1: Alien: Trial part kinds in each unit "1"表示Unit中的第1種Trial part "2"表示Unit中的第2種Trial part "3"表示Unit中的第3種Trial part Note:Trial part kinds should not over 3 in each new build unit
Note on H1: Jenas_Wang: "New-Qualify" 表示第一次测试该材料. "Re-Qualify" 表示该材料之前有测试fail过,现在重新导入
Note on I1: Alien: Fail: INV fail Pass: Qualify pass Pending: Test pause, waiting for FACA and improved samples Planning: Prepared to test but test shcedule is TBC Testing: Test on going
Note on J1: Happy_Zhang: Trail run parts category. Such as: CPU\HDD\RAM\ODD...
Note on M1: Alien: Detail information is nessary e.g. Adapter:輸出電壓;輸出電流 Battery:Cell vendor;cell數量;容量 Camera:像素（1.3M…);F/W;PID:VID CPU:世代 (Penryn...);代號 (T3200…);頻率 (GHz) HDD:世代(ML320…);容量;轉速;H/W;F/W ODD:型號(UJ890A…);H/W;F/W RAM:容量;頻率（MHz);Datecode;chip vendor. LCD:尺寸;鏡面/非鏡面;EDID WLAN:類別（b/g/n…);區域（MOW...);Chip(Broadcom...)
Note on N1: Yin. Rita (CIT): Lenovo要求報告填寫TP Lenovo PN, 可直接從PM處得知, 并填寫.
Note on Q1: Wayne Zhou: 這個欄位你可以寫很多文字，但是不要把欄位寬度變大。看Remark的話可以把Curcer移上去看。
Note on S1: Wayne Zhou: QAD QE 收到INV文。