## IssuesBreakdown-Edit
Project | FFRT Entry unclose issue | SIT Exit unclose issue | 1st FFRT | 2nd FFRT | 3rd FFRT | 4th FFRT | 5th FFRT | 6th FFRT | 分類 | Remark | FFRT | Defect ID | Title | Create date | Update date | Status | Severity | Category | Component | BIOS/KBC | Comments | Author | Assign to | Description | Reproduce steps | Age
HLAV5 | 67 | 41 | 2023-12-05~2023-12-18 | 2023-12-19~2023-12-25 |  |  |  |  | New found_Unidentified | Copilot PCR new feature issue | FFRT1 | 398743 | [S590-14&16IRU_SIT_UMA] Copilot PCR, Press Right Ctrl(Copilot Key) to launch Copilot window, then enter/resume MS/S4 or launch other windows, close Copilot window need press twice Right Ctrl (F/R: 2/2u, 4/4c) | 2023-12-20 | 2023-12-25 | Postpone | 3 | OS | OS | PFCN08WW | Kun 2023-12-25 13:55:58 postpone and keep tracking MS update with MS bug ID Bernie 2023-12-25 13:41:39 Dear JiKun sir, 1.Per 12/25 issue review we submit MS bug 911031 keep tracking MS update. 2.Suggest postpone this issue first. ¦911031¦[Lenovo-NB-S590-14/16IRU-Win11 23H2][Compal] Press Right Ctrl(Copilot Key) to launch Copilot window, then enter/resume MS/S4 or launch other windows, close Copilot window need press twice Right Ctrl (F/R: 2/2u, 4/4c)¦ Bernie 2023-12-20 16:52:21 1.Check S590-15IRU also have the same symptom. 2.Report to MS bug for tracking. 3.Suggest low priortiy to severity 4 for this issue due to Copilot fucntion still not formal version and now copilot key is working normally. ¦911031¦[Lenovo-NB-S590-14/16IRU-Win11 23H2][Compal] Press Right Ctrl(Copilot Key) to launch Copilot window, then enter/resume MS/S4 or launch other windows, close Copilot window need press twice Right Ctrl (F/R: 2/2u, 4/4c)¦ Gary 2023-12-20 15:23:30 Please SA check the issue | Vickie_Wang@compal.com | liulan4 | Test configuration: Image: V8 OS: Win11 23H2 build 22631.2715 Driver: V1.00 BIOS/EC: PFCN08WW/PFEC08WW, 2023/12/14 Edge: V120.0.2210.77 Detect by: Ad-hoc Fail scope: Tested unit: 2units(14-I7U16WFS05#38, 16-I5U08WFS02#02) Failed unit: 2units(14-I7U16WFS05#38, 16-I5U08WFS02#02) F/R: 2/2u, 4/4c Observed symptom: Press Right Ctrl(Copilot Key) to launch Copilot window, then enter/resume MS/S4 or launch other windows, close Copilot window need press twice Right Ctrl Error code/ message: None Expected behavior: Press Right Ctrl(Copilot Key) to launch Copilot window, then enter/resume MS/S4 or launch other windows, close Copilot window need press once Right Ctrl. How to recover: None. | 1.Preload V8 image and after OOBE then enter OS(OS:22621.2715). 2.Install kb5027397 ->update OS to 22631.2715. 3. Install KB999999 in test mode. 4. Connect internet, Open Edge->Settings->About Microsoft Edge->update edge to the latest 120.0.2210.77. 5. Press Right Ctrl(Copilot Key),enter MS/S4/ launch other windows. 6.Found need to press twice Right Ctrl to close Copilot window. | 4
HLAV5 | 67 | 41 | 2023-12-05~2023-12-18 | 2023-12-19~2023-12-25 |  |  |  |  | New found_Stress | Copilot PCR new feature issue | FFRT1 | 398738 | [S590-14&16IRU_SIT_UMA]Copilot PCR, press Right Ctrl(Copilot Key), the folder and characters on the desktop will move when launch or close Copilot window (F/R: 2/2u, 4/4c) | 2023-12-20 | 2023-12-25 | Postpone | 3 | OS | OS | PFCN08WW | Kun 2023-12-25 13:56:43 postpone and keep tracking MS update with MS bug ID Bernie 2023-12-25 13:43:57 Dear JiKun sir, 1.Check S590-15IRU also have the same symptom. 2.Report to MS bug for tracking. 3.Suggest postpone this issue first keep tracking MS update due to Copilot fucntion still not formal version and now copilot key is working normally. ¦911028¦[Lenovo-NB-S590-14/16IRU-Win11 23H2][Compal] press Right Ctrl(Copilot Key), the folder and characters on the desktop will move when launch or close Copilot window (F/R: 2/2u, 4/4c)¦ Bernie 2023-12-20 16:50:45 1.Check S590-15IRU also have the same symptom. 2.Report to MS bug for tracking. 3.Suggest low priortiy to severity 4 for this issue due to Copilot fucntion still not formal version and now copilot key is working normally. ¦911028¦[Lenovo-NB-S590-14/16IRU-Win11 23H2][Compal] press Right Ctrl(Copilot Key), the folder and characters on the desktop will move when launch or close Copilot window (F/R: 2/2u, 4/4c)¦ Gary 2023-12-20 15:23:03 Please SA check the issue | Vickie_Wang@compal.com | liulan4 | Test configuration: Image: V8 OS: Win11 23H2 build 22631.2715. Driver: V1.00 BIOS/EC: PFCN08WW/PFEC08WW, 2023/12/14 Edge: V120.0.2210.77 Detect by: Ad-hoc Fail scope: Tested unit: 2units(14-I7U16WFS05#38, 16-I5U08WFS02#02) Failed unit: 2units(14-I7U16WFS05#38, 16-I5U08WFS02#02) F/R: 2/2u, 4/4c Observed symptom: 1.Press Right Ctrl(Copilot Key),the right folder and characters (Copilot window area) on the desktop will move to left/right when launch/close Copilot window 2.Press Right Ctrl(Copilot Key),the left folder on the desktop will move to right/left when launch/close Copilot window Error code/ message: None Expected behavior: Press Right Ctrl(Copilot Key), the folder and characters on the desktop can show normal when launch or close Copilot window How to recover: None. | 1. Preload V8 image and after OOBE then enter OS(OS:22621.2715). 2. Install kb5027397 ->update OS to 22631.2715. 3. Install KB999999 in test mode. 4. Connect internet, Open Edge->Settings->About Microsoft Edge->update edge to the latest 120.0.2210.77. 5. Press Right Ctrl(Copilot Key), found the folder and characters on the desktop will move. | 4
HLAV5 | 67 | 41 | 2023-12-05~2023-12-18 | 2023-12-19~2023-12-25 |  |  |  |  | New found_MWD | SIT Full Function測試有類似Issue並基於BIOS V2驗證PASS, VGA driver v4953 regression測試Fail again | FFRT1 | 398706 | [S590-14&16 IRU_SIT_UMA] SDC OLED Panel SKU IGCC OPST no function. (F/R:2/2u) | 2023-12-20 | 2023-12-25 | Postpone | 3 | BIOS | BIOS | PFCN08WW | Kun 2023-12-25 13:31:58 aligned to postpone and QD closed, Postopne IvanTY 2023-12-25 11:43:39 Intel provide workaround to modify GOP pnp id of panel 1 not all 00. Suggest postpone. BIOS v09 will fix this issue. IvanTY 2023-12-25 11:36:17 change status. Jager 2023-12-20 15:52:06 Correct Description Gary 2023-12-20 13:56:56 Please SW check the issue Bernie 2023-12-20 13:50:35 Dear Gary sir, 1.It is need BIOS modified GOP for OLED on first priority. 2.BIOS provide test BIOS PFCN08WW.T05.GOP verify on SA side can get pass result. 3.Suggest BIOS team help to check it. Thanks. Gary 2023-12-20 13:44:20 Please SA check the issue | Jager_Gao@compal.com | liulan4 | Description Test configuration: Image: V10 OS: Win11 22H2 build 22621.2715 EN/CN Driver: V1.02 BIOS/EC: PFCN08WW/PFEC08WW, 2023/12/14 IGCC: V1.100.5180.0 VGA driver: 31.0.101.4953 Detect by: CGA010_CF Intel DPST/OPST Fail scope: Tested unit: 2u(14-I7U32WFS06#27; 16-I7U3220S06#02) Failed unit: 2u(14-I7U32WFS06#27; 16-I7U3220S06#02) F/R: 2/2u Observed symptom: SDC OLED Panel SKU IGCC OPST no function. Unit can get pass result on BIOS/EC:PFCN07WW/ PFEC07WW + Image: V08 Error code/ message: None Expected behavior: SDC OLED SKU IGCC OPST function is normal. How to recover: None | Reproduce Steps 1. Power on unit and enter OS. 2. Launch the IGCC. 3. Click System --> Power tab, check DPST status. 4. Find SDC OLED Panel SKU IGCC OPST no function.=>Problem | 4
HLAV5 | 67 | 41 | 2023-12-05~2023-12-18 | 2023-12-19~2023-12-25 |  |  |  |  | Regression Fail | SIT Full Function測試PASS, VGA driver版本更新至v4953後 fail | FFRT1 | 398685 | [S590-14&16 IRU_SIT_UMA] 398685_SDC OLED Panel, Brightness can’t adjust to high level when press brightness+ key after WB.(F/R: 2/2u, 3/10c) | 2023-12-20 | 2023-12-25 | Postpone | 3 | Driver | Graphic | PFCN08WW | Kun 2023-12-25 10:56:35 QD closed and postpone aligned Sam 2023-12-20 13:38:12 Update Description Sam 2023-12-20 13:23:22 Update the title Bernie 2023-12-20 10:16:15 Dear JiKun sir, 1.Brightness can not adjust to high level is cause by Intel VGA driver relate OLED setting wrong. 2.SA base on current v4953 version modified OLED inf setting can not duplicate this issue. 3.Plan fix it and release fixed v4953(Version no change) VGA driver before SS. 4.Suggest for OLED issue set postpone first. Thank you. Bernie 2023-12-20 10:13:06 Change status to working. Gary 2023-12-20 10:01:31 Please SA check the issue | Sam_Ge@compal.com | liulan4 | Test configuration: Image: V10 OS: Win11 22H2 build 22621.2715 EN/CN Driver: V1.02 BIOS/EC: PFCN08WW/PFEC08WW, 2023/12/14 Panel: 14”SDCOLED WUXGA(1920*1200) PN: AC60002K820 , 16” SDC 2K OLED, PN: AC60002OA00 VGA driver: 31.0.101.4953 Detect by: IAA025_CF Display quality Test Fail scope: Tested unit: 2units(14-I7U32WFS06#24,16-I7U3220S06#10) Failed unit: 2units F/R: 2/2u, 3/10c Observed symptom: SDC OLED Panel, Brightness can’t adjust to high level when press brightness+ key after WB. CB/S4 CND this issue(F/R: 0/2u, 0/10c) Taskbar will light flash when resume from WB/CB with dark computer theme. LCD Panel SKU CND this issue(F/R: 0/10u, 0/50c) BIOS: PFCN07WW + Preload: V8 CND this issue when direct WB(F/R: 0/2u, 0/10c) Error code/ message: None Expected behavior: Brightness can adjust to high level when press brightness+ key. How to recover: Press hot key F5(brightness-) or adjust brightness in Settings | 1. Power on unit and enter OS. 2. Press hot key F5 to make the screen low brightness. 3. Do WB. 4. Find Brightness can’t adjust to high level when press brightness+ key after WB.=>Problem. | 4
HLAV5 | 67 | 41 | 2023-12-05~2023-12-18 | 2023-12-19~2023-12-25 |  |  |  |  | New found_Unidentified | VGA Driver 更新時，OLED panel setting copy錯誤 | FFRT1 | 398513 | [S590-14&16IRU_SIT_UMA]SDC OLED Panel, Level10 brightness can’t meet spec(Spec: 360nits~440nits, 14’/16’ result: 314.6nits/313nits). (F/R: 2/2u, 4/4c) | 2023-12-19 | 2023-12-25 | Postpone | 3 | Driver | Graphic | PFCN08WW | Kun 2023-12-25 10:57:05 QD closed and postpone aligned Bernie 2023-12-20 10:10:03 Dear JiKun sir, 1.Brightness can not meet spec is cause by Intel VGA driver relate OLED setting wrong. 2.SA base on current v4953 version modified OLED inf setting to correct and Panel team measure can meet spec. 3.Plan fix it and release fixed v4953 VGA driver before SS. 4.Suggest for OLED issue set postpone first. Thank you. Aaron 2023-12-20 10:04:10 Change status to working. Gary 2023-12-20 10:02:29 Please SA check the issue Gary 2023-12-19 11:30:30 Please SW check the issue Tommy 2023-12-19 11:23:38 Dear Gary sir, 您好，與SA確認，此issue是因 vga 更新導致 (For AC/DC切換亮度改變issue) 需要BIOS team幫忙重新調整亮度設定meet brightness spec. Thanks! Gary 2023-12-19 10:29:42 Please panel team check the issue | Vickie_Wang@compal.com | liulan4 | Test configuration: Image: V10 OS: Win11 22H2 build 22621.2715 EN/CN Driver: V1.02 BIOS/EC: PFCN08WW/PFEC08WW, 2023/12/14 Panel: 14”SDCOLED WUXGA(1920*1200) PN: AC60002K820 , 16” SDC 2K OLED, PN: AC60002OA00 VGA driver: 31.0.101.4953 Detect by: IAA025_CF Display quality test Fail scope: Tested unit: 2units(14-I7U32WFS06#39, 16-I7U3220S06#37) Failed unit: 2units(14-I7U32WFS06#39, 16-I7U3220S06#37) F/R: 2/2u, 4/4c Observed symptom: SDC OLED Panel, Level10 brightness can’t meet spec(Spec: 360nits~440nits, 14’/16’ result: 314.6nits/313nits) Unit can get pass result on BIOS/EC:PFCN07WW/ PFEC07WW + Image: V08 Error code/ message: None Expected behavior: SDC OLED Panel, Level10 brightness can meet spec(Spec:360nits~440nits ). How to recover: None. | 1. Preload image and after OOBE then enter OS. 2. Open pat2.exe, adjust brightness to level10. 3. Measure 5points brightness on each level by C410 brightness color analyzer. 4. Found brightness can’t meet spec. | 5
HLAV5 | 67 | 41 | 2023-12-05~2023-12-18 | 2023-12-19~2023-12-25 |  |  |  |  | New found_Unidentified | SIT Full Function測試PASS, VGA driver版本更新至v4953後 fail | FFRT1 | 398502 | [S590-14&16IRU_SIT_UMA]SDC OLED Panel, Panel brightness will change(14’/16’: 315nits/313nits->280nits&286nits) when plug out adapter. (F/R: 2/2u, 4/4c) | 2023-12-18 | 2023-12-25 | Postpone | 3 | BIOS | BIOS | PFCN08WW | Kun 2023-12-25 13:32:46 aligned to postpone and QD closed, Postopne Kun 2023-12-25 13:32:32 aligned to postpone and QD closed, Postopne IvanTY 2023-12-25 11:46:29 Intel provide workaround to modify GOP pnp id of panel 1 not all 00. Suggest postpone. BIOS v09 will fix this issue. IvanTY 2023-12-25 11:45:36 change status. Gary 2023-12-19 11:13:42 Please SW check the issue Bernie 2023-12-19 10:30:12 Dear Gary sir, 1.It is need BIOS modified GOP for OLED on first priority. 2.BIOS provide test BIOS PFCN08WW.T05.GOP verify on SA side can get pass result. 3.Suggest BIOS team help to check it. Thanks. Vickie 2023-12-19 10:27:53 Update restart in DC mode brightness data. Aaron 2023-12-19 10:19:33 Dear Gary sir, 1.It is need BIOS modified GOP for OLED on first priority. 2.BIOS provide test BIOS PFCN08WW.T05.GOP verify on SA side can get pass result. 3.Suggest BIOS team help to check it. Thanks. Gary 2023-12-19 10:07:27 Please SA check the issue | Vickie_Wang@compal.com | liulan4 | Test configuration: Image: V10 OS: Win11 22H2 build 22621.2715 EN/CN Driver: V1.02 BIOS/EC: PFCN08WW/PFEC08WW, 2023/12/14 Panel: 14”SDCOLED WUXGA(1920*1200) PN: AC60002K820 , 16” SDC 2K OLED, PN: AC60002OA00 VGA driver: 31.0.101.4953 Detect by: CGA005_CF Graphics basic function Fail scope: Tested unit: 2units(14-I7U32WFS06#39, 16-I7U3220S06#37) Failed unit: 2units(14-I7U32WFS06#39, 16-I7U3220S06#37) F/R: 2/2u, 4/4c Observed symptom: 1. Panel Brightness will brighten when plug in adapter and dim when plug out adapter. 2. The around of panel show gray when select white as background in DC mode. 3. Power on in AC mode, unplug adapter, 14’/16’: 5points average brightness changes from 315nits&313nits->280nits&286nits, brightness setting keeps 100%, plug in adapter, brightness recover. 4. Power on in DC mode, measure 5points average brightness is 281nits~286nits, F/R: 2/2units, 10/10cycles. 5. Power on in DC mode, plug in adapter after enter OS, measure 5points average brightness: 313nits~316nits. 6. Restart OS in DC mode, measure 5points average brightness is 312.69nits~314nits. 7. CB in DC mode,measure 5points average brightness is 280.2nits~286.84nits. 8. Issue can’t duplicate after change Settings->System->Display->'Change brightness based on content' to 'Off' Error code/ message: None Expected behavior: Panel display show normal. How to recover: None. | 1.Power on unit and enter OS. 2.Plug in adapter, found brightness brighten 3.Plug out adapter, found brightness dim, set white as background, found the around of panel show gray(AC normal) | 6
HLAV5 | 67 | 41 | 2023-12-05~2023-12-18 | 2023-12-19~2023-12-25 |  |  |  |  | New found_Unidentified | SIT Full Function 3輪 Manual_MS測試CND, FFRT fail | FFRT1 | 398214 | [S590-14&16 IRU_SIT_UMA] Manual_MS, USB port(USB-A&USB-C) cannot recognize the USB device when resume from MS via lid open/power button in AC/DC mode. (F/R: 3/36u,3/2520c) | 2023-12-15 | 2023-12-25 | Fixed | 3 | BIOS | BIOS | PFCN08WW/PFEC08WW | Sam 2023-12-25 12:01:41 Based on RD comment:[ivanty_yu@compal.com 2023-12-22 16:05:00] Based on BIOS v09+image v10, RD test 36 unit pass. F/R: 0/36 units, 0/5000 cycles. So close it by fixed PeterTW 2023-12-25 10:30:21 BIOS 09W add Intel suggest WA to fix this issue. Based on BIOS v09+image v10, RD test 36 unit manual MS pass. F/R: 0/36 units, 0/5000 cycles. IvanTY 2023-12-22 16:05:00 Based on BIOS v09+image v10, RD test 36 unit pass. F/R: 0/36 units, 0/5000 cycles. IvanTY 2023-12-16 17:41:33 IPS 00851149 Re-test Manual MS CND this issue. F/R: 0/50 units x 30 cycles keep duplicate IvanTY 2023-12-16 14:47:22 Re-test Manual MS CND this issue. F/R: 0/50 units x 30 cycles PeterTW 2023-12-15 20:55:38 Analyze failed unit status and provide log to Intel with IPS 00850862. Arrange DQA unit an TPE unit to duplicate issue. Gary 2023-12-15 19:01:48 Please SW check the issue | Sam_Ge@compal.com | Sam_Ge@compal.com | Test configuration: Image: V8 OS: Win11 22H2 build 22621.2715 EN/CN Driver: V1.00 BIOS/EC: PFCN08WW/PFEC08WW, 2023/12/14 Detect by: STA018_EF Stress-Manually Power Management Test Fail scope: Tested unit: 36units Failed unit: 3units (16-I5U08WFS02#08@5, 16-I5U08WFS02#13@1, 16-I5U16WFS01#07@19) F/R: 3/36u, 3/2520c Observed symptom: 1. 16-I5U08WFS02#08, 16-I5U08WFS02#13: USB port(USB-A&USB-C) cannot recognize the USB device when resume from MS after 10mintues via lid open/power button in AC mode. 2. 16-I5U16WFS01#07: USB port(USB-A&USB-C) cannot recognize the USB device when resume from MS via power button in DC mode. Error code/ message: None Expected behavior: System has no BSoD/Blackscreen/Hangup/Error during stress test and test result show pass. How to recover: Do CB | 1. Power on unit and enter OS. 2. Follow test case STA018_EF Stress-Manually Power Management Test do pre-settings. 3. Put the system enter MS by close lid/power button/start menu. 4. Find USB port(USB-A&USB-C) cannot recognize the USB device when resume from MS via lid open/power button in AC/DC mode.=>Problem. | 6
HLAV5 | 67 | 41 | 2023-12-05~2023-12-18 | 2023-12-19~2023-12-25 |  |  |  |  | New found_Unidentified | Issue 需同時打開Media Player 和 Camera APP，並將Media Player放置於Camera APP前面, Test case 無此定義 | FFRT2 | 398212 | [S590-14&16 IRU_SIT_UMA] Media Player window edge show garbage with camera opened. (F/R: 6/54u) | 2023-12-15 | 2023-12-16 | Will not fix | 3 | OS | Graphic | PFCN08WW/PFEC08WW | Kun 2023-12-16 21:50:32 WNF Bernie 2023-12-15 20:16:10 Dear JiKun sir, 1.It is Intel platform common issue and the same with S590-1416MTL TDMS392819. 2.Suggest close it as will not fix. Thank you. Bernie 2023-12-15 20:12:53 Change status to working. Aaron 2023-12-15 20:11:06 1. no the issue if playing the video by media play only. 2. if the window's size of media player is bigger than window camera's, no see the issue. 3. Also can see the issue on Intel MP project S570 or L370...etc. 4. MSFT bug ID is 769494 and MSFT feedback as below. ===== Comments Moved by Partner Bug Service 03/20/2023 05:45 PM UTC ===== Issue confirmed/known. duplicate on tracking bug. =========================================================== Low risk to end users and suggest to set will not fix for the issue. Gary 2023-12-15 18:08:46 Please SA check the issue | Sam_Ge@compal.com | jikun1 | Test configuration: Image: V8 OS: Win11 22H2 build 22621.2715 EN/CN Driver: V1.00 BIOS/EC: PFCN08WW/PFEC08WW, 2023/12/14 Camera:2022.2201.4.0 VGA:31.0.101.4667 Mediaplayer:11.2202.46.0 Detect by: Ad-Hoc Fail scope: Tested unit: 54units Failed unit: 6units (14-I5U16WFS02#17, 16-I5U16WFS01#36, 16-I5U16WFS01#08, 16-I5U16WFS01#12, 16-I7U16WFS03#22, 16-I5U08WFS04#36) F/R: 6/54u Observed symptom: Media Player window edge show garbage with camera opened. Error code/ message: None Expected behavior: Media Player window edge show normally with camera opened. How to recover: None | 1. Power on unit and enter OS. 2. Follow test case STA018_EF Stress-Manually Power Management Test do pre-settings. 3. Open camera. 4. Open Media player and play video. 5. Find Media Player window edge show garbage with camera opened.=>Problem. | 1
HLAV5 | 67 | 41 | 2023-12-05~2023-12-18 | 2023-12-19~2023-12-25 |  |  |  |  | New found_Unidentified | SIT Full Function 5輪 Stress_WB測試CND, Samsung PM9c1a SSD new FW(5L1Q) regression fail | FFRT2 | 398081 | [S590-14&16 IRU_SIT_UMA] Samsung PM9c1a SSD new FW(5L1Q):Stress_ WB, System show critical event 'Web Threat Defense User Service' stopped working in system& security. (F/R:1/30u, 1/9000c) | 2023-12-15 | 2023-12-19 | Postpone | 3 | OS | Windows management | PFCN07WW/PFEC07WW | Kun 2023-12-19 10:46:29 low FR and need keep tracking MS update, postpone Bernie 2023-12-18 15:02:46 Dear JiKun sir 1.Report for MS bug and keep tracking MS update. 2.F/R is low and no end user impact please consider to set S4 or postpone first wait MS update. Bernie 2023-12-15 20:20:37 1.Report for MS bug and keep tracking MS update. 2.F/R is low and no end user impact please consider to set S4 or postpone first wait MS update. Gary 2023-12-15 10:50:39 Please SA cehck the issue | Sam_Ge@compal.com | liulan4 | Test configuration: Image: V8 OS: Win11 22H2 build 22621.2715 EN/CN Driver: V1.00 BIOS/EC: PFCN07WW/PFEC07WW, 2023/12/05 STPM version:V2.6.0.0 SSD: Samsung PM9c1a 1TB FW: 5L1QKXD7 SSD: Samsung PM9c1a 512G FW: 5L1QKXD7 Detect by: STA004_CF: Stress-Warmboot Test Fail scope: Tested unit:30units Failed unit:1u(16-I5U16WFS01#06) F/R: 1/30u,1/9000c Observed symptom: System show critical event 'Web Threat Defense User Service' stopped working in system& security. Error code/ message: None Expected behavior: System has no BSoD/Blackscreen/Hangup/Error during stress test and test result show pass. How to recover: None | 1. Power on unit and enter OS. 2. Follow test case STA004_CF: Stress-WB test do pre-settings. 3. Run Stress_WB test by STPM tool(Count down 90secs before Test, 300counts). 4. Find System show critical event 'Web Threat Defense User Service' stopped working in system& security. =>Problem. | 7
HLAV5 | 67 | 41 | 2023-12-05~2023-12-18 | 2023-12-19~2023-12-25 |  |  |  |  | New found_Unidentified | SIT Full Function 5輪 Stress_WB測試CND, Samsung PM9c1a SSD new FW(5L1Q) regression fail | FFRT2 | 398078 | [S590-14&16 IRU_SIT_UMA] Samsung PM9c1a SSD new FW(5L1Q):Stress_ WB, System show critical event 'Senary Audio Daemon' stopped working in system& security. (F/R:1/30u, 1/9000c) | 2023-12-15 | 2023-12-19 | Postpone | 3 | OS | Windows management | PFCN07WW/PFEC07WW | Kun 2023-12-19 10:47:18 low FR and need keep tracking vendor update, postpone Bernie 2023-12-18 15:04:24 Dear JiKun sir, 1.Report for Senary audio vendor and keep tracking Senary update. 2.F/R is low and no end user impact please consider to set S4 or postpone first wait Senary audio update. Bernie 2023-12-15 19:59:57 1.Report for Senary audio vendor and keep tracking Senary update. 2.F/R is low and no end user impact please consider to set S4 or postpone first wait Senary audio update. Gary 2023-12-15 10:49:49 Please SA check the issue | Sam_Ge@compal.com | liulan4 | Test configuration: Image: V8 OS: Win11 22H2 build 22621.2715 EN/CN Driver: V1.00 BIOS/EC: PFCN07WW/PFEC07WW, 2023/12/05 STPM version:V2.6.0.0 SSD: Samsung PM9c1a 1TB FW: 5L1QKXD7 SSD: Samsung PM9c1a 512G FW: 5L1QKXD7 Detect by: STA004_CF: Stress-Warmboot Test Fail scope: Tested unit:30units Failed unit:1u(16-I5U16WFS01#06) F/R: 1/30u,1/9000c Observed symptom: System show critical event 'Senary Audio Daemon' stopped working in system& security. Error code/ message: None Expected behavior: System has no BSoD/Blackscreen/Hangup/Error during stress test and test result show pass. How to recover: None | 2. Follow test case STA004_CF: Stress-WB test do pre-settings. 3. Run Stress_WB test by STPM tool(Count down 90secs before Test, 300counts). 4. Find System show critical event 'Senary Audio Daemon' stopped working in system& security. =>Problem. | 7
HLAV5 | 67 | 41 | 2023-12-05~2023-12-18 | 2023-12-19~2023-12-25 |  |  |  |  | New found_Unidentified | SIT Full Function 5輪 Stress_WB測試CND, Samsung PM9c1a SSD new FW(5L1Q) regression fail | FFRT2 | 398077 | [S590-14&16 IRU_SIT_UMA] Samsung PM9c1a SSD new FW(5L1Q): Stress_ WB, System show critical event 'Biometric Enrollment Host' stopped working in system& security. (F/R:1/30u, 1/9000c) | 2023-12-15 | 2023-12-19 | Postpone | 3 | OS | Windows management | PFCN07WW/PFEC07WW | Kun 2023-12-19 10:48:06 low FR and need keep tracking MS update, postpone Bernie 2023-12-18 15:05:45 Dear JiKun sir, MS bug ID 870050 to track the issue. SA checked the WindowsHello Face and Finger still can work normally when the event occurred. Biometric Enrollment means the process of collecting biometric data samples from a person and subsequently storing the data in a reference template representing a user's identity, to be used for later comparison. Suggest low priority 4 keep tracking MS update. Bernie 2023-12-18 10:09:50 MS bug ID 870050 to track the issue. SA checked the WindowsHello Face and Finger still can work normally when the event occurred. Biometric Enrollment means the process of collecting biometric data samples from a person and subsequently storing the data in a reference template representing a user's identity, to be used for later comparison. Bernie 2023-12-15 19:58:48 1.Report for MS bug and keep tracking MS update. 2.F/R is low and no end user impact please consider to set S4 or postpone first wait MS update. Gary 2023-12-15 10:47:53 Please SA check the issue | Sam_Ge@compal.com | liulan4 | Test configuration: Image: V8 OS: Win11 22H2 build 22621.2715 EN/CN Driver: V1.00 BIOS/EC: PFCN07WW/PFEC07WW, 2023/12/05 STPM version:V2.6.0.0 SSD: Samsung PM9c1a 1TB FW: 5L1QKXD7 SSD: Samsung PM9c1a 512G FW: 5L1QKXD7 Detect by: STA004_CF: Stress-Warmboot Test Fail scope: Tested unit:30units Failed unit:1u(14-I7U32WFS06#13) F/R: 1/30u,1/9000c Observed symptom: System show critical event 'Biometric Enrollment Host' stopped working in system& security. Error code/ message: None Expected behavior: System has no BSoD/Blackscreen/Hangup/Error during stress test and test result show pass. How to recover: None | 1. Power on unit and enter OS. 2. Follow test case STA004_CF: Stress-WB test do pre-settings. 3. Run Stress_WB test by STPM tool(Count down 90secs before Test, 300counts). 4. Find System show critical event 'Biometric Enrollment Host' stopped working in system& security. =>Problem. | 7
HLAV5 | 67 | 41 | 2023-12-05~2023-12-18 | 2023-12-19~2023-12-25 |  |  |  |  | New found_Unidentified | SIT Full Function 3輪 Manual_S4測試CND, FFRT fail | FFRT2 | 398074 | [S590-14&16 IRU_SIT_UMA] Manual_S4, USB port(USB-A&USB-C) cannot recognize the USB device when resume from S4 via lid open in AC mode. (F/R: 1/36u,1/1512c) | 2023-12-15 | 2023-12-25 | Fixed | 3 | BIOS | BIOS | PFCN07WW/PFEC07WW | Sam 2023-12-25 12:00:01 Based on RD comment:[ivanty_yu@compal.com 2023-12-22 16:05:00] Based on BIOS v09+image v10, RD test 36 unit pass. F/R: 0/36 units, 0/5000 cycles. So close it by fixed PeterTW 2023-12-25 10:34:48 BIOS 09W add Intel suggest WA to fix this issue. Based on BIOS v09+image v10, RD test 36 unit manual S4 pass. F/R: 0/36 units, 0/3000 cycles. IvanTY 2023-12-22 16:06:27 Based on BIOS v09+image v10, RD test 36 unit pass. F/R: 0/36 units, 0/3000 cycles. Sam 2023-12-18 11:26:00 Update the Description IvanTY 2023-12-16 17:43:00 IPS 00850862 Re-test Manual S4 CND this issue. F/R: 0/50 units x 30 cycles keep duplicate IvanTY 2023-12-16 14:48:17 Re-test Manual S4 CND this issue. F/R: 0/50 units x 30 cycles PeterTW 2023-12-15 14:19:29 Analyze failed unit status and provide log to Intel with IPS 00850862. TPE try to duplicate issue. Gary 2023-12-15 10:47:16 Please SW check the issue | Sam_Ge@compal.com | Sam_Ge@compal.com | Test configuration: Image: V8 OS: Win11 22H2 build 22621.2715 EN/CN Driver: V1.00 BIOS/EC: PFCN07WW/PFEC07WW, 2023/12/05 Detect by: STA018_EF Stress-Manually Power Management Test Fail scope: Tested unit: 36units Failed unit: 1unit(16-I5U08WFS02#18@10) F/R: 1/36u,1/1512c Observed symptom: USB port(USB-A&USB-C) cannot recognize the USB device when resume from S4 via lid open in AC mode. Error code/ message: None Expected behavior: System has no BSoD/Blackscreen/Hangup/Error during stress test and test result show pass. How to recover: Do CB | 1. Power on unit and enter OS. 2. Follow test case STA018_EF Stress-Manually Power Management Test do pre-settings. 3. Put the system enter S4 by close lid. 4. USB port(USB-A&USB-C) cannot recognize the USB device when resume from S4 via lid open in AC mode.=>Problem. | 6
HLAV5 | 67 | 41 | 2023-12-05~2023-12-18 | 2023-12-19~2023-12-25 |  |  |  |  | New found_Unidentified | SIT Full Function測試H4_Manual_CB_5℃有類似Issue並已unknown fix, FFRT 測試Manual_S4 fail again. | FFRT2 | 398071 | [S590-14&16 IRU_SIT_UMA] Manual_S4, System show blackscreen w/o backlight(P80:24h) after resume from S4 by start menu in AC mode.(F/R: 1/36u,1/1512c) | 2023-12-15 | 2023-12-20 | CND | 3 | BIOS | BIOS | PFCN07WW/PFEC07WW | Sam 2023-12-20 18:14:21 Per issue review meeting aligned w/ PA/RD, close this issue as CND based on: 1. Issue only occured 1time, and RD retest Manual S4 over triple cycles CND on the fail unit 16-I5U08WFS02#18, F/R: 0/150cycles. 2. RD run stress S4 1200cycles on the CND this issue. 3. RD do manual S4 on total 44 units * 100 cycles CND this issue. PeterTW 2023-12-20 17:57:13 Manual S4 on faied unit 16-I5U08WFS02#18 150 cycles pass. Arrange 44 units manual S4 4400 cycles pass. Discuess with PA/DQA, will go CND. PeterTW 2023-12-18 14:00:42 Fail unit stress S4 pass 1200 cycles. Keep running. IvanTY 2023-12-16 17:50:35 Fail unit stress S4 pass 657 cycles. Re-test Manual S4 CND this issue. F/R: 0/50 units x 30 cycles IvanTY 2023-12-16 14:49:09 Re-test Manual S4 CND this issue. F/R: 0/50 units x 30 cycles PeterTW 2023-12-15 13:51:36 Take fail unit try to get DCI log hang up issue. Gary 2023-12-15 10:45:56 Please SW check the issue | Sam_Ge@compal.com | Sam_Ge@compal.com | Test configuration: Image: V8 OS: Win11 22H2 build 22621.2715 EN/CN Driver: V1.00 BIOS/EC: PFCN07WW/PFEC07WW, 2023/12/05 Detect by: STA018_EF Stress-Manually Power Management Test Fail scope: Tested unit: 36units Failed unit: 1unit(16-I5U08WFS02#18@4) F/R: 1/36u,1/1512c Observed symptom: System show blackscreen w/o backlight(P80:24h) after resume from S4 by start menu in AC mode. Error code/ message: P80:24h Expected behavior: System has no BSoD/Blackscreen/Hangup/Error during stress test and test result show pass. How to recover: Press power button 10s to force shutdown and then power on. | 1. Power on unit and enter OS. 2. Follow test case STA018_EF Stress-Manually Power Management Test do pre-settings. 3. Put the system enter S4 by start menu. 4. Find System show blackscreen w/o backlight(P80:24h) after resume from S4 by start menu in AC mode.=>Problem. | 3
HLAV5 | 67 | 41 | 2023-12-05~2023-12-18 | 2023-12-19~2023-12-25 |  |  |  |  | New found_Unidentified | SIT Full Function 3輪 Manual_S4測試CND, FFRT fail | FFRT2 | 398069 | [S590-14&16 IRU_SIT_UMA] Manual_S4, Windows camera show black screen when resume from S4 via lid open in DC mode.(F/R: 1/36u,1/1512c) | 2023-12-15 | 2023-12-18 | Will not fix | 3 | OS | Camera | PFCN07WW/PFEC07WW | Kun 2023-12-18 12:07:29 low FR and easy recovery, WNF base on MSFT feedback Bernie 2023-12-15 20:18:02 Dear Jikun sir, 1.It is OS common issue and also can found on MP intel/amd platform. 2.When issue occur re-open camera application can recover. 3.We have report to MS before and MS reply "Won't fix" since low user imapct. Thank you. Aaron 2023-12-15 20:08:31 1.It is OS common issue and also can found on MP intel/amd platform. 2.When issue occur re-open camera application can recover. 3.We have report to MS before and MS reply "Won't fix" since low user imapct. Gary 2023-12-15 09:39:53 Please SA check the issue | Sam_Ge@compal.com | jikun1 | Test configuration: Image: V8 OS: Win11 22H2 build 22621.2715 EN/CN Driver: V1.00 BIOS/EC: PFCN07WW/PFEC07WW, 2023/12/05 Camera driver:10.0.22000.20306 Detect by: STA018_EF Stress-Manually Power Management Test Fail scope: Tested unit: 36units Failed unit: 1unit(14-I5U08WFS03#19@37) F/R: 1/36u,1/1512c Observed symptom: Windows camera show black screen when resume from S4 via lid open in DC mode. Error code/ message: None Expected behavior: System has no BSoD/Blackscreen/Hangup/Error during stress test and test result show pass. How to recover: Reopen windows camera. | 1. Power on unit and enter OS. 2. Follow test case STA018_EF Stress-Manually Power Management Test do pre-settings. 3. Put the system enter S4 by close lid. 4. Find Windows camera show black screen when resume from S4 via lid open in DC mode.=>Problem. | 1
Note on K1: 作者: New found_Unidentified New found_MWD: miss wrong damage BIOS/EC/Image/APP 包錯 New found_New Implement New found_Stress Regression Fail UE Adhoc: Out off test cases Late found