## 工作表1
RD Project Plan | Year | DataType | CG | Compal Model | Customer Model | Marketing type (Commercial / Consumer) | Status: Planning =P Executing=E | Customer | Product Type (NB/PAD/AIO/IPC) | Jan | Feb | Mar | Apr | May | Jun | July | Aug | Sep | Oct | Nov | Dec
No | 2024 | Actual | CG13 | ILVR4 | TB Gen6+ 14" Intel Meteor Lake 16:10_i5i7 | SMB/Commercial | E | C38 | NB | Jan: OOC
No | 2024 | Actual | CG13 | ILVR4 | TB Gen6+ 14" Intel Meteor Lake 16:10_i9+7500/8400 RAM | SMB/Commercial | E | C38 | NB | Feb: SIT
Yes | 2024 | Actual | CG13 | ILVR6 | TB Gen6+ 16" Intel Meteor Lake 16:10_i5i7 | SMB/Commercial | E | C38 | NB | Jan: OOC
Yes | 2024 | Actual | CG13 | ILVR6 | TB Gen6+ 16" Intel Meteor Lake 16:10_i9 | SMB/Commercial | E | C38 | NB | Jan: SIT
Yes | 2024 | Actual | CG13 | ILVP4 | TB Gen6+ 14" AMD Hawk Point 16:10 | SMB/Commercial | E | C38 | NB | Jan: OOC
Yes | 2024 | Actual | CG13 | ILVP6 | TB Gen6+ 16" AMD Hawk Point 16:10 | SMB/Commercial | E | C38 | NB | Jan: OOC
No | 2024 | Actual | CG13 | ILS4M | S590 14" Intel MTL H28 (Plastic/Metal) | Consumer | E | C38 | NB | Jan: OOC
No | 2024 | Actual | CG13 | ILS6M | S590 16" Intel MTL H28 (Plastic/Metal) | Consumer | E | C38 | NB | Jan: OOC
Yes | 2024 | Actual | CG13 | ILS4P | S590 14" AMD Hawk Point (Plastic/Metal) (IPCM) | Consumer | E | C38 | NB | Jan: SIT
Yes | 2024 | Actual | CG13 | ILS6P | S590 16" AMD Hawk Point (Plastic/Metal) (IPCM) | Consumer | E | C38 | NB | Jan: SIT
Yes | 2024 | Actual | CG13 | JLS4R | S590 14" RPL-U Refresh | Consumer | E | C38 | NB | Jan: OOC
Yes | 2024 | Actual | CG13 | JLS6R | S590 16" RPL-U Refresh | Consumer | E | C38 | NB | Jan: OOC
Yes | 2024 | Actual | CG13 | JLS5I | S590 15.3" Intel RPL (IPCM) | Consumer | E | C38 | NB | Jan: OOC
Yes | 2024 | Actual | CG15 | JOC10 | AIO 390 24" Intel Raptor Lake H/P/U | AIO | E | C38 | AIO | Jan: OOC
Yes | 2024 | Actual | CG15 | JOC70 | AIO 390 27" Intel Raptor Lake H/P/U | AIO | E | C38 | AIO | Jan: OOC
Yes | 2024 | Actual | CG15 | JOC20 | AIO 390 24" AMD Rembrandt_R | AIO | E | C38 | AIO | Jan: OOC
Yes | 2024 | Actual | CG15 | JOC72 | AIO 390 27" AMD Rembrandt_R | AIO | E | C38 | AIO | Jan: OOC
Yes | 2024 | Actual | CG15 | JOY10 | Neo 50a 24" Gen5 Intel Raptor Lake H/P/U | AIO | E | C38 | AIO | Jan: OOC
Yes | 2024 | Actual | CG15 | JOY70 | Neo 50a 27" Gen5 Intel Raptor Lake H/P/U | AIO | E | C38 | AIO | Jan: OOC
Yes | 2024 | Actual | CG15 | JOK10 | QT A970 24" Intel Raptor Lake U/H | AIO | E | C38 | AIO | Jan: SIT
No | 2024 | Actual | CG15 | JLY20 | Y590s 16" AMD Hawk Point H45 + NV GPU | Consumer | E | C38 | NB | Jan: OOC
Yes | 2024 | Actual | CG15 | JLG50 | L390 15" AMD Hawk Point H45 + NV GPU | Consumer | E | C38 | NB | Jan: OOC
Yes | 2024 | Actual | CG15 | JLY2R | Y590s 16" AMD Rembrandt+ H45 + NV GPU | Consumer | P | C38 | NB | Jan: SIT
Yes | 2024 | Actual | CG15 | JLG52 | L390 15" AMD Rembrandt+ H45 + NV GPU | Consumer | P | C38 | NB | Jan: SIT
No | 2024 | Actual | CG15 | JLY10 | Y590s 16" Intel Raptor Lake HX55 + NV GPU | Consumer | E | C38 | NB | Jan: OOC
No | 2024 | Actual | CG15 | ILYGA | Y790s 16“ Intel Raptor Lake HX55 + NV GPU | Consumer | E | C38 | NB | Jan: OOC
No | 2024 | Actual | CG15 | JLG10 | L390 15" Intel Raptor Lake HX55 + NV GPU wave2 | Consumer | E | C38 | NB | Jan: SIT
Yes | 2024 | Actual | CG15 | JLG20 | L390 15" Intel ADL-HX55 + Intel DG2 GPU wave2 | Consumer | E | C38 | NB | Jan: SIT
Yes | 2024 | Actual | CG15 | JLG12 | L390 15" Intel ADL-HX55 + NV GPU | Consumer | E | C38 | NB | Jan: SIT
Yes | 2024 | Actual | CG15 | Gaming | Copilot key enablement PCR - L390/Y590S/Y790S | Consumer | E | C38 | NB | Jan: SIT
| 2024 | w/o OOC | CG13 | ILVR6 | TB Gen6+ 16" Intel Meteor Lake 16:10 (IPCM) | SMB/Commercial | E | C38 | NB | Jan: SVT/SOVP/SS
| 2024 | w/o OOC | CG13 | ILVP4 | TB Gen6+ 14" AMD Hawk Point 16:10 (IPCM) | SMB/Commercial | E | C38 | NB | Jan: SVT/SOVP/SS
| 2024 | w/o OOC | CG13 | ILVP6 | TB Gen6+ 16" AMD Hawk Point 16:10 (IPCM) | SMB/Commercial | E | C38 | NB | Jan: SVT/SOVP/SS
| 2024 | w/o OOC | CG13 | JLVI4 | Next Gen: TB Gen6+ 14" Intel Arrow Lake-H 16:10 (IPCM) | SMB/Commercial | P | C38 | NB | PCR | PCR | PCR | Kick Off | Kick Off | SDV | SDV | FVT | FVT | FVT | SIT | SIT
| 2024 | w/o OOC | CG13 | JLVI6 | Next Gen: TB Gen6+ 16" Intel Arrow Lake-H 16:10 (IPCM) | SMB/Commercial | P | C38 | NB | PCR | PCR | PCR | Kick Off | Kick Off | SDV | SDV | FVT | FVT | FVT | SIT | SIT
| 2024 | w/o OOC | CG13 | JLVA4 | Next Gen: TB Gen6+ 14" AMD KracKen 16:10 (IPCM) | SMB/Commercial | P | C38 | NB | PCR | PCR | PCR | Kick Off | Kick Off | Kick Off | SDV | SDV | FVT | FVT | SIT | SIT
| 2024 | w/o OOC | CG13 | JLVA6 | Next Gen: TB Gen6+ 16" AMD KracKen 16:10 (IPCM) | SMB/Commercial | P | C38 | NB | PCR | PCR | PCR | Kick Off | Kick Off | Kick Off | SDV | SDV | FVT | FVT | SIT | SIT
| 2024 | w/o OOC | CG13 | IWAP6 IWAP7 IWAP8 | T12 Syrah 13"/14"/15" RPL -R | SMB/Commercial | P | T12 | NB | bar: Jan to Mar
| 2024 | w/o OOC | CG13 | JWADA | T12 Chrome 10.1" Detachable MTK8186 | SMB/Commercial | P | T12 | NB
| 2024 | w/o OOC | CG13 | JMMI4 | T89 Modern 14" Intel RPL-U | SMB/Commercial | P | T89 | NB | Jan: Pre-MP/SS
| 2024 | w/o OOC | CG13 | JMMI5 | T89 Modern 15" Intel RPL-U | SMB/Commercial | P | T89 | NB | Jan: Pre-MP/SS
| 2024 | w/o OOC | CG13 | JMMR4 | T89 Modern 14" Intel RPL-R | SMB/Commercial | P | T89 | NB | Jan: Kick Off; Feb: Kick Off; Mar: SIT; Apr: Pre-MP; May: SS
| 2024 | w/o OOC | CG13 | JMMR5 | T89 Modern 15" Intel RPL-R | SMB/Commercial | P | T89 | NB | Jan: Kick Off; Feb: Kick Off; Mar: SIT; Apr: Pre-MP; May: SS
| 2024 | w/o OOC | CG13 | JMMA4 | T89 Modern 14"AMD BRC-R | SMB/Commercial | P | T89 | NB | Jan: Kick Off; Feb: Kick Off; Mar: SIT; Apr: Pre-MP; May: SS
| 2024 | w/o OOC | CG13 | JMMA5 | T89 Modern 15" AMD LCN | SMB/Commercial | P | T89 | NB | Jan: Kick Off; Feb: Kick Off; Mar: SIT; Apr: Pre-MP; May: SS
| 2024 | w/o OOC | CG13 | ILS4P | S590 14" AMD Hawk Point (Plastic/Metal) (IPCM) | Consumer | E | C38 | NB | Jan: SVT/SOVP; Feb: SS
| 2024 | w/o OOC | CG13 | ILS6P | S590 16" AMD Hawk Point (Plastic/Metal) (IPCM) | Consumer | E | C38 | NB | Jan: SVT/SOVP; Feb: SS
| 2024 | w/o OOC | CG13 | JLS4R | S590 14" RPL-U Refresh | Consumer | E | C38 | NB | Jan: SVT/SOVP; Feb: SS
| 2024 | w/o OOC | CG13 | JLS6R | S590 16" RPL-U Refresh | Consumer | E | C38 | NB | Jan: SVT/SOVP; Feb: SS
| 2024 | w/o OOC | CG13 | JLS5I | S590 15.3" Intel RPL (IPCM) | Consumer | E | C38 | NB | Jan: SVT/SOVP; Feb: SS
| 2024 | w/o OOC | CG13 | JLSI3 | Next Gen: S5X0 13" Intel Arrow Lake | Consumer | P | C38 | NB | RFI | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | FVT | FVT | SIT | SVT
| 2024 | w/o OOC | CG13 | JLSI5 | Next Gen: S5X0 15" Intel Arrow Lake | Consumer | P | C38 | NB | RFI | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | FVT | FVT | SIT | SVT
| 2024 | w/o OOC | CG13 | JLSI4I | Next Gen: S5X0 14" Intel Arrow Lake | Consumer | P | C38 | NB | RFI | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | FVT | FVT | SIT | SVT
| 2024 | w/o OOC | CG13 | JLSI6 | Next Gen: S5X0 16" Intel Arrow Lake | Consumer | P | C38 | NB | RFI | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | FVT | FVT | SIT | SVT
| 2024 | w/o OOC | CG13 | JLSA4 | Next Gen: S5X0 14" AMD KracKen | Consumer | P | C38 | NB | RFI | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | FVT | FVT | SIT | SVT
| 2024 | w/o OOC | CG13 | JLSA6 | Next Gen: S5X0 16" AMD KracKen | Consumer | P | C38 | NB | RFI | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | FVT | FVT | SIT | SVT
| 2024 | w/o OOC | CG13 | JL7I4 | C7 GenX 14" Intel Arrow Lake | Consumer | P | C38 | NB | RFI | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | FVT | FVT | SIT | SVT
| 2024 | w/o OOC | CG13 | JL7I6 | C7 GenX 16" Intel Arrow Lake | Consumer | P | C38 | NB | RFI | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | FVT | FVT | SIT | SVT
| 2024 | w/o OOC | CG13 | JL7A4 | C7 GenX 14" AMD KracKen | Consumer | P | C38 | NB | RFI | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | FVT | FVT | SIT | SVT
| 2024 | w/o OOC | CG13 | JL7A6 | C7 GenX 16" AMD KracKen | Consumer | P | C38 | NB | RFI | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | FVT | FVT | SIT | SVT
| 2024 | w/o OOC | CG15 | JLG50 | L390 15" AMD Hawk Point H45 + NV GPU (PCR) | Gaming | E | C38 | NB | Jan: SOVP/SS
| 2024 | w/o OOC | CG15 | KLG10 | L3X0 15" Intel RPL Refresh HX55 + NV GPU | Gaming | P | C38 | NB | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | FVT | SIT | SVT | SOVP/SS
| 2024 | w/o OOC | CG15 | KLG50 | L3X0 15" AMD Strix Point H45 + NV GPU | Gaming | P | C38 | NB | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | SIT | SIT | SIT | SVT | SOVP/SS
| 2024 | w/o OOC | CG15 | KLG20 | L3X0 15" Intel RPL Refresh HX55 + Intel DG2 GPU | Gaming | P | C38 | NB | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | SIT | SVT | SOVP/SS
| 2024 | w/o OOC | CG15 | JLY20 | Y590s 16" AMD Hawk Point H45 + NV GPU (PCR) | Gaming | E | C38 | NB | bar: Jan
| 2024 | w/o OOC | CG15 | JLY20 | Y590s 16" AMD Rembrandt-H + NV GPU (PCR) | Gaming | P | C38 | NB | Jan: SVT; Feb: SOVP; Mar: SS
| 2024 | w/o OOC | CG15 | KLY10 | Y5X0s 16" Intel Raptor Lake Refresh HX55 + NV GPU | Gaming | P | C38 | NB | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | FVT | SIT | SIT | SVT | SOVP/SS
| 2024 | w/o OOC | CG15 | KLY50 | Y5X0s 16" AMD Strix Point H45 + NV GPU | Gaming | P | C38 | NB | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | SIT | SIT | SIT | SVT | SOVP/SS
| 2024 | w/o OOC | CG15 | KLYGA | Y7X0s 16" Intel Raptor Lake Refresh HX55 + NV GPU | Gaming | P | C38 | NB | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | FVT | SIT | SIT | SVT | SOVP/SS
| 2024 | w/o OOC | CG15 | JOC10 | AIO 390 24" Intel Raptor Lake H/P/U | AIO | E | C38 | AIO | Jan: SOVP/SS
| 2024 | w/o OOC | CG15 | JOC70 | AIO 390 27" Intel Raptor Lake H/P/U | AIO | E | C38 | AIO | Jan: SOVP/SS
| 2024 | w/o OOC | CG15 | JOC20 | AIO 390 24" AMD Rembrandt_R | AIO | E | C38 | AIO | Jan: SOVP/SS
| 2024 | w/o OOC | CG15 | JOC72 | AIO 390 27" AMD Rembrandt_R | AIO | E | C38 | AIO | Jan: SOVP/SS
| 2024 | w/o OOC | CG15 | KOC10 | AIO 3X0 24" Intel Meteor Lake H/P/U | AIO | P | C38 | AIO | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | SDV | SIT | SIT | SVT | SOVP/SS
| 2024 | w/o OOC | CG15 | KOC70 | AIO 3X0 27" Intel Meteor Lake H/P/U | AIO | P | C38 | AIO | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | SDV | SIT | SIT | SVT | SOVP/SS
| 2024 | w/o OOC | CG15 | KOC71 | AIO 3X0 27" QHD Intel Meteor Lake H/P/U | AIO | P | C38 | AIO | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | SDV | SIT | SIT | SVT | SOVP/SS
| 2024 | w/o OOC | CG15 | KOC20 | AIO 3X0 24" AMD Hawk Point U | AIO | P | C38 | AIO | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | SDV | SIT | SIT | SVT | SOVP/SS
| 2024 | w/o OOC | CG15 | KOC72 | AIO 3X0 27" AMD Hawk Point U | AIO | P | C38 | AIO | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | SDV | SIT | SIT | SVT | SOVP/SS
| 2024 | w/o OOC | CG15 | JOY10 | Neo 50a 24" Gen5 Intel Raptor Lake H/P/U | AIO | E | C38 | AIO | Jan: SOVP/SS
| 2024 | w/o OOC | CG15 | JOY70 | Neo 50a 27" Gen5 Intel Raptor Lake H/P/U | AIO | E | C38 | AIO | Jan: SOVP/SS
| 2024 | w/o OOC | CG15 | KOY10 | Neo 50a 24" Gen6 Intel Meteor Lake H/P/U | AIO | P | C38 | AIO | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | SDV | SIT | SIT | SVT | SOVP/SS
| 2024 | w/o OOC | CG15 | KOY70 | Neo 50a 27" Gen6 Intel Meteor Lake H/P/U | AIO | P | C38 | AIO | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | SDV | SIT | SIT | SVT | SOVP/SS
| 2024 | w/o OOC | CG15 | JOK10 | QT A970 24" Intel Raptor Lake U/H | AIO | E | C38 | AIO | Jan: SVT/SS
| 2024 | w/o OOC | CG15 | KOK10 | QT A970 24" Intel Meteor Lake U/H | AIO | P | C38 | AIO | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | SDV | SIT | SIT | SVT | SOVP/SS
| 2024 | w/o OOC | CG15 | JOG32 | Yoga 9 32" Refresh Intel Lunar Lake | AIO | E | C38 | AIO | Kick Off | SDV | SDV | SDV | FVT | FVT | FVT | FVT | SIT | SIT | SVT | SOVP/SS
| 2024 | w/o OOC | CG15 | KOA32 | 32" Bendable AIO Intel Meteor Lake H | AIO | P | C38 | AIO |  |  | RFQ | RFQ | RFQ | Kick Off | SDV | SDV | FVT | FVT | SIT | SVT
| 2024 | w/o OOC | CG5 | JLSVB | Server (Venice -AMD) L10 commodity, 2400W | Server | P | C38 | Server | Design Join | Design Join | SIT | SIT | SIT | SIT | SIT | SVT | SVT | SVT | SVT | SOVP/SS
| 2024 | w/o OOC | CG5 | JLSVA | Server (BHS MS "Perth" Intel) Birch Stream platform 1U/2U | Server | P | C38 | Server | RFI | RFQ | RFQ | RFQ | Kick Off | SDV | SDV | SDV | SIT | SIT | SVT | SOVP/SS
| 2024 | with OOC | CG13 | ILVR6 | TB Gen6+ 16" Intel Meteor Lake 16:10 (IPCM) | SMB/Commercial | E | C38 | NB | Jan: OOC; Feb: OOC
| 2024 | with OOC | CG13 | ILVP4 | TB Gen6+ 14" AMD Hawk Point 16:10 (IPCM) | SMB/Commercial | E | C38 | NB | Jan: OOC; Feb: OOC
| 2024 | with OOC | CG13 | ILVP6 | TB Gen6+ 16" AMD Hawk Point 16:10 (IPCM) | SMB/Commercial | E | C38 | NB | Jan: OOC; Feb: OOC
| 2024 | with OOC | CG13 | JLVI4 | Next Gen: TB Gen6+ 14" Intel Arrow Lake-H 16:10 (IPCM) | SMB/Commercial | P | C38 | NB | PCR | PCR | PCR | Kick Off | Kick Off | SDV | SDV | FVT | FVT | FVT | SIT | SIT
| 2024 | with OOC | CG13 | JLVI6 | Next Gen: TB Gen6+ 16" Intel Arrow Lake-H 16:10 (IPCM) | SMB/Commercial | P | C38 | NB | PCR | PCR | PCR | Kick Off | Kick Off | SDV | SDV | FVT | FVT | FVT | SIT | SIT
| 2024 | with OOC | CG13 | JLVA4 | Next Gen: TB Gen6+ 14" AMD KracKen 16:10 (IPCM) | SMB/Commercial | P | C38 | NB | PCR | PCR | PCR | Kick Off | Kick Off | Kick Off | SDV | SDV | FVT | FVT | SIT | SIT
| 2024 | with OOC | CG13 | JLVA6 | Next Gen: TB Gen6+ 16" AMD KracKen 16:10 (IPCM) | SMB/Commercial | P | C38 | NB | PCR | PCR | PCR | Kick Off | Kick Off | Kick Off | SDV | SDV | FVT | FVT | SIT | SIT
| 2024 | with OOC | CG13 | IWAP6 IWAP7 IWAP8 | T12 Syrah 13"/14"/15" RPL -R | SMB/Commercial | P | T12 | NB | bar: Jan to Mar
| 2024 | with OOC | CG13 | JWADA | T12 Chrome 10.1" Detachable MTK8186 | SMB/Commercial | P | T12 | NB
| 2024 | with OOC | CG13 | JMMI4 | T89 Modern 14" Intel RPL-U | SMB/Commercial | P | T89 | NB | Jan: Pre-MP/SS
| 2024 | with OOC | CG13 | JMMI5 | T89 Modern 15" Intel RPL-U | SMB/Commercial | P | T89 | NB | Jan: Pre-MP/SS
| 2024 | with OOC | CG13 | JMMR4 | T89 Modern 14" Intel RPL-R | SMB/Commercial | P | T89 | NB | Jan: Kick Off; Feb: Kick Off; Mar: SIT; Apr: Pre-MP; May: SS
| 2024 | with OOC | CG13 | JMMR5 | T89 Modern 15" Intel RPL-R | SMB/Commercial | P | T89 | NB | Jan: Kick Off; Feb: Kick Off; Mar: SIT; Apr: Pre-MP; May: SS
| 2024 | with OOC | CG13 | JMMA4 | T89 Modern 14"AMD BRC-R | SMB/Commercial | P | T89 | NB | Jan: Kick Off; Feb: Kick Off; Mar: SIT; Apr: Pre-MP; May: SS
| 2024 | with OOC | CG13 | JMMA5 | T89 Modern 15" AMD LCN | SMB/Commercial | P | T89 | NB | Jan: Kick Off; Feb: Kick Off; Mar: SIT; Apr: Pre-MP; May: SS
| 2024 | with OOC | CG13 | ILS4M | S590 14" Intel MTL H28 (Plastic/Metal) | Consumer | E | C38 | NB | Jan: OOC; Feb: OOC
| 2024 | with OOC | CG13 | ILS6M | S590 16" Intel MTL H28 (Plastic/Metal) | Consumer | E | C38 | NB | Jan: OOC; Feb: OOC
| 2024 | with OOC | CG13 | ILS4P | S590 14" AMD Hawk Point (Plastic/Metal) (IPCM) | Consumer | E | C38 | NB | Jan: OOC; Feb: OOC; Mar: OOC
| 2024 | with OOC | CG13 | ILS6P | S590 16" AMD Hawk Point (Plastic/Metal) (IPCM) | Consumer | E | C38 | NB | Jan: OOC; Feb: OOC; Mar: OOC
| 2024 | with OOC | CG13 | JLS4R | S590 14" RPL-U Refresh | Consumer | E | C38 | NB | Jan: OOC; Feb: OOC; Mar: OOC
| 2024 | with OOC | CG13 | JLS6R | S590 16" RPL-U Refresh | Consumer | E | C38 | NB | Jan: OOC; Feb: OOC; Mar: OOC
| 2024 | with OOC | CG13 | JLS5I | S590 15.3" Intel RPL (IPCM) | Consumer | E | C38 | NB | Jan: OOC; Feb: OOC
| 2024 | with OOC | CG13 | JLSI3 | Next Gen: S5X0 13" Intel Arrow Lake | Consumer | P | C38 | NB | RFI | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | FVT | FVT | SIT | SVT
| 2024 | with OOC | CG13 | JLSI5 | Next Gen: S5X0 15" Intel Arrow Lake | Consumer | P | C38 | NB | RFI | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | FVT | FVT | SIT | SVT
| 2024 | with OOC | CG13 | JLSI4I | Next Gen: S5X0 14" Intel Arrow Lake | Consumer | P | C38 | NB | RFI | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | FVT | FVT | SIT | SVT
| 2024 | with OOC | CG13 | JLSI6 | Next Gen: S5X0 16" Intel Arrow Lake | Consumer | P | C38 | NB | RFI | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | FVT | FVT | SIT | SVT
| 2024 | with OOC | CG13 | JLSA4 | Next Gen: S5X0 14" AMD KracKen | Consumer | P | C38 | NB | RFI | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | FVT | FVT | SIT | SVT
| 2024 | with OOC | CG13 | JLSA6 | Next Gen: S5X0 16" AMD KracKen | Consumer | P | C38 | NB | RFI | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | FVT | FVT | SIT | SVT
| 2024 | with OOC | CG13 | JL7I4 | C7 GenX 14" Intel Arrow Lake | Consumer | P | C38 | NB | RFI | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | FVT | FVT | SIT | SVT
| 2024 | with OOC | CG13 | JL7I6 | C7 GenX 16" Intel Arrow Lake | Consumer | P | C38 | NB | RFI | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | FVT | FVT | SIT | SVT
| 2024 | with OOC | CG13 | JL7A4 | C7 GenX 14" AMD KracKen | Consumer | P | C38 | NB | RFI | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | FVT | FVT | SIT | SVT
| 2024 | with OOC | CG13 | JL7A6 | C7 GenX 16" AMD KracKen | Consumer | P | C38 | NB | RFI | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | FVT | FVT | SIT | SVT
| 2024 | with OOC | CG15 | JLG50 | L390 15" AMD Hawk Point H45 + NV GPU (PCR) | Gaming | E | C38 | NB | Jan: SOVP/SS
| 2024 | with OOC | CG15 | KLG10 | L3X0 15" Intel RPL Refresh HX55 + NV GPU | Gaming | P | C38 | NB | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | FVT | SIT | SVT | SOVP/SS
| 2024 | with OOC | CG15 | KLG50 | L3X0 15" AMD Strix Point H45 + NV GPU | Gaming | P | C38 | NB | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | SIT | SIT | SIT | SVT | SOVP/SS
| 2024 | with OOC | CG15 | KLG20 | L3X0 15" Intel RPL Refresh HX55 + Intel DG2 GPU | Gaming | P | C38 | NB | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | SIT | SVT | SOVP/SS
| 2024 | with OOC | CG15 | JLY20 | Y590s 16" AMD Hawk Point H45 + NV GPU (PCR) | Gaming | E | C38 | NB | bar: Jan
| 2024 | with OOC | CG15 | JLY20 | Y590s 16" AMD Rembrandt-H + NV GPU (PCR) | Gaming | P | C38 | NB | Jan: SVT; Feb: SOVP; Mar: SS
| 2024 | with OOC | CG15 | KLY10 | Y5X0s 16" Intel Raptor Lake Refresh HX55 + NV GPU | Gaming | P | C38 | NB | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | FVT | SIT | SIT | SVT | SOVP/SS
| 2024 | with OOC | CG15 | KLY50 | Y5X0s 16" AMD Strix Point H45 + NV GPU | Gaming | P | C38 | NB | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | SIT | SIT | SIT | SVT | SOVP/SS
| 2024 | with OOC | CG15 | KLYGA | Y7X0s 16" Intel Raptor Lake Refresh HX55 + NV GPU | Gaming | P | C38 | NB | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | FVT | SIT | SIT | SVT | SOVP/SS
| 2024 | with OOC | CG15 | JOC10 | AIO 390 24" Intel Raptor Lake H/P/U | AIO | E | C38 | AIO | Jan: OOC
| 2024 | with OOC | CG15 | JOC70 | AIO 390 27" Intel Raptor Lake H/P/U | AIO | E | C38 | AIO | Jan: OOC
| 2024 | with OOC | CG15 | JOC20 | AIO 390 24" AMD Rembrandt_R | AIO | E | C38 | AIO | Jan: OOC
| 2024 | with OOC | CG15 | JOC72 | AIO 390 27" AMD Rembrandt_R | AIO | E | C38 | AIO | Jan: OOC
| 2024 | with OOC | CG15 | KOC10 | AIO 3X0 24" Intel Meteor Lake H/P/U | AIO | P | C38 | AIO | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | SDV | SIT | SIT | SVT | SOVP/SS
| 2024 | with OOC | CG15 | KOC70 | AIO 3X0 27" Intel Meteor Lake H/P/U | AIO | P | C38 | AIO | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | SDV | SIT | SIT | SVT | SOVP/SS
| 2024 | with OOC | CG15 | KOC71 | AIO 3X0 27" QHD Intel Meteor Lake H/P/U | AIO | P | C38 | AIO | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | SDV | SIT | SIT | SVT | SOVP/SS
| 2024 | with OOC | CG15 | KOC20 | AIO 3X0 24" AMD Hawk Point U | AIO | P | C38 | AIO | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | SDV | SIT | SIT | SVT | SOVP/SS
| 2024 | with OOC | CG15 | KOC72 | AIO 3X0 27" AMD Hawk Point U | AIO | P | C38 | AIO | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | SDV | SIT | SIT | SVT | SOVP/SS
| 2024 | with OOC | CG15 | JOY10 | Neo 50a 24" Gen5 Intel Raptor Lake H/P/U | AIO | E | C38 | AIO | Jan: OOC
| 2024 | with OOC | CG15 | JOY70 | Neo 50a 27" Gen5 Intel Raptor Lake H/P/U | AIO | E | C38 | AIO | Jan: OOC
| 2024 | with OOC | CG15 | KOY10 | Neo 50a 24" Gen6 Intel Meteor Lake H/P/U | AIO | P | C38 | AIO | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | SDV | SIT | SIT | SVT | SOVP/SS
| 2024 | with OOC | CG15 | KOY70 | Neo 50a 27" Gen6 Intel Meteor Lake H/P/U | AIO | P | C38 | AIO | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | SDV | SIT | SIT | SVT | SOVP/SS
| 2024 | with OOC | CG15 | JOK10 | QT A970 24" Intel Raptor Lake U/H | AIO | E | C38 | AIO | Jan: SVT/SS
| 2024 | with OOC | CG15 | KOK10 | QT A970 24" Intel Meteor Lake U/H | AIO | P | C38 | AIO | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | SDV | SIT | SIT | SVT | SOVP/SS
| 2024 | with OOC | CG15 | JOG32 | Yoga 9 32" Refresh Intel Lunar Lake | AIO | E | C38 | AIO | Kick Off | SDV | SDV | SDV | FVT | FVT | FVT | FVT | SIT | SIT | SVT | SOVP/SS
| 2024 | with OOC | CG15 | KOA32 | 32" Bendable AIO Intel Meteor Lake H | AIO | P | C38 | AIO |  |  | RFQ | RFQ | RFQ | Kick Off | SDV | SDV | FVT | FVT | SIT | SVT
| 2024 | with OOC | CG5 | JLSVB | Server (Venice -AMD) L10 commodity, 2400W | Server | P | C38 | Server | Design Join | Design Join | SIT | SIT | SIT | SIT | SIT | SVT | SVT | SVT | SVT | SOVP/SS
| 2024 | with OOC | CG5 | JLSVA | Server (BHS MS "Perth" Intel) Birch Stream platform 1U/2U | Server | P | C38 | Server | RFI | RFQ | RFQ | RFQ | Kick Off | SDV | SDV | SDV | SIT | SIT | SVT | SOVP/SS