## Change History
Change History
Date | Modified Items | Owner
2024-01-11 | Initial Release | Canny_Xing

## Comparison_C38&T89
[9 empty] | 已發生 | 已發生 | 已發生 | 已發生 | 已發生 | 預估 | 預估 | 預估 | 預估 | 預估 | 預估 | 預估
[6 empty] | 差異 (實際 - 預算) |  | Phase | Jan | Feb | Mar | Apr | May | Jun | July | Aug | Sep | Oct | Nov | Dec | Total
[8 empty] | FVT | 0 | 0 | 1 | 1 | 1 | 1 | -2 | -4 | -9 | -5 | 12 | 4 | 0
[8 empty] | SIT | 11 | 7 | 1 | 3 | 5 | 8 | 10 | 0 | -7 | -6 | -11 | 10 | 31
[8 empty] | OOC | 2 | 2 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
[8 empty] | OS-R | 0 | 0 | 13 | 20 | 24 | 29 | 15 | 4 | 0 | 0 | 0 | 0 | 105
|  | Actual: | 填入每月實際，注意與Gatt相對應 |  |  | 實際 |  | FVT | 0 | 0 | 1 | 1 | 2 | 2 | 0 | 1 | 6 | 10 | 12 | 4
[8 empty] | SIT | 11 | 7 | 6 | 4 | 6 | 9 | 11 | 4 | 7 | 8 | 4 | 14
[8 empty] | OOC | 19 | 13 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | OS-R | 0 | 0 | 13 | 20 | 24 | 29 | 15 | 4 | 0 | 0 | 0 | 0
2024 Project Acutal
RD Project Plan | No. | CG | Compal Model | Customer Model | Marketing type (Gaming / Consumer / SMB) | Status: Planning =P Executing=E | Customer | Product Type (NB/PAD/AIO/IPC) | Jan | Feb | Mar | Apr | May | Jun | July | Aug | Sep | Oct | Nov | Dec
No | 1 | CG5 | ILVR4 | TB Gen6+ 14" Intel Meteor Lake 16:10_i5i7 | SMB | E | C38 | NB | Jan: OOC; Feb: OOC; Mar: OOC | i5/i7 SS Delay to 1/8
No | 2 | CG5 | ILVR4 | TB Gen6+ 14" Intel Meteor Lake 16:10_i9 | SMB | E | C38 | NB | Feb: SIT; Mar: SIT; Apr: SIT; May: SIT
Yes | 3 | CG5 | ILVR6 | TB Gen6+ 16" Intel Meteor Lake 16:10_i5i7 | SMB | E | C38 | NB | Jan: OOC; Feb: OOC; Mar: OOC
No | 4 | CG5 | ILVR6 | TB Gen6+ 16" Intel Meteor Lake 16:10_i9 | SMB | E | C38 | NB | Jan: SIT; Feb: SIT; Mar: SIT; Apr: SIT
No | 5 | CG5 | ILVR4 | TB Gen6+ 14" Intel Meteor Lake_GSKU | SMB | E | C38 | NB | Jun: SIT; July: SIT
No | 6 | CG5 | ILVR6 | TB Gen6+ 16" Intel Meteor Lake_GSKU | SMB | E | C38 | NB | Jun: SIT; July: SIT
Yes | 7 | CG5 | ILVP4 | TB Gen6+ 14" AMD Hawk Point 16:10 | SMB | E | C38 | NB | Jan: OOC; Feb: OOC; Mar: OOC
Yes | 8 | CG5 | ILVP6 | TB Gen6+ 16" AMD Hawk Point 16:10 | SMB | E | C38 | NB | Jan: OOC; Feb: OOC; Mar: OOC
No | 9 | CG5 | JLVP4 | TB Gen7+ 14" AMD Strix Point | SMB | E | C38 | NB | May: FVT; Jun: FVT; July: SIT; Aug: SIT; Sep: SOVP/SS
No | 10 | CG5 | JLVP6 | TB Gen7+ 16" AMD Strix Point | SMB | E | C38 | NB | May: FVT; Jun: FVT; July: SIT; Aug: SIT; Sep: SOVP/SS
Yes | 11 | CG5 | JLVI4 | TB Gen7+ 14" Intel Arrow Lake-H | SMB | P | C38 | NB | Aug: SDV; Sep: SDV; Oct: FVT; Nov: FVT; Dec: SIT
Yes | 12 | CG5 | JLVI4 | TB Gen7+ 14" Intel Arrow Lake-H_GN22 X2X4 | SMB | P | C38 | NB | Nov: FVT; Dec: FVT
Yes | 13 | CG5 | JLVI6 | TB Gen7+ 16" Intel Arrow Lake-H | SMB | P | C38 | NB | Sep: SDV; Oct: FVT; Nov: FVT; Dec: SIT
Yes | 14 | CG5 | JLVI6 | TB Gen7+ 16" Intel Arrow Lake-H_GN22 X2X4 | SMB | P | C38 | NB | Oct: SDV; Nov: FVT; Dec: FVT
Yes | 15 | CG5 | JLVA4 | TB Gen7+ 14" AMD KracKen | SMB | P | C38 | NB | Dec: SIT
Yes | 16 | CG5 | JLVA6 | TB Gen7+ 16" AMD KracKen | SMB | P | C38 | NB | Dec: SIT
No | 17 | CG13 | ILS4M | S590 14" Intel MTL H28 (Plastic/Metal) | Consumer | E | C38 | NB | Jan: OOC; Feb: OOC
No | 18 | CG13 | ILS6M | S590 16" Intel MTL H28 (Plastic/Metal) | Consumer | E | C38 | NB | Jan: OOC; Feb: OOC
Yes | 19 | CG13 | ILS4P | S590 14" AMD Hawk Point (Plastic/Metal) (IPCM) | Consumer | E | C38 | NB | Jan: SIT; Feb: OOC; Mar: OOC
Yes | 20 | CG13 | ILS6P | S590 16" AMD Hawk Point (Plastic/Metal) (IPCM) | Consumer | E | C38 | NB | Jan: SIT; Feb: OOC; Mar: OOC
Yes | 21 | CG13 | JLS4R | S590 14" RPL-U Refresh | Consumer | E | C38 | NB | Jan: OOC; Feb: OOC; Mar: OOC
Yes | 22 | CG13 | JLS6R | S590 16" RPL-U Refresh | Consumer | E | C38 | NB | Jan: OOC; Feb: OOC; Mar: OOC
Yes | 23 | CG13 | JLS5I | S590 15.3" Intel RPL (IPCM) | Consumer | E | C38 | NB | Jan: OOC; Feb: OOC; Mar: OOC
No | 24 | CG13 | JLS4Q | S590-14 Qualcomm | Consumer | E | C38 | NB | Feb: SDV; Mar: FVT; Apr: FVT; May: SIT; Jun: SIT; July: SIT; Aug: SOVP/SS
No | 25 | CG13 | KLS5H | S590 15.3" Intel RPH refresh (H45) | Consumer | E | C38 | NB | Aug: SDV; Sep: SIT; Oct: SIT; Nov: SOVP/SS
No | 26 | CG13 | KLS5I | S5 Pro 14" Intel Arrow Lake | Consumer | E | C38 | NB | July: SDV; Aug: SDV; Sep: FVT; Oct: FVT; Nov: FVT; Dec: SIT
No | 27 | CG13 | KLS7I | S7 Pro 14.5" Intel Arrow Lake | Consumer | E | C38 | NB | July: SDV; Aug: SDV; Sep: FVT; Oct: FVT; Nov: FVT; Dec: SIT
No | 28 | CG13 | KLS5A | S5 Pro 14" AMD KracKen / AMD Strix Point | Consumer | E | C38 | NB | Aug: SDV; Sep: SDV; Oct: FVT; Nov: FVT; Dec: SIT
No | 29 | CG13 | KLS7A | S7 Pro 14.5" AMD KracKen / AMD Strix Point | Consumer | E | C38 | NB | Aug: SDV; Sep: SDV; Oct: FVT; Nov: FVT; Dec: SIT
No | 30 | CG13 | KLS7D | S7 Pro 14.5" Intel Arrow Lake + NV GN22 GPU | Consumer | E | C38 | NB | Sep: SDV; Oct: SDV; Nov: FVT; Dec: FVT
No | 31 | CG13 | KLS71 | Slim7 14" Intel Lunar Lake | Consumer | E | C38 | NB | July: SDV; Aug: FVT; Sep: FVT; Oct: SIT; Nov: SIT; Dec: SVT
No | 32 | CG13 | KLS72 | Slim7 14" AMD KracKen | Consumer | E | C38 | NB | Aug: SDV; Sep: FVT; Oct: FVT; Nov: SIT; Dec: SIT
Yes | 33 | CG15 | JLY20 | Y590s 16" AMD Hawk Point H45 + NV GPU | Gaming | E | C38 | NB | Jan: OOC; Feb: OOC
Yes | 34 | CG15 | JLG50 | L390 15" AMD Hawk Point H45 + NV GPU | Gaming | E | C38 | NB | Jan: OOC
Yes | 35 | CG15 | JLY2R | Y590s 16" AMD Rembrandt+ H45 + NV GPU | Gaming | E | C38 | NB | Jan: SIT; Feb: SIT; Mar: SIT
No | 36 | CG15 | JLG52 | L390 15" AMD Rembrandt(W/O IGPU) H45 + NV GPU | Gaming | E | C38 | NB | Jan: SIT; Feb: SIT; Mar: SIT
Yes | 37 | CG15 | JLY10 | Y590s 16" Intel Raptor Lake HX55 + NV GPU | Gaming | E | C38 | NB | Jan: OOC; Feb: OOC
Yes | 38 | CG15 | ILYGA | Y790s 16“ Intel Raptor Lake HX55 + NV GPU | Gaming | E | C38 | NB | Jan: OOC
Yes | 39 | CG15 | JLG10 | L390 15" Intel Raptor Lake HX55 + NV GPU wave2 | Gaming | E | C38 | NB | Jan: SIT; Feb: SIT
No | 40 | CG15 | JLG20 | L390 15" Intel ADL-HX55 + Intel DG2 GPU wave2 | Gaming | E | C38 | NB | Jan: SIT
No | 41 | CG15 | JLG12 | L390 15" Intel ADL-HX55 + NV GPU | Gaming | E | C38 | NB | Jan: SIT; Feb: SIT; Mar: SIT
No | 42 | CG15 | Gaming | Copilot key enablement PCR - L390/Y590S/Y790S | Gaming | E | C38 | NB | Jan: SIT
No | 43 | CG15 | Gaming | Y590s 16" Intel Raptor Lake HX55 + NV GPU LAA AI APP | Gaming | E | C38 | NB | Jan: SIT; Feb: SIT
No | 44 | CG15 | Gaming | Y590s 16" AMD Rembrandt(W/O IGPU) H45 + NV GPU | Gaming | P | C38 | NB | Apr: SIT; May: SIT
No | 45 | CG15 | Gaming | Y790s 16" Intel Raptor Lake HX55 + NV GPU LAA AI APP | Gaming | E | C38 | NB | Mar: SIT; Apr: SIT
No | 46 | CG15 | JLG52 | L390 15" AMD Rembrandt(W/O IGPU) H45 + X6 GPU | Gaming | E | C38 | NB | Apr: SDV; May: SIT; Jun: SIT
Yes | 47 | CG15 | TBD | L3X0 15" Intel RPL Refresh HX55 + NV GPU | Gaming | P | C38 | NB | July: SDV; Aug: SDV; Sep: SDV; Oct: SDV; Nov: FVT; Dec: SIT
No | 48 | CG15 | TBD | L3X0 17" Intel RPL Refresh HX55 + NV GPU | Gaming | P | C38 | NB | Sep: SDV; Oct: SDV; Nov: SDV; Dec: FVT
Yes | 49 | CG15 | TBD | L3X0 15" AMD Hawk Point RefreshH45 + NV GPU | Gaming | P | C38 | NB | July: SDV; Aug: SDV; Sep: SDV; Oct: SDV; Nov: FVT; Dec: SIT
No | 50 | CG15 | JLY10 | Win11 24H2 OSR_JLY10 Y590s 16" Intel RPL HX55 | Gaming | E | C38 | NB | Mar: OS-R; Apr: OS-R; May: OS-R; Jun: OS-R
No | 51 | CG15 | ILYGA | Win11 24H2 OSR_ILYGA Y790s 16“ Intel RPL HX55 | Gaming | E | C38 | NB | Mar: OS-R; Apr: OS-R; May: OS-R; Jun: OS-R
No | 52 | CG15 | JLG1012 | Win11 24H2 OSR_JLG1012 L390 15" Intel ADL & RPL HX55 | Gaming | E | C38 | NB | Mar: OS-R; Apr: OS-R; May: OS-R; Jun: OS-R
No | 53 | CG15 | JLG50 | Win11 24H2 OSR_JLG50 L390 15" AMD Hawk Point H45 | Gaming | E | C38 | NB | Mar: OS-R; Apr: OS-R; May: OS-R; Jun: OS-R
No | 54 | CG15 | JLY20 | Win11 24H2 OSR_JLY20 Y590s 16" AMD Hawk Point H45 | Gaming | E | C38 | NB | Apr: OS-R; May: OS-R; Jun: OS-R; July: OS-R
No | 55 | CG15 | JLY2R | Win11 24H2 OSR_JLY2R Y590s 16" AMD Rembrandt+ H45 | Gaming | E | C38 | NB | Apr: OS-R; May: OS-R; Jun: OS-R; July: OS-R
No | 56 | CG15 | JLG20 | Win11 24H2 OSR_JLG20 L390 15" Intel ADL-HX55 + Intel DG2 GPU | Gaming | E | C38 | NB | Apr: OS-R; May: OS-R; Jun: OS-R; July: OS-R
No | 57 | CG15 | GOG22 | Win11 24H2 OSR_GOG22 L360 -15ACH6 | Gaming | E | C38 | NB | Apr: OS-R; May: OS-R; Jun: OS-R; July: OS-R
No | 58 | CG15 | JLG52 | Win11 24H2 OSR_JLG52 L390 15" AMD Rembrandt+ H45 | Gaming | E | C38 | NB | Apr: OS-R; May: OS-R; Jun: OS-R; July: OS-R
No | 59 | CG13 | HLC3D | Win11 24H2 OSR_HLC3D C680-13ABR | Consumer | E | C38 | NB | Mar: OS-R; Apr: OS-R; May: OS-R; Jun: OS-R
No | 60 | CG13 | HLS1C1D | Win11 24H2 OSR_HLS1C1D S170-1415 AMD Mendocino | Consumer | E | C38 | NB | Mar: OS-R; Apr: OS-R; May: OS-R; Jun: OS-R
No | 61 | CG13 | HLS4A/ILS6A | Win11 24H2 OSR_HLS4A/ILS6A S580-1416 AMD Barcelo Refresh | Consumer | E | C38 | NB | Mar: OS-R; Apr: OS-R; May: OS-R; Jun: OS-R
No | 62 | CG13 | ILS4M6M | Win11 24H2 OSR_ILS4M6M S590_14/16 Intel MTL H28 | Consumer | E | C38 | NB | Mar: OS-R; Apr: OS-R; May: OS-R; Jun: OS-R
No | 63 | CG13 | JLS4R6R | Win11 24H2 OSR_JLS4R6R S590_1416" Intel RPL U15 refresh | Consumer | E | C38 | NB | Mar: OS-R; Apr: OS-R; May: OS-R; Jun: OS-R
No | 64 | CG13 | JLS5I5U | Win11 24H2 OSR_JLS5I S590 15" Intel RPL H45& U15 | Consumer | E | C38 | NB | Mar: OS-R; Apr: OS-R; May: OS-R; Jun: OS-R
No | 65 | CG13 | ILS4P6P | Win11 24H2 OSR_ILS4P6P S590 1416" AMD Hawk Point | Consumer | E | C38 | NB | Mar: OS-R; Apr: OS-R; May: OS-R; Jun: OS-R
No | 66 | CG13 | HLS4I/ILS6I ILS4H/6H | Win11_24H2 OSR_S580-1416 IRL,IAH | Consumer | E | C38 | NB | Apr: OS-R; May: OS-R; Jun: OS-R; July: OS-R
No | 67 | CG5 | ILVP4P6 | Win11 24H2 OSR_TB Gen6+ 14"16" AMD Hawk Point | SMB | E | C38 | NB | Apr: OS-R; May: OS-R; Jun: OS-R
No | 68 | CG5 | ILVR4 | Win11 24H2 OSR_TB Gen6+ 14" Intel Meteor Lake | SMB | E | C38 | NB | July: OS-R; Aug: OS-R
No | 69 | CG5 | ILVR6 | Win11 24H2 OSR_TB Gen6+ 16" Intel Meteor Lake | SMB | E | C38 | NB | July: OS-R; Aug: OS-R
Yes | 1 | CG13 | JMMI4 | T89 Modern 14" Intel RPL-U | Consumer | E | T89 | NB | May: SIT; Jun: SIT; July: SIT; Aug: SOVP/SS
Yes | 2 | CG13 | JMMI5 | T89 Modern 15" Intel RPL-U | Consumer | E | T89 | NB | May: SIT; Jun: SIT; July: SIT; Aug: SOVP/SS
No | 3 | CG13 | JMMI3 | T89 Modern 13" Intel RPL-U | Consumer | E | T89 | NB | Jun: SIT; July: SIT; Aug: SIT; Sep: SOVP/SS
Yes | 1 | CG15 | JOC10 | AIO 390 24" Intel Raptor Lake H/P/U | AIO | E | C38 | AIO | Jan: OOC
Yes | 2 | CG15 | JOC70 | AIO 390 27" Intel Raptor Lake H/P/U | AIO | E | C38 | AIO | Jan: OOC
Yes | 3 | CG15 | JOC20 | AIO 390 24" AMD Rembrandt_R | AIO | E | C38 | AIO | Jan: OOC
Yes | 4 | CG15 | JOC72 | AIO 390 27" AMD Rembrandt_R | AIO | E | C38 | AIO | Jan: OOC
Yes | 5 | CG15 | JOY10 | Neo 50a 24" Gen5 Intel Raptor Lake H/P/U | AIO | E | C38 | AIO | Jan: OOC
Yes | 6 | CG15 | JOY70 | Neo 50a 27" Gen5 Intel Raptor Lake H/P/U | AIO | E | C38 | AIO | Jan: OOC
Yes | 7 | CG15 | JOK10 | QT A970 24" Intel Raptor Lake U/H | AIO | E | C38 | AIO | Jan: SIT
Yes | 8 | CG15 | KOC20 | AIO 3X0 24" AMD Hawk Point U | AIO | E | C38 | AIO | Apr: SDV; May: SDV; Jun: SIT; July: SIT; Aug: SOVP/SS
Yes | 9 | CG15 | KOC72 | AIO 3X0 27" AMD Hawk Point U | AIO | E | C38 | AIO | Apr: SDV; May: SDV; Jun: SIT; July: SIT; Aug: SOVP/SS
No | 10 | CG15 | KOL30 | Fighting Model AIO 24" | AIO | P | C38 | AIO | May: SDV; Jun: SDV; July: SIT; Aug: SIT; Sep: SOVP/SS
Yes | 11 | CG15 | JOG32 | Yoga 9 32" Refresh Intel Lunar Lake | AIO | P | C38 | AIO | July: SDV; Aug: SDV; Sep: FVT; Oct: FVT; Nov: SIT; Dec: SIT
Yes | 12 | CG15 | KOC10 | AIO 3X0 24" Intel Meteor Lake H/P/U | AIO | P | C38 | AIO | Jun: SDV; July: SDV; Aug: SDV; Sep: SIT; Oct: SIT; Nov: SVT; Dec: SOVP/SS
Yes | 13 | CG15 | KOC70 | AIO 3X0 27" Intel Meteor Lake H/P/U | AIO | P | C38 | AIO | Jun: SDV; July: SDV; Aug: SDV; Sep: SIT; Oct: SIT; Nov: SVT; Dec: SOVP/SS
Yes | 14 | CG15 | KOC71 | AIO 3X0 27" QHD Intel Meteor Lake H/P/U | AIO | P | C38 | AIO | Jun: SDV; July: SDV; Aug: SDV; Sep: SIT; Oct: SIT; Nov: SVT; Dec: SOVP/SS
Yes | 15 | CG15 | KOY10 | Neo 50a 24" Gen6 Intel Meteor Lake H/P/U | AIO | P | C38 | AIO | Jun: SDV; July: SDV; Aug: SDV; Sep: SIT; Oct: SIT; Nov: SVT; Dec: SOVP/SS
Yes | 16 | CG15 | KOY70 | Neo 50a 27" Gen6 Intel Meteor Lake H/P/U | AIO | P | C38 | AIO | Jun: SDV; July: SDV; Aug: SDV; Sep: SIT; Oct: SIT; Nov: SVT; Dec: SOVP/SS
Yes | 17 | CG15 | KOK10 | QT A970 24" Intel Meteor Lake U/H | AIO | P | C38 | AIO | Jun: SDV; July: SDV; Aug: SDV; Sep: SIT; Oct: SIT; Nov: SVT; Dec: SOVP/SS
No | 18 | Type-2 | KOA70 | Yoga AIO 7 27" Intel Meter Lake | AIO | P | C38 | AIO | July: SDV; Aug: SDV; Sep: FVT; Oct: FVT; Nov: SIT; Dec: SIT
No | 19 | Type-2 | KOA70 | Yoga AIO 7 27" Intel Arrow Lake + NV GPU | AIO | P | C38 | AIO | July: SDV; Aug: SDV; Sep: SDV; Oct: FVT; Nov: FVT; Dec: SIT
No | 20 | CG15 | JOC10/70 | AIO 390 24"/27“ Intel Raptor Lake H/P/U | AIO | E | C38 | AIO | Mar: OS-R; Apr: OS-R; May: OS-R; Jun: OS-R
No | 21 | CG15 | JOC20/72 | AIO 390 24" /27" AMD Rembrandt_R | AIO | P | C38 | AIO | May: OS-R; Jun: OS-R
No | 22 | CG15 | JOY10/70 | Neo 50a 24" /27" Gen5 Intel Raptor Lake H/P/U | AIO | E | C38 | AIO | Mar: OS-R; Apr: OS-R; May: OS-R; Jun: OS-R
No | 23 | CG15 | JOK10 | QT A970 24" Intel Raptor Lake U/H 23H2 | AIO | P | C38 | AIO | May: OS-R; Jun: OS-R
No | 24 | CG15 | JOK10 | QT A970 24" Intel Raptor Lake U/H 24H2 | AIO | P | C38 | AIO | Jun: OS-R; July: OS-R
No | 25 | CG15 | JOC71 | AIO 390 27" Intel Raptor Lake H/P/U QHD | AIO | P | C38 | AIO | May: OS-R; Jun: OS-R
No | 26 | CG15 | IOG32 | Yoga 9 32" Intel Raptor Lake | AIO | P | C38 | AIO | May: OS-R; Jun: OS-R
No | 27 | CG15 | IOC30/31/73 | AIO 370 Refresh 24"/22"/27" Intel RPL-P Refresh | AIO | P | C38 | AIO | Jun: OS-R; July: OS-R
No | 28 | CG15 | IOB10/70 | AIO 570 Refresh 24"/27" Intel Raptor Lake H | AIO | P | C38 | AIO | Jun: OS-R; July: OS-R
No | 29 | CG15 | IOY10 | Neo 50a 24" Gen4 Intel Raptor Lake | AIO | P | C38 | AIO | Jun: OS-R; July: OS-R
No | 30 | CG15 | IOY50 | A600 24IRH | AIO | P | C38 | AIO | Jun: OS-R; July: OS-R
No | 31 | CG15 | HOC10/11/70 | AIO 370 -24/22/27 Intel ADL-P | AIO | P | C38 | AIO | July: OS-R; Aug: OS-R
No | 32 | CG15 | IOC60/76 | AIO 360 Refresh 24"/27" AMD Barcelo Refresh | AIO | P | C38 | AIO | July: OS-R; Aug: OS-R
|  | Plan (w/ OOC): | 基於年度預算時RD Project Plan
1. 多個機種合併的，按照project code分開
|  |  | 2. Final版中移除(灰底)以及T12專案，相關專案資料已刪除 |  |  | 預算 (含OOC) |  | FVT | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 5 | 15 | 15 | 0 | 0
|  |  | 3. 年度人力預算時，有估OOC需求的，請填入相應的機種&月份 |  |  |  |  | SIT | 0 | 0 | 5 | 1 | 1 | 1 | 1 | 4 | 14 | 14 | 15 | 4
[8 empty] | OOC | 17 | 11 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2024 Project Plan (with OOC)
| No. | CG | Compal Model | Customer Model | Marketing type (Commercial / Consumer) | Status: Planning =P Executing=E | Customer | Product Type (NB/PAD/AIO/IPC) | Jan | Feb | Mar | Apr | May | Jun | July | Aug | Sep | Oct | Nov | Dec
| 1 | CG13 | ILVR4 | TB Gen6+ 14" Intel Meteor Lake 16:10 (Skip Via) (IPCM) | SMB/Commercial | E | C38 | NB | Jan: OOC; Feb: OOC | OOC按照SOVP& SS+1 估了兩個月
| 2 | CG13 | ILVR6 | TB Gen6+ 16" Intel Meteor Lake 16:10 (IPCM) | SMB/Commercial | E | C38 | NB | Jan: OOC; Feb: OOC
| 3 | CG13 | ILVP4 | TB Gen6+ 14" AMD Hawk Point 16:10 (IPCM) | SMB/Commercial | E | C38 | NB | Jan: OOC; Feb: OOC
| 3 | CG13 | ILVP6 | TB Gen6+ 16" AMD Hawk Point 16:10 (IPCM) | SMB/Commercial | E | C38 | NB | Jan: OOC; Feb: OOC
| 4 | CG13 | JLVI4 | Next Gen: TB Gen6+ 14" Intel Arrow Lake-H 16:10 (IPCM) | SMB/Commercial | P | C38 | NB | PCR | PCR | PCR | Kick Off | Kick Off | SDV | SDV | FVT | FVT | FVT | SIT | SIT
| 4 | CG13 | JLVI6 | Next Gen: TB Gen6+ 16" Intel Arrow Lake-H 16:10 (IPCM) | SMB/Commercial | P | C38 | NB | PCR | PCR | PCR | Kick Off | Kick Off | SDV | SDV | FVT | FVT | FVT | SIT | SIT
| 5 | CG13 | JLVA4 | Next Gen: TB Gen6+ 14" AMD KracKen 16:10 (IPCM) | SMB/Commercial | P | C38 | NB | PCR | PCR | PCR | Kick Off | Kick Off | Kick Off | SDV | SDV | FVT | FVT | SIT | SIT
| 5 | CG13 | JLVA6 | Next Gen: TB Gen6+ 16" AMD KracKen 16:10 (IPCM) | SMB/Commercial | P | C38 | NB | PCR | PCR | PCR | Kick Off | Kick Off | Kick Off | SDV | SDV | FVT | FVT | SIT | SIT
| 6 | CG13 | TBD | Chrome 11.6"/14" Intel Twin Lake-N 6W~15w | SMB/Commercial | P | C38 | NB
| 7 | CG13 | IWAP6 IWAP7 IWAP8 | T12 Syrah 13"/14"/15" RPL -R | SMB/Commercial | P | T12 | NB | bar: Jan to Mar
| 8 | CG13 | JWADA | T12 Chrome 10.1" Detachable MTK8186 | SMB/Commercial | P | T12 | NB
| 9 | CG13 | JWACB | T12 Chrome 11.6" Convertible MTK8186 | SMB/Commercial | P | T12 | NB
| 10 | CG13 | JMMI4 | T89 Modern 14" Intel RPL-U | SMB/Commercial | P | T89 | NB | Jan: PreMP/SS
| 10 | CG13 | JMMI5 | T89 Modern 15" Intel RPL-U | SMB/Commercial | P | T89 | NB | Jan: PreMP/SS
| 11 | CG13 | JMMR4 | T89 Modern 14" Intel RPL-R | SMB/Commercial | P | T89 | NB | Jan: Kick Off; Feb: Kick Off; Mar: SIT; Apr: Pre-MP; May: SS
| 11 | CG13 | JMMR5 | T89 Modern 15" Intel RPL-R | SMB/Commercial | P | T89 | NB | Jan: Kick Off; Feb: Kick Off; Mar: SIT; Apr: Pre-MP; May: SS
| 12 | CG13 | JMMA4 | T89 Modern 14"AMD BRC-R | SMB/Commercial | P | T89 | NB | Jan: Kick Off; Feb: Kick Off; Mar: SIT; Apr: Pre-MP; May: SS
| 12 | CG13 | JMMA5 | T89 Modern 15" AMD LCN | SMB/Commercial | P | T89 | NB | Jan: Kick Off; Feb: Kick Off; Mar: SIT; Apr: Pre-MP; May: SS
| 13 | CG13 | ILS4M | S590 14" Intel MTL H28 (Plastic/Metal) | Consumer | E | C38 | NB | Jan: OOC; Feb: OOC
| 14 | CG13 | ILS6M | S590 16" Intel MTL H28 (Plastic/Metal) | Consumer | E | C38 | NB | Jan: OOC; Feb: OOC
| 15 | CG13 | ILS4P | S590 14" AMD Hawk Point (Plastic/Metal) (IPCM) | Consumer | E | C38 | NB | Jan: OOC; Feb: OOC; Mar: OOC
| 16 | CG13 | ILS6P | S590 16" AMD Hawk Point (Plastic/Metal) (IPCM) | Consumer | E | C38 | NB | Jan: OOC; Feb: OOC; Mar: OOC
| 17 | CG13 | JLS4R | S590 14" RPL-U Refresh | Consumer | E | C38 | NB | Jan: OOC; Feb: OOC; Mar: OOC
| 18 | CG13 | JLS6R | S590 16" RPL-U Refresh | Consumer | E | C38 | NB | Jan: OOC; Feb: OOC; Mar: OOC
| 19 | CG13 | JLS5I | S590 15.3" Intel RPL (IPCM) | Consumer | E | C38 | NB | Jan: OOC; Feb: OOC
| 16 | CG13 | JLSI3 | Next Gen: S5X0 13" Intel Arrow Lake | Consumer | P | C38 | NB | RFI | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | FVT | FVT | SIT | SVT
| 16 | CG13 | JLSI5 | Next Gen: S5X0 15" Intel Arrow Lake | Consumer | P | C38 | NB | RFI | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | FVT | FVT | SIT | SVT
| 17 | CG13 | TBD | Next Gen: S5X0 13"/15" AMD KracKen | Consumer | P | C38 | NB
| 18 | CG13 | JLSI4I | Next Gen: S5X0 14" Intel Arrow Lake | Consumer | P | C38 | NB | RFI | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | FVT | FVT | SIT | SVT
| 18 | CG13 | JLSI6 | Next Gen: S5X0 16" Intel Arrow Lake | Consumer | P | C38 | NB | RFI | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | FVT | FVT | SIT | SVT
| 19 | CG13 | JLSA4 | Next Gen: S5X0 14" AMD KracKen | Consumer | P | C38 | NB | RFI | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | FVT | FVT | SIT | SVT
| 19 | CG13 | JLSA6 | Next Gen: S5X0 16" AMD KracKen | Consumer | P | C38 | NB | RFI | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | FVT | FVT | SIT | SVT
| 20 | CG13 | JL7I4 | C7 GenX 14" Intel Arrow Lake | Consumer | P | C38 | NB | RFI | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | FVT | FVT | SIT | SVT
| 20 | CG13 | JL7I6 | C7 GenX 16" Intel Arrow Lake | Consumer | P | C38 | NB | RFI | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | FVT | FVT | SIT | SVT
| 21 | CG13 | JL7A4 | C7 GenX 14" AMD KracKen | Consumer | P | C38 | NB | RFI | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | FVT | FVT | SIT | SVT
| 21 | CG13 | JL7A6 | C7 GenX 16" AMD KracKen | Consumer | P | C38 | NB | RFI | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | FVT | FVT | SIT | SVT
| 22 | CG15 | JLG50 | L390 15" AMD Hawk Point H45 + NV GPU (PCR) | Gaming | E | C38 | NB | Jan: SOVP/SS
| 23 | CG15 | KLG10 | L3X0 15" Intel RPL Refresh HX55 + NV GPU | Gaming | P | C38 | NB | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | FVT | SIT | SVT | SOVP/SS
| 24 | CG15 | KLG50 | L3X0 15" AMD Strix Point H45 + NV GPU | Gaming | P | C38 | NB | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | SIT | SIT | SIT | SVT | SOVP/SS
| 25 | CG15 | KLG20 | L3X0 15" Intel RPL Refresh HX55 + Intel DG2 GPU | Gaming | P | C38 | NB | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | SIT | SVT | SOVP/SS
| 26 | CG15 | JLY20 | Y590s 16" AMD Hawk Point H45 + NV GPU (PCR) | Gaming | E | C38 | NB | bar: Jan
| 27 | CG15 | JLY20 | Y590s 16" AMD Rembrandt-H + NV GPU (PCR) | Gaming | P | C38 | NB | Jan: SVT; Feb: SOVP; Mar: SS
| 28 | CG15 | KLY10 | Y5X0s 16" Intel Raptor Lake Refresh HX55 + NV GPU | Gaming | P | C38 | NB | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | FVT | SIT | SIT | SVT | SOVP/SS
| 29 | CG15 | KLY50 | Y5X0s 16" AMD Strix Point H45 + NV GPU | Gaming | P | C38 | NB | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | SIT | SIT | SIT | SVT | SOVP/SS
| 30 | CG15 | KLYGA | Y7X0s 16" Intel Raptor Lake Refresh HX55 + NV GPU | Gaming | P | C38 | NB | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | FVT | SIT | SIT | SVT | SOVP/SS
| 31 | CG15 | JOC10 | AIO 390 24" Intel Raptor Lake H/P/U | AIO | E | C38 | AIO | Jan: OOC
| 31 | CG15 | JOC70 | AIO 390 27" Intel Raptor Lake H/P/U | AIO | E | C38 | AIO | Jan: OOC
| 32 | CG15 | JOC20 | AIO 390 24" AMD Rembrandt_R | AIO | E | C38 | AIO | Jan: OOC
| 32 | CG15 | JOC72 | AIO 390 27" AMD Rembrandt_R | AIO | E | C38 | AIO | Jan: OOC
| 33 | CG15 | KOC10 | AIO 3X0 24" Intel Meteor Lake H/P/U | AIO | P | C38 | AIO | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | SDV | SIT | SIT | SVT | SOVP/SS
| 33 | CG15 | KOC70 | AIO 3X0 27" Intel Meteor Lake H/P/U | AIO | P | C38 | AIO | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | SDV | SIT | SIT | SVT | SOVP/SS
| 34 | CG15 | KOC71 | AIO 3X0 27" QHD Intel Meteor Lake H/P/U | AIO | P | C38 | AIO | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | SDV | SIT | SIT | SVT | SOVP/SS
| 35 | CG15 | KOC20 | AIO 3X0 24" AMD Hawk Point U | AIO | P | C38 | AIO | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | SDV | SIT | SIT | SVT | SOVP/SS
| 35 | CG15 | KOC72 | AIO 3X0 27" AMD Hawk Point U | AIO | P | C38 | AIO | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | SDV | SIT | SIT | SVT | SOVP/SS
| 36 | CG15 | JOY10 | Neo 50a 24" Gen5 Intel Raptor Lake H/P/U | AIO | E | C38 | AIO | Jan: OOC
| 36 | CG15 | JOY70 | Neo 50a 27" Gen5 Intel Raptor Lake H/P/U | AIO | E | C38 | AIO | Jan: OOC
| 37 | CG15 | KOY10 | Neo 50a 24" Gen6 Intel Meteor Lake H/P/U | AIO | P | C38 | AIO | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | SDV | SIT | SIT | SVT | SOVP/SS
| 37 | CG15 | KOY70 | Neo 50a 27" Gen6 Intel Meteor Lake H/P/U | AIO | P | C38 | AIO | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | SDV | SIT | SIT | SVT | SOVP/SS
| 38 | CG15 | JOK10 | QT A970 24" Intel Raptor Lake U/H | AIO | E | C38 | AIO | Jan: SVT/SS
| 39 | CG15 | KOK10 | QT A970 24" Intel Meteor Lake U/H | AIO | P | C38 | AIO | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | SDV | SIT | SIT | SVT | SOVP/SS
| 40 | CG15 | JOG32 | Yoga 9 32" Refresh Intel Lunar Lake | AIO | E | C38 | AIO | Kick Off | SDV | SDV | SDV | FVT | FVT | FVT | FVT | SIT | SIT | SVT | SOVP/SS
| 41 | CG15 | KOA32 | 32" Bendable AIO Intel Meteor Lake H | AIO | P | C38 | AIO |  |  | RFQ | RFQ | RFQ | Kick Off | SDV | SDV | FVT | FVT | SIT | SVT
| 42 | CG15 | KLG00 | SFF Gaming DT 2L Intel-RPL HX + NV GPU | DT | P | C38 | DT
| 43 | CG5 | JLSVB | Server (Venice -AMD) L10 commodity, 2400W | Server | P | C38 | Server | Design Join | Design Join | SIT | SIT | SIT | SIT | SIT | SVT | SVT | SVT | SVT | SOVP/SS
| 44 | CG5 | JLSVA | Server (BHS MS "Perth" Intel) Birch Stream platform 1U/2U | Server | P | C38 | Server | RFI | RFQ | RFQ | RFQ | Kick Off | SDV | SDV | SDV | SIT | SIT | SVT | SOVP/SS
|  | Plan (w/o OOC): | 基於年度預算時RD Project Plan
|  |  | 1. 多個機種合併的，按照project code分開 |  |  | 預算 (不含OOC) |  | FVT | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 5 | 15 | 15 | 0 | 0
|  |  | 2. Final版中移除(灰底)以及T12專案，相關專案資料已刪除 |  |  |  |  | SIT | 0 | 0 | 5 | 1 | 1 | 1 | 1 | 4 | 14 | 14 | 15 | 4
[8 empty] | OOC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2024 Project Plan (w/o OOC)
| No. | CG | Compal Model | Customer Model | Marketing type (Commercial / Consumer) | Status: Planning =P Executing=E | Customer | Product Type (NB/PAD/AIO/IPC) | Jan | Feb | Mar | Apr | May | Jun | July | Aug | Sep | Oct | Nov | Dec
| 1 | CG13 | ILVR4 | TB Gen6+ 14" Intel Meteor Lake 16:10 (Skip Via) (IPCM) | SMB/Commercial | E | C38 | NB | [12 empty] | SS pull in to 2023/12 | bar: Jan
| 2 | CG13 | ILVR6 | TB Gen6+ 16" Intel Meteor Lake 16:10 (IPCM) | SMB/Commercial | E | C38 | NB | Jan: SVT/SOVP/SS
| 3 | CG13 | ILVP4 | TB Gen6+ 14" AMD Hawk Point 16:10 (IPCM) | SMB/Commercial | E | C38 | NB | Jan: SVT/SOVP/SS
| 3 | CG13 | ILVP6 | TB Gen6+ 16" AMD Hawk Point 16:10 (IPCM) | SMB/Commercial | E | C38 | NB | Jan: SVT/SOVP/SS
| 4 | CG13 | JLVI4 | Next Gen: TB Gen6+ 14" Intel Arrow Lake-H 16:10 (IPCM) | SMB/Commercial | P | C38 | NB | PCR | PCR | PCR | Kick Off | Kick Off | SDV | SDV | FVT | FVT | FVT | SIT | SIT
| 4 | CG13 | JLVI6 | Next Gen: TB Gen6+ 16" Intel Arrow Lake-H 16:10 (IPCM) | SMB/Commercial | P | C38 | NB | PCR | PCR | PCR | Kick Off | Kick Off | SDV | SDV | FVT | FVT | FVT | SIT | SIT
| 5 | CG13 | JLVA4 | Next Gen: TB Gen6+ 14" AMD KracKen 16:10 (IPCM) | SMB/Commercial | P | C38 | NB | PCR | PCR | PCR | Kick Off | Kick Off | Kick Off | SDV | SDV | FVT | FVT | SIT | SIT
| 5 | CG13 | JLVA6 | Next Gen: TB Gen6+ 16" AMD KracKen 16:10 (IPCM) | SMB/Commercial | P | C38 | NB | PCR | PCR | PCR | Kick Off | Kick Off | Kick Off | SDV | SDV | FVT | FVT | SIT | SIT
| 6 | CG13 | TBD | Chrome 11.6"/14" Intel Twin Lake-N 6W~15w | SMB/Commercial | P | C38 | NB
| 7 | CG13 | IWAP6 IWAP7 IWAP8 | T12 Syrah 13"/14"/15" RPL -R | SMB/Commercial | P | T12 | NB | bar: Jan to Mar
| 8 | CG13 | JWADA | T12 Chrome 10.1" Detachable MTK8186 | SMB/Commercial | P | T12 | NB
| 9 | CG13 | JWACB | T12 Chrome 11.6" Convertible MTK8186 | SMB/Commercial | P | T12 | NB
| 10 | CG13 | JMMI4 | T89 Modern 14" Intel RPL-U | SMB/Commercial | P | T89 | NB | Jan: Pre-MP/SS
| 10 | CG13 | JMMI5 | T89 Modern 15" Intel RPL-U | SMB/Commercial | P | T89 | NB | Jan: Pre-MP/SS
| 11 | CG13 | JMMR4 | T89 Modern 14" Intel RPL-R | SMB/Commercial | P | T89 | NB | Jan: Kick Off; Feb: Kick Off; Mar: SIT; Apr: Pre-MP; May: SS
| 11 | CG13 | JMMR5 | T89 Modern 15" Intel RPL-R | SMB/Commercial | P | T89 | NB | Jan: Kick Off; Feb: Kick Off; Mar: SIT; Apr: Pre-MP; May: SS
| 12 | CG13 | JMMA4 | T89 Modern 14"AMD BRC-R | SMB/Commercial | P | T89 | NB | Jan: Kick Off; Feb: Kick Off; Mar: SIT; Apr: Pre-MP; May: SS
| 12 | CG13 | JMMA5 | T89 Modern 15" AMD LCN | SMB/Commercial | P | T89 | NB | Jan: Kick Off; Feb: Kick Off; Mar: SIT; Apr: Pre-MP; May: SS
| 13 | CG13 | ILS4P | S590 14" AMD Hawk Point (Plastic/Metal) (IPCM) | Consumer | E | C38 | NB | Jan: SVT/SOVP; Feb: SS
| 13 | CG13 | ILS6P | S590 16" AMD Hawk Point (Plastic/Metal) (IPCM) | Consumer | E | C38 | NB | Jan: SVT/SOVP; Feb: SS
| 14 | CG13 | JLS4R | S590 14" RPL-U Refresh | Consumer | E | C38 | NB | Jan: SVT/SOVP; Feb: SS
| 14 | CG13 | JLS6R | S590 16" RPL-U Refresh | Consumer | E | C38 | NB | Jan: SVT/SOVP; Feb: SS
| 15 | CG13 | JLS5I | S590 15.3" Intel RPL (IPCM) | Consumer | E | C38 | NB | Jan: SVT/SOVP; Feb: SS
| 16 | CG13 | JLSI3 | Next Gen: S5X0 13" Intel Arrow Lake | Consumer | P | C38 | NB | RFI | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | FVT | FVT | SIT | SVT
| 16 | CG13 | JLSI5 | Next Gen: S5X0 15" Intel Arrow Lake | Consumer | P | C38 | NB | RFI | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | FVT | FVT | SIT | SVT
| 17 | CG13 | TBD | Next Gen: S5X0 13"/15" AMD KracKen | Consumer | P | C38 | NB
| 18 | CG13 | JLSI4I | Next Gen: S5X0 14" Intel Arrow Lake | Consumer | P | C38 | NB | RFI | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | FVT | FVT | SIT | SVT
| 18 | CG13 | JLSI6 | Next Gen: S5X0 16" Intel Arrow Lake | Consumer | P | C38 | NB | RFI | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | FVT | FVT | SIT | SVT
| 19 | CG13 | JLSA4 | Next Gen: S5X0 14" AMD KracKen | Consumer | P | C38 | NB | RFI | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | FVT | FVT | SIT | SVT
| 19 | CG13 | JLSA6 | Next Gen: S5X0 16" AMD KracKen | Consumer | P | C38 | NB | RFI | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | FVT | FVT | SIT | SVT
| 20 | CG13 | JL7I4 | C7 GenX 14" Intel Arrow Lake | Consumer | P | C38 | NB | RFI | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | FVT | FVT | SIT | SVT
| 20 | CG13 | JL7I6 | C7 GenX 16" Intel Arrow Lake | Consumer | P | C38 | NB | RFI | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | FVT | FVT | SIT | SVT
| 21 | CG13 | JL7A4 | C7 GenX 14" AMD KracKen | Consumer | P | C38 | NB | RFI | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | FVT | FVT | SIT | SVT
| 21 | CG13 | JL7A6 | C7 GenX 16" AMD KracKen | Consumer | P | C38 | NB | RFI | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | FVT | FVT | SIT | SVT
| 22 | CG15 | JLG50 | L390 15" AMD Hawk Point H45 + NV GPU (PCR) | Gaming | E | C38 | NB | Jan: SOVP/SS
| 23 | CG15 | KLG10 | L3X0 15" Intel RPL Refresh HX55 + NV GPU | Gaming | P | C38 | NB | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | FVT | SIT | SVT | SOVP/SS
| 24 | CG15 | KLG50 | L3X0 15" AMD Strix Point H45 + NV GPU | Gaming | P | C38 | NB | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | SIT | SIT | SIT | SVT | SOVP/SS
| 25 | CG15 | KLG20 | L3X0 15" Intel RPL Refresh HX55 + Intel DG2 GPU | Gaming | P | C38 | NB | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | SIT | SVT | SOVP/SS
| 26 | CG15 | JLY20 | Y590s 16" AMD Hawk Point H45 + NV GPU (PCR) | Gaming | E | C38 | NB | bar: Jan
| 27 | CG15 | JLY20 | Y590s 16" AMD Rembrandt-H + NV GPU (PCR) | Gaming | P | C38 | NB | Jan: SVT; Feb: SOVP; Mar: SS
| 28 | CG15 | KLY10 | Y5X0s 16" Intel Raptor Lake Refresh HX55 + NV GPU | Gaming | P | C38 | NB | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | FVT | SIT | SIT | SVT | SOVP/SS
| 29 | CG15 | KLY50 | Y5X0s 16" AMD Strix Point H45 + NV GPU | Gaming | P | C38 | NB | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | SIT | SIT | SIT | SVT | SOVP/SS
| 30 | CG15 | KLYGA | Y7X0s 16" Intel Raptor Lake Refresh HX55 + NV GPU | Gaming | P | C38 | NB | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | FVT | SIT | SIT | SVT | SOVP/SS
| 31 | CG15 | JOC10 | AIO 390 24" Intel Raptor Lake H/P/U | AIO | E | C38 | AIO | Jan: SOVP/SS
| 31 | CG15 | JOC70 | AIO 390 27" Intel Raptor Lake H/P/U | AIO | E | C38 | AIO | Jan: SOVP/SS
| 32 | CG15 | JOC20 | AIO 390 24" AMD Rembrandt_R | AIO | E | C38 | AIO | Jan: SOVP/SS
| 32 | CG15 | JOC72 | AIO 390 27" AMD Rembrandt_R | AIO | E | C38 | AIO | Jan: SOVP/SS
| 33 | CG15 | KOC10 | AIO 3X0 24" Intel Meteor Lake H/P/U | AIO | P | C38 | AIO | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | SDV | SIT | SIT | SVT | SOVP/SS
| 33 | CG15 | KOC70 | AIO 3X0 27" Intel Meteor Lake H/P/U | AIO | P | C38 | AIO | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | SDV | SIT | SIT | SVT | SOVP/SS
| 34 | CG15 | KOC71 | AIO 3X0 27" QHD Intel Meteor Lake H/P/U | AIO | P | C38 | AIO | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | SDV | SIT | SIT | SVT | SOVP/SS
| 35 | CG15 | KOC20 | AIO 3X0 24" AMD Hawk Point U | AIO | P | C38 | AIO | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | SDV | SIT | SIT | SVT | SOVP/SS
| 35 | CG15 | KOC72 | AIO 3X0 27" AMD Hawk Point U | AIO | P | C38 | AIO | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | SDV | SIT | SIT | SVT | SOVP/SS
| 36 | CG15 | JOY10 | Neo 50a 24" Gen5 Intel Raptor Lake H/P/U | AIO | E | C38 | AIO | Jan: SOVP/SS
| 36 | CG15 | JOY70 | Neo 50a 27" Gen5 Intel Raptor Lake H/P/U | AIO | E | C38 | AIO | Jan: SOVP/SS
| 37 | CG15 | KOY10 | Neo 50a 24" Gen6 Intel Meteor Lake H/P/U | AIO | P | C38 | AIO | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | SDV | SIT | SIT | SVT | SOVP/SS
| 37 | CG15 | KOY70 | Neo 50a 27" Gen6 Intel Meteor Lake H/P/U | AIO | P | C38 | AIO | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | SDV | SIT | SIT | SVT | SOVP/SS
| 38 | CG15 | JOK10 | QT A970 24" Intel Raptor Lake U/H | AIO | E | C38 | AIO | Jan: SVT/SS
| 39 | CG15 | KOK10 | QT A970 24" Intel Meteor Lake U/H | AIO | P | C38 | AIO | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | SDV | SIT | SIT | SVT | SOVP/SS
| 40 | CG15 | JOG32 | Yoga 9 32" Refresh Intel Lunar Lake | AIO | E | C38 | AIO | Kick Off | SDV | SDV | SDV | FVT | FVT | FVT | FVT | SIT | SIT | SVT | SOVP/SS
| 41 | CG15 | KOA32 | 32" Bendable AIO Intel Meteor Lake H | AIO | P | C38 | AIO |  |  | RFQ | RFQ | RFQ | Kick Off | SDV | SDV | FVT | FVT | SIT | SVT
| 42 | CG15 | KLG00 | SFF Gaming DT 2L Intel-RPL HX + NV GPU | DT | P | C38 | DT
| 43 | CG5 | JLSVB | Server (Venice -AMD) L10 commodity, 2400W | Server | P | C38 | Server | Design Join | Design Join | SIT | SIT | SIT | SIT | SIT | SVT | SVT | SVT | SVT | SOVP/SS
| 44 | CG5 | JLSVA | Server (BHS MS "Perth" Intel) Birch Stream platform 1U/2U | Server | P | C38 | Server | RFI | RFQ | RFQ | RFQ | Kick Off | SDV | SDV | SDV | SIT | SIT | SVT | SOVP/SS

## 2024 RD3 Project Plan(v1017)
2024 Project Plan
No. | CG | Compal Model | Customer Model | Marketing type (Commercial / Consumer) | Status: Planning =P Executing=E | Customer | Jan | Feb | Mar | Apr | May | Jun | July | Aug | Sep | Oct | Nov | Dec | Product Type (NB/PAD/AIO/IPC) | HW | ME
1 | CG13 | ILVR4 | TB Gen6+ 14" Intel Meteor Lake 16:10 (Skip Via) (IPCM) | SMB/Commercial | E | C38 | SS | [11 empty] | NB | 0 | 0 | SS pull in to 2023/12
2 | CG13 | ILVR6 | TB Gen6+ 16" Intel Meteor Lake 16:10 (IPCM) | SMB/Commercial | E | C38 | SVT/SOVP/SS | [11 empty] | NB | 1 | 0.5
3 | CG13 | ILVP4 ILVP6 | TB Gen6+ 14"&16" AMD Hawk Point 16:10 (IPCM) | SMB/Commercial | E | C38 | SVT/SOVP/SS | [11 empty] | NB | 1 | 0.5
4 | CG13 | JLVI4 JLVI6 | Next Gen: TB Gen6+ 14"&16" Intel Arrow Lake-H 16:10 (IPCM) | SMB/Commercial | P | C38 | PCR | PCR | PCR | Kick Off | Kick Off | SDV | SDV | FVT | FVT | FVT | SIT | SIT | NB | 2 | 0
5 | CG13 | JLVA4 JLVA6 | Next Gen: TB Gen6+ 14"&16" AMD KracKen 16:10 (IPCM) | SMB/Commercial | P | C38 | PCR | PCR | PCR | Kick Off | Kick Off | Kick Off | SDV | SDV | FVT | FVT | SIT | SIT | NB | 1 | 0
6 | CG13 | TBD | Chrome 11.6"/14" Intel Twin Lake-N 6W~15w | SMB/Commercial | P | C38 | [6 empty] | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | NB | 0 | 0
7 | CG13 | IWAP6 IWAP7 IWAP8 | T12 Syrah 13"/14"/15" RPL -R | SMB/Commercial | P | T12 | PVT | Pre-MP | SS | [9 empty] | NB | 0.5 | 0
8 | CG13 | JWADA | T12 Chrome 10.1" Detachable MTK8186 | SMB/Commercial | P | T12 | Kick Off | Kick Off | SDV | SDV | SDV | FVT | FVT | FVT | SIT | SIT | SVT | SOVP/SS | NB | 1 | 1
9 | CG13 | JWACB | T12 Chrome 11.6" Convertible MTK8186 | SMB/Commercial | P | T12 | Kick Off | Kick Off | SDV | SDV | SDV | FVT | FVT | FVT | SIT | SIT | SVT | SOVP/SS | NB | 0 | 0
10 | CG13 | JMMI4 JMMI5 | T89 Modern 14"/15" Intel RPL-U | SMB/Commercial | P | T89 | Pre-MP/SS | [11 empty] | NB | 0.5 | 1
11 | CG13 | JMMR4 JMMR5 | T89 Modern 14"/15" Intel RPL-R | SMB/Commercial | P | T89 | Kick Off | Kick Off | PVT | Pre-MP | SS | [7 empty] | NB | 0.5 | 0
12 | CG13 | JMMA4 JMMA5 | T89 Modern 14"AMD BRC-R/15" AMD LCN | SMB/Commercial | P | T89 | Kick Off | Kick Off | PVT | Pre-MP | SS | [7 empty] | NB | 0.5 | 0
13 | CG13 | ILS4P ILS6P | S590 14"/16" AMD Hawk Point (Plastic/Metal) (IPCM) | Consumer | E | C38 | SVT/SOVP | SS | [10 empty] | NB | 1.3 | 0.6
14 | CG13 | JLS4R JLS6R | S590 14"/16" RPL-U Refresh | Consumer | E | C38 | SVT/SOVP | SS | [10 empty] | NB | 0.5 | 0
15 | CG13 | JLS5I | S590 15.3" Intel RPL (IPCM) | Consumer | E | C38 | SVT/SOVP | SS | [10 empty] | NB | 1 | 1
16 | CG13 | JLSI3 JLSI5 | Next Gen: S5X0 13"/15" Intel Arrow Lake | Consumer | P | C38 | RFI | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | FVT | FVT | SIT | SVT | NB | 1 | 2
17 | CG13 | TBD | Next Gen: S5X0 13"/15" AMD KracKen | Consumer | P | C38 | RFI | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | FVT | FVT | SIT | SVT | NB | 0 | 0
18 | CG13 | JLSI4I JLSI6 | Next Gen: S5X0 14"/16" Intel Arrow Lake | Consumer | P | C38 | RFI | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | FVT | FVT | SIT | SVT | NB | 1 | 2
19 | CG13 | JLSA4 JLSA6 | Next Gen: S5X0 14"/16" AMD KracKen | Consumer | P | C38 | RFI | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | FVT | FVT | SIT | SVT | NB | 1 | 0
20 | CG13 | JL7I4 JL7I6 | C7 GenX 14"/16" Intel Arrow Lake | Consumer | P | C38 | RFI | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | FVT | FVT | SIT | SVT | NB | 2 | 2
21 | CG13 | JL7A4 JL7A6 | C7 GenX 14"/16" AMD KracKen | Consumer | P | C38 | RFI | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | FVT | FVT | SIT | SVT | NB | 0 | 0
22 | CG15 | JLG50 | L390 15" AMD Hawk Point H45 + NV GPU (PCR) | Gaming | E | C38 | SOVP/SS | [11 empty] | NB | 0.2 | 0.5
23 | CG15 | KLG10 | L3X0 15" Intel RPL Refresh HX55 + NV GPU | Gaming | P | C38 | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | FVT | SIT | SVT | SOVP/SS |  |  | NB | 1 | 1
24 | CG15 | KLG50 | L3X0 15" AMD Strix Point H45 + NV GPU | Gaming | P | C38 | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | SIT | SIT | SIT | SVT | SOVP/SS | NB | 1 | 0
25 | CG15 | KLG20 | L3X0 15" Intel RPL Refresh HX55 + Intel DG2 GPU | Gaming | P | C38 | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | SIT | SVT | SOVP/SS |  |  | NB | 1 | 0
26 | CG15 | JLY20 | Y590s 16" AMD Hawk Point H45 + NV GPU (PCR) | Gaming | E | C38 | SS | [11 empty] | NB | 0.2 | 0.5
27 | CG15 | JLY20 | Y590s 16" AMD Rembrandt-H + NV GPU (PCR) | Gaming | P | C38 | SVT | SOVP | SS | [9 empty] | NB | 0.5 | 0
28 | CG15 | KLY10 | Y5X0s 16" Intel Raptor Lake Refresh HX55 + NV GPU | Gaming | P | C38 | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | FVT | SIT | SIT | SVT | SOVP/SS | NB | 1 | 1
29 | CG15 | KLY50 | Y5X0s 16" AMD Strix Point H45 + NV GPU | Gaming | P | C38 | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | SIT | SIT | SIT | SVT | SOVP/SS | NB | 1 | 0
30 | CG15 | KLYGA | Y7X0s 16" Intel Raptor Lake Refresh HX55 + NV GPU | Gaming | P | C38 | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | FVT | SIT | SIT | SVT | SOVP/SS | NB | 0.5 | 1
31 | CG15 | JOC10 JOC70 | AIO 390 24"/27" Intel Raptor Lake H/P/U | AIO | E | C38 | SOVP/SS | [11 empty] | AIO | 0.2 | 0.5
32 | CG15 | JOC20 JOC72 | AIO 390 24"/27" AMD Rembrandt_R | AIO | E | C38 | SOVP/SS | [11 empty] | AIO | 0.2 | 0.5
33 | CG15 | KOC10 KOC70 | AIO 3X0 24"/27" Intel Meteor Lake H/P/U | AIO | P | C38 | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | SDV | SIT | SIT | SVT | SOVP/SS | AIO | 1 | 0
34 | CG15 | KOC71 | AIO 3X0 27" QHD Intel Meteor Lake H/P/U | AIO | P | C38 | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | SDV | SIT | SIT | SVT | SOVP/SS | AIO | 0.5 | 0
35 | CG15 | KOC20 KOC72 | AIO 3X0 24"/27" AMD Hawk Point U | AIO | P | C38 | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | SDV | SIT | SIT | SVT | SOVP/SS | AIO | 1 | 0
36 | CG15 | JOY10 JOY70 | Neo 50a 24"/27" Gen5 Intel Raptor Lake H/P/U | AIO | E | C38 | SOVP/SS | [11 empty] | AIO | 0.2 | 0.5
37 | CG15 | KOY10 KOY70 | Neo 50a 24"/27" Gen6 Intel Meteor Lake H/P/U | AIO | P | C38 | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | SDV | SIT | SIT | SVT | SOVP/SS | AIO | 0.5 | 0
38 | CG15 | JOK10 | QT A970 24" Intel Raptor Lake U/H | AIO | E | C38 | SVT/SS | [11 empty] | AIO | 0.2 | 0.5
39 | CG15 | KOK10 | QT A970 24" Intel Meteor Lake U/H | AIO | P | C38 | RFI | RFQ | RFQ | Kick Off | Kick Off | SDV | SDV | SDV | SIT | SIT | SVT | SOVP/SS | AIO | 0.5 | 0
40 | CG15 | JOG32 | Yoga 9 32" Refresh Intel Lunar Lake | AIO | E | C38 | Kick Off | SDV | SDV | SDV | FVT | FVT | FVT | SIT | SIT | SIT | SVT | SOVP/SS | AIO | 1 | 0.5
41 | CG15 | KOA32 | 32" Bendable AIO Intel Meteor Lake H | AIO | P | C38 |  |  | RFQ | RFQ | RFQ | Kick Off | SDV | SDV | FVT | FVT | SIT | SVT | AIO | 1 | 1.5
42 | CG15 | KLG00 | SFF Gaming DT 2L Intel-RPL HX + NV GPU | DT | P | C38 | Kick Off | SDV | SDV | SIT | SVT | SOVP/SS | [6 empty] | DT | 0 | 0
43 | CG5 | JLSVB | Server (Venice -AMD) L10 commodity, 2400W | Server | P | C38 | Design Join | Design Join | SIT | SIT | SIT | SIT | SIT | SVT | SVT | SVT | SVT | SOVP/SS | Server | 0.5 | 0.5
44 | CG5 | JLSVA | Server (BHS MS "Perth" Intel) Birch Stream platform 1U/2U | Server | P | C38 | RFI | RFQ | RFQ | RFQ | Kick Off | SDV | SDV | SDV | SIT | SIT | SVT | SOVP/SS | Server | 1 | 3
[20 empty] | 30 | 22.1